## 2020 me2
2020 Site | Due date | Date started | Date complete | Complete within tolerance | Duration (days) | Report received | Report delay (days) | Checked by | Sent to UKT | 2020-08-27
ABERDEEN AGI (Offtake) | 2020-07-15 | 2020-03-03 | 2020-03-06 | Y | 3 | 2020-03-10 | 4 | SS
Hume AGI (Offtake) | 2020-03-15 | 2020-03-09 | 2020-03-12 | Y | 3 | 2020-03-27 | 15 | SS | 2020-04-08
Soutra AGI (Offtake) | 2020-03-15 | 2020-03-30 | 2020-03-31 | Y | 1 | 2020-04-01 | 1 | SS | 2020-04-08
Ipsden A AGI (Offtake) | 2020-03-15 | 2020-04-06 | 2020-04-09 | Y | 3 | 2020-05-06 | 27 | SS | 2020-04-08
Ipsden B AGI (Offtake) | 2020-03-15 | 2020-05-11 | 2020-05-15 | Y | 4 | 2020-08-26 | 103 | SS | 2020-04-08
WYTCH FARM - Supply to 3rd Party | 2020-03-15 | 2020-04-20 | 2020-04-23 | Y | 3 | 2020-04-27 | 4 | SS | 2020-07-24
MITCHAM BIOMETHANE | 2020-03-15 | 2020-03-09 | 2020-03-12 | Y | 3 | 2020-03-17 | 5 | SS | 2020-07-24
Balgray AGI (Offtake) | 2020-04-15 | 2020-04-20 | 2020-04-21 | Y | 1 | 2020-04-24 | 3 | SS | 2020-07-24
GLENMAVIS (OFFTAKE) | 2020-04-15 | 2020-04-20 | 2020-04-21 | Y | 1 | 2020-04-22 | 1 | SS | 2020-07-24
Pitcairngreen AGI (Offtake) | 2020-04-15 | 2020-05-04 | 2020-05-05 | Y | 1 | 2020-05-11 | 6 | SS | 2020-07-24
ARLA BIOMETHANE BIO | 2020-04-15 |  |  |  | 0 |  | 0
Armadale AGI (Offtake) | 2020-05-01 | 2020-05-25 | 2020-05-26 | Y | 1 | 2020-05-28 | 2 | SS | 2020-07-24
Bathgate AGI (Offtake) | 2020-05-15 | 2020-05-11 | 2020-05-13 | Y | 2 | 2020-05-14 | 1 | SS | 2020-07-24
Careston AGI (Offtake) | 2020-05-15 | 2020-05-18 | 2020-05-19 | Y | 1 | 2020-05-20 | 1 | SS | 2020-07-24
Kinknockie AGI (Offtake) | 2020-05-15 | 2020-04-14 | 2020-04-16 | Y | 2 | 2020-04-20 | 4 | SS | 2020-07-24
Nether Howcleugh AGI (Offtake) | 2020-05-15 | 2020-04-27 | 2020-04-29 | Y | 2 | 2020-04-29 | 0 | SS | 2020-07-24
Winkfield AGI SE (Offtake) | 2020-05-15 | 2020-04-29 | 2020-05-04 | Y | 5 | 2020-05-14 | 10 | SS | 2020-07-24
Winkfield AGI SO (Offtake) | 2020-05-15 | 2020-04-16 | 2020-04-24 | Y | 8 | 2020-04-29 | 5 | SS | 2020-07-24
Mappowder AGI (Offtake) | 2020-05-15 | 2020-05-27 | 2020-05-28 | Y | 1 | 2020-05-29 | 1 | SS | 2020-07-24
Lockerbie AGI (Offtake) | 2020-06-15 | 2020-06-15 | 2020-06-16 | Y | 1 | 2020-06-29 | 13 | SS | 2020-07-24
Farningham AGI A End of Life (Offtake) | 2020-06-15 | 2020-05-11 | 2020-05-13 | Y | 2 | 2020-05-22 | 9 | SS | 2020-07-24
Farningham AGI B (Offtake) | 2020-06-15 | 2020-07-04 | 2020-07-16 | Y | 12 | 2020-07-23 | 7 | SS | 2020-07-24
Hardwick AGI (Offtake) | 2020-06-15 | 2020-06-02 | 2020-06-04 | Y | 2 | 2020-07-09 | 35 | SS | 2020-07-24
BRAISHFIELD A AGI (OFFTAKE) | 2020-06-15 | 2020-05-12 | 2020-05-15 | Y | 3 | 2020-08-25 | 102 | SS | 2020-07-24
BRAISHFIELD B AGI (OFFTAKE) | 2020-06-15 | 2020-05-18 | 2020-05-20 | Y | 2 | 2020-05-20 | 0 | SS | 2020-07-24
GLENMAVIS (OFFTAKE) Winter ME2 | 2020-06-15 | 2020-06-19 | 2020-06-22 | Y | 3 | 2020-06-29 | 7 | SS | 2020-07-24
Drum AGI (Offtake) | 2020-07-15 | 2020-07-21 | 2020-07-22 | Y | 1 | 2020-07-22 | 0 | SS | 2020-08-05
Shorne AGI (Offtake) | 2020-07-15 | 2020-07-29 | 2020-07-31 | Y | 2 | 2020-08-25 | 25 | SS | 2020-08-27
Isle Of Grain PRS | 2020-07-15 |  |  |  | 0 |  | 0
Broxburn AGI (Offtake) | 2020-08-15 | 2020-07-08 | 2020-07-09 | Y | 1 | 2020-07-10 | 1 | SS | 2020-08-27
Broxburn AGI (Offtake) USM install |  | 2020-07-23 | 2020-07-29 | Y | 6 | 2020-07-29 | 0 | SS | 2020-08-27
Tatsfield AGI (Offtake) | 2020-08-15 | 2020-08-18 | 2020-08-21 | Y | 3 | 2020-08-24 | 3 | SS | 2020-08-27
Lamberton Metering Site | 2020-08-15 |  |  |  | 0 |  | 0
GLENMAVIS (OFFTAKE) | 2020-09-15 |  |  |  | 0 |  | 0
St Fergus AGI (Offtake) | 2020-09-15 |  |  |  | 0 |  | 0
WYTCH FARM - Supply to 3rd Party | 2020-09-15 |  |  |  | 0 |  | 0
PORTSDOWN HILL BIOMETHANE | 2020-09-15 |  |  |  | 0 |  | 0
PORTSDOWN HILL BIOMETHANE | 2020-09-15 |  |  |  | 0 |  | 0
PORTSDOWN HILL BIOMETHANE | 2020-09-15 |  |  |  | 0 |  | 0
PORTSDOWN HILL BIOMETHANE | 2020-09-15 |  |  |  | 0 |  | 0
PORTSDOWN HILL BIOMETHANE | 2020-09-15 |  |  |  | 0 |  | 0
Stranraer AGI (Offtake) | 2020-10-15 |  |  |  | 0 |  | 0
POUNDBURY BIOMETHANE SITE | 2020-10-15 |  |  |  | 0 |  | 0
APSLEY FARM BIOMETHANE SITE | 2020-11-10 |  |  |  | 0 |  | 0
Langholm AGI (Offtake) | 2020-11-15 |  |  |  | 0 |  | 0
Burnhervie AGI (Offtake) | 2020-11-15 |  |  |  | 0 |  | 0
Burnhervie AGI (Offtake) | 2020-11-15 |  |  |  | 0 |  | 0
GIRVAN BIOMETHANE | 2020-12-15 |  |  |  | 0 |  | 0
ST NICHOLAS COURT FARM BIOMETHANE | 2020-12-15 |  |  |  | 0 |  | 0
COUPAR ANGUS BIOMETHANE | 2020-12-15 |  |  |  | 0 |  | 0
Note on E1: Rose, Kathryn: Tolerance = 15days from start to finsih