## Project Plan 2018-19
This Project Plan uses the convention that quarters are categorised using the calendar year. E.G. Q1 is Jan-Mar
|  |  |  | 2018 | [11 empty] | 2019 | [11 empty] | 2020
| Status | Date | Date Complete | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January
Steering and Control
Project plan (including budget), with future looking budget | Ongoing | Q1 2018
Undertake consultation of project plan and budget |  | Q2 2018
Communications strategy |  | Q1 2018
Define what analysis PAC wish to see on a monthly basis |  | Q2 2018
Monitor progress of the Electricity PAF Review |  | Q2 2018
Instruct PAFA to analyse the pre and post-Nexus reporting to identify any concerns or issues over performance |  | Q4 2018
Consider performance reports and whether they provide the expected insight into settlement risks |  | Q2 2018
Develop dashboard of industry performance |  | Q3 2018
Consider performance issues and materiality and whether or not it would be beneficial for settlement accuracy to look at targets |  | Q3 2018
Consider other areas that the PAF should be monitoring performance impacts (e.g. switching and data issues) |  | Q3 2018
Consider whether to introduce a critical friend role for the PAFA to help industry Parties |  | Q3 2018
Consider if other reporting is necessary to support the risk methodology and consultation |  | Q3 2018
Consider industry developments that might lead to PAF risks |  | Q3 2018
Agree how industry will be kept up to date on effectiveness of approach |  | Q3 2018
Agree how the effectiveness of the PAF methodology will be assessed |  | Q3 2018
Consider other areas that the PAF should be monitoring performance impacts (e.g. switching and data issues) |  | Q4 2018
Consider the need to interface with the SPAA governance arrangements |  | Q4 2018
PAC member elections |  | Q3 2018
End of PAF year review |  | Q3 2018
End of year evaluation of the PAFA |  | Q2 2018
Performance Reports
Performance reports published by Xoserve |  | Q1 2018
Trial reporting period |  | Q2 2018
PAFA adoption of PARR report publishing |  | Q2 2018
Report publication |  | Q3 2018
Investigate and consider additional reporting areas not covered by MOD520A reporting |  | Q1 2018
Investigate any additional reporting element requirements required from the reports |  | Q2 2018
Risk Register
Approval of PAF Risk Register |  | Q3 2018
Discussion on PAF Risk Register and next steps |  | Q1 2018
Agree if within period changes will be allowed, under what circumstances, and how these will be recognised |  | Q1 2018
Risk Register management |  | Q1 2018
Define additional risks for Risk Register |  | Q1 2018
Review materiality of performance and highlight any areas for concern |  | Q3 2018
Consider any additional elements required from reporting to strengthen risk controls |  | Q2 2018
Assess risks and determine the treatment |  | Q1 2018
PAF approach on incentives/controls
Define Incentive approach |  | Q1 2018
Assess where there are opportunities to improve performance through incentives/controls |  | Q2 2018
Agree on Incentive approach to take |  | Q2 2018
Assess other techniques for the PAF (Detective, Preventive, Remedy) |  | Q2 2018
Commence incentive/control mechanisms on a prioritisation basis |  | Q3 2018
Risk Model
Risk Model management |  | Q2 2018
Agree if within period changes will be allowed, under what circumstances, and how these will be recognised |  | Q3 2018