## CMC_Summary
Totals by Budget Area (£,000's) | [10 empty] | Current Year Value of Work Done Split By Customer Class
|  |  | Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | RAG Status
Summary (by Budget Area) | Expenditure Type | Approved Budget Value 18/19 | Total Approved Value | Estimated Cost at Completion | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Current Year Total vs Budget | Estimated Cost at Completion vs. Total Approved Value | Transmission Network Operator | Distribution Network Operator | DNs & IGTs | IGT's | Shippers
DSC Change Budget | External | 2206.68 | 2352.3791 | 1837.4762 | 508.504 | 170.7755 | 1158.1967 | 0 | G | G | 34.7673 | 44.3023 | 20.8482 | 0 | 70.8577
| Internal |  |  | 396.886 | 119.055 | 37.259 | 240.572 | 0 | NA | NA | 21.0826 | 3.4 | 1.6 | 0 | 11.1764
| Total |  |  | 2234.3622 | 627.559 | 208.0345 | 1398.7687 | 0 | NA | NA | 55.85 | 47.7023 | 22.4482 | 0 | 82.034
Note that project expenditure & budget values shown do not include margin | [8 empty] | Green - At or below target
Internal costs are not deducted from budget (unless otherwise notified) | [8 empty] | Red - Above target
Details of Changes
| Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year
Project Line Level Changes | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Current Year Value of Work Done | Change in Current Year Value of Work Remaining | Change in Future Financial Years Value of Work Remaining
No Change - Start of Financial Year
This section summarises any value change between this report and the previous report. Positive values indicate an increase since the last report, negative indicates a decrease.

## CMC_Current
Values in £0,000s |  |  |  |  | Values pertaining to the Total Cost of the Project |  |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | Percentage to Customer Class |  |  |  |  | Current Year Actual Cost by Customer Class (£0,000's)
Budget Pot Reference | Project Ref No | Project Title | High Level Process Stage | Expenditure Type | Total Approved Value | Estimated Cost at Completion | RAG | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | CCR Status | Comments
B.BP18-020.1 | 4361 | UKL Release 2 (DSC CB) Programme Summary | Delivery | External [O] | 1449.1201 | 934.2177 | 514.9024 | 468.029 | 130.301 | 335.8877 | 0 | 47% | 3% | 34% | 16% | 0% | 61.2415 | 3.909 | 44.3023 | 20.8482 | 0
B.BP18-020.1 | 4361 | UKL Release 2 (DSC CB) Programme Summary | Delivery | Internal [O] | 368.9906 | 151.555 |  | 119.055 | 10 | 22.5 | 0 | 47% | 3% | 34% | 16% | 0% | 4.7 | 0.3 | 3.4 | 1.6 | 0
B.BP18-020.1 | 4361 | UKL Release 2 (DSC CB) Programme Summary | Delivery | Total [O] | 1818.1107 | 1085.7727 |  | 587.084 | 140.301 | 358.3877 | 0 | 47% | 3% | 34% | 16% | 0% | 65.9415 | 4.209 | 47.7023 | 22.4482 | 0
B.BP18-020.1 | 4572 | Retail & Network Release 3 (DSC Change Budget) | Delivery | External [O] | 903.259 | 903.2585 | 0.0005 | 40.475 | 40.4745 | 822.309 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 9.6162 | 30.8583 | 0 | 0 | 0
B.BP18-020.1 | 4572 | Retail & Network Release 3 (DSC Change Budget) | Delivery | Internal [O] | 0 | 245.331 |  | 0 | 27.259 | 218.072 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 6.4764 | 20.7826 | 0 | 0 | 0
B.BP18-020.1 | 4572 | Retail & Network Release 3 (DSC Change Budget) | Delivery | Total [O] | 903.259 | 1148.5895 |  | 40.475 | 67.7335 | 1040.381 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 16.0926 | 51.6409 | 0 | 0 | 0