## IP - In Analysis
UK Link Modification Implementation Plan - In Analysis
Documentation changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | iGT | Other
NA | NA | AML Schedule Proposal | 1839.1 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 14/02/2018 - rejected | Rejected at ChMC on 14th February. Xoserve to produce additional information - Cost vs benefit for further discussion. Further industry discussions to be held for both defects and requirements.
Functional Changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Implementation Date
[7 empty] | Shipper | DNs | NTS | iGT | Other
NA | NA | Incrementing Reads on Isolation Supply Meter Points | 1839.3 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 14/02/2018 Deferred | Rejected at ChMC on 14th February. Xoserve are awaiting further clarification from the parties who rejected the change. XRN4622 has raised - propose to remove from implementation plan as this is on the Change Register

## IP - For Approval
UK Link Modification Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | iGT | Other
4249.B | NA | Address Maintenance Solution - Migration Activities | 1905.1 | 2018-03-29 | 2018-04-09 | 2018-04-10 | X |  |  |  |  | 1919 | 2018-05-09 | 7th July 2018 (Contingency date 14th July 2018) | 2 x reps both in support
4538 | NA | Insertion of Maximum Number of Occurrences in Meter Inspection Date Notice (MID) File | 1898.1 RCP 1917.1 | 21/03/2018 11/04/2018 | 2018-04-06 | 2018-04-11 | X |  |  |  |  | 1917.1 | 2018-05-02 | Release 3 (2nd November 2018) | Revised change summary and representation comments issued on 11th April to confirm the direction of flow of the file
4273 | NA | Introducing IHD (In-Home Display) Installed Status of Failed | 1898.2 RCP 1901.1 | 21/03/2018 27/03/2018 | 2018-04-06 | 2018-04-11 | X |  |  |  |  | NA | 2018-05-02 | Release 3 (2nd November 2018) | Revised change summary issued on 27th March to include omitted files that were impacted. 1 comments received in support as this aligns to electricity
4337 | NA | To change the optionality of the Supply Point confirmation reference for the T51 file | 1898.3 | 2018-03-21 | 2018-04-06 | 2018-04-11 | X |  |  |  |  | NA | 2018-05-02 | Release 3 (2nd November 2018) | No representation comments received, however a comment of support
4443 | NA | File Format Changes Aug 16 Unique Sites (deferred items from CR252) | 1898.4 RCP 1928.2 | 2018-03-21 | 2018-04-06 | 2018-04-11 | X |  |  |  |  | NA | 2018-05-02 | Release 3 (2nd November 2018) | No representation comments received, however a comment of support. A revised change summary was issued to correct the statement to say 'up to 100' occurences as opposed to '100' in the ANT hierarchy and format
3656 | NA | Read Validation Tolerances | 1909.1 | 2018-04-04 | 2018-04-18 | 2018-04-25 | X |  |  |  |  | 1927 | 2018-05-02 | Release 3 (2nd November 2018) | 3 x reps received all in support
4431 | NA | Reads failing market breaker tolerance to be accepted for correct date following AQ Correction | 1909.2 RCP 1921.1 RCP 1928.1 | 04/04/2018 16/04/2018 | 2018-04-18 | 2018-04-25 | X |  |  |  |  | 1927 | 2018-05-02 | Release 3 (2nd November 2018) | 4 x reps received, 1 x tbc, 2 x approved, 1 x rejected - 2 revised change summaries have been issued in response to concerns raised. These have incorporated the inclusion of the U01 as optional and allowed for a read to be submitted up to 6 months. 1 representation comment rejects this change. These comments will be discussed at ChMC
4458 | NA | Class 4 CSEPS Reconciliation Variance Identification | 1909.3 | 2018-04-04 | 2018-04-18 | 2018-04-25 | X |  |  |  |  | 1927 | 2018-05-02 | Release 3 (2nd November 2018) | 3 x reps received all in support
4486 | NA | Meter Type O = Orifice to be an acceptable value in file formats and reports | 1909.4 | 2018-04-04 | 2018-04-18 | 2018-04-25 | X |  |  |  |  | 1927 | 2018-05-02 | Release 3 (2nd November 2018) | 4 representation comments received - 2 in support, 2 to reject. The rejections were based on the equivalent change being required for MDD. The change has been raised to include O as a Meter Type in MDD with a proposed implementation date of 2nd November
4534 | NA | Amendment to RGMA Validation Rules for Meter Asset Installation Date | 1909.5 | 2018-04-04 | 2018-04-18 | 2018-04-25 | X |  |  |  |  | 1927 | 2018-05-02 | Release 3 (2nd November 2018) | 3 x reps received, 2 in support, 1 rejected - information was provided to support understanding around why the situation itself could occur.
4454 | NA | Cadent Billing - DN Sales (Outbound Services) | 1918.1 | 2018-04-11 | 2018-04-25 | 2018-04-27 | X | X | X |  |  | NA | 2018-05-02 | Release 3 (2nd November 2018) | 1 x comment received - in support
4539 | NA | New File Level Rejection | 1918.2 | 2018-04-11 | 2018-04-25 | 2018-04-27 | X | X | X | X | X | NA | 2018-05-02 | Release 3 (2nd November 2018) | 1 x comment received - in support
4495 | NA | Energy Tolerance Rejection code | 1922.1 | 2018-04-16 | 2018-04-30 | 2018-05-02 | X |  |  |  |  | TBC | 2018-05-09 | Release 3 (2nd November 2018) | 1 x representation comment received rejecting the change. To be discussed at ChMC
4453 | NA | File Format Should Have Changes | 1856.3 1922.2 | 31/01/2018 16/04/2018 | 2018-04-30 | 2018-05-02 | X | X | X | X | X | NA | 2018-05-09 | Release 3 (2nd November 2018) | 2 x representations in support, 1 seeking a few clarifications
4481 | NA | Resolution of penny mismatches within invoice supporting information for Core invoices | 1922.3 | 2018-04-16 | 2018-04-30 | 2018-05-02 | X |  |  |  |  | TBC | 2018-05-09 | Release 3 (2nd November 2018) | 1 x comment in support
Documentation changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party | [5 empty] | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | iGT | Other
There are no documentation changes

## IP - Approved Last Meeting
UK Link Modification Implementation Plan - Approved on 7th March
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Approval date | Implementation Date
[7 empty] | Shipper | DNs | NTS | iGT | Other
4465 | 0576 | Annual Production and notification of LIS-3years read | 1884.1 | 2018-03-09 | NA | NA | X |  |  |  |  | Retrospective approval 11th April | 1st April 2018
4249.A | NA | Address Maintenance Solution - Code | 1856.2 | 2018-01-31 | 2018-02-14 | 2018-02-21 | X | X |  | X |  | 2018-04-11 | Proposed for Release 2
Documentation Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Approval date | Implementation Date
[7 empty] | Shipper | DNs | NTS | iGT | Other
NA | NA | Changes Proposed for Removal from the Change Log | 1856.1 | 2018-01-31 | 2018-02-14 | 2018-02-21 | X | X | X | X | X | 2018-03-07 | 2018-03-08
NA | NA | New User Notification Method | 1866.1 | 2018-02-09 | 2018-02-23 | 2018-03-02 | X |  |  |  |  | 2018-03-07 | 2018-05-07

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
6764 | Gemini and Gemini Exit Disaster Recovery Test | 2018-06-16 | 03:15 UK BST | 2018-06-16 | 07:30 UK BST | Annual test to prove disaster recovery capabilities and procedures for Gemini and Gemini Exit. (Should it be necessary to fail back to the primary site, the outage window will be extended to 12:30 UK BST). | 2018-05-09
6764 | Gemini and Gemini Exit Disaster Recovery Test | 2018-06-17 | 03:00 UK BST | 2018-06-17 | 07:30 UK BST | Annual test to prove disaster recovery capabilities and procedures for Gemini and Gemini Exit (Should it be necessary to fail back to the primary site, the outage window will be extended to 12:30 UK BST). | 2018-05-09
NA | UK Link & CMS Disaster Recovery test 2018 | 2018-08-03 | TBC | 2018-08-05 | TBC | To test and confirm disaster recovery processes and procedures for the UK Link application. 2 outages will be required over the weekend, times to be confirmed. | 2018-05-09