## Slide 1: DSC ChMC CSS update 13th June 2018

## Slide 2: Context
At May ChMC and CoMC committees, Xoserve outlined:
  The results of a ‘Level 1’ impact assessment, that indicated a likely increase to CSS Consequential (CSSC) change delivery costs, and;
  A strategy to minimise risk to CSSC costs by bidding for the CSS registration service (CSSB)
This pack provides an update on forthcoming ChMC and CoMC considerations and associated governance; committee feedback is requested.

## Slide 3
 | Q1 18 | Q2 18 | Q3 18 | Q4 18 | Q1 19 | Q2 19 | Q3 19 | Q4 19 | Q1 20 | Q2 20 | Q3 20 | Q4 20 | Q1 21 | Q3 21 | Q4 21
Ofgem Timeline |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CSS Consequential (CSSC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CSS Bid (CSSB) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-Qual.
Tender Process
Contract
Contract
Award – Feb 19
Build & Test
Level 2 IA
Level 3 IA
Customer & Stakeholder Engagement
Solution Agnostic – Delivery (Design, Build & Test)
MT
Imp.
PIS
‘No regrets’ delivery plan
& costs understood
Solution Specific Design and Delivery
Data Cleanse
L2 Solution Options
Delivery – Design, Build, Test
PIS
Contract
Indicative Ofgem Timelines
Agnostic
Design
Baselined
Solution Specific
Design Baselined
Identify ‘Regrets / No Regrets’ Work
Industry Delays?
Industry Delays?
MT
Imp.
Pre-Delivery
Checkpoint
Pre-Level 3
Check Point
Level 1
Impact
Analysis
Demo
Pre-Qualify
Bid Submission
Bid Analysis
Key:
Indicative Timelines
Draft Timelines
Planned Timelines
CP2
CP1
L1 IA
Level 2 Impacts
L3 Solution Options
Level 3 Impacts
Final bid prep
Part C1:
Initial analysis, commence data cleanse and HLD of CSSC
Part C2:
Commencing development work on ‘no regrets’ CSSC
Part C3:
Full delivery of CSSC
Part B1:
Initial analysis and Bid development for CSSB
Part B2:
Full delivery of CSSB
Part C4:
Operate Costs
Part B3:
Operate Costs
Part A:
Bid Support as existing central service provider
Potential Go Live Range

## Slide 4: DSC governance
Over the coming months, there will be a number of areas that need to be shared with and approval sought from DSC committees; the following diagram describes the areas, assumed approval bodies, and indicative time scales
Jun 2018
CoMC
Request to modify BP18 submission for parts ‘A’, ‘C1’ and ‘B1’
Jun 2018
CoMC
Request approval to respond to PQQ
Aug-Oct 2018
CoMC
Request approval to Bid
Feb-Apr 2019
CoMC
Request approval to Contract
Change Delivery decisions (e.g. Change packs, portfolio congestion)
ChMC
Nov 2019
ChMC
Request BER approval for ‘C2’
Oct 2018
CoMC
Request to modify BP18 submission for ‘C2’
Jun 18–Mar 19
CoMC
Standard BP19 process to approve parts ‘C3’, ‘C4’, B2’ and ‘B3’
Mar-Apr 2019
ChMC
Request BER approval for ‘C3’