## Slide 1: Indicative PRIDe Project Plan
12 June 2018

## Slide 2: PRIDe in Gas Model
The PRID(e) in Gas PAF model is based on simple, but robust, principles
Complementary set of Preventive, Detective, Incentive and Remedial assurance techniques. Used flexibly to address Settlement risks
Will provide a clear and transparent set of performance assurance framework techniques
Will provide clarity on how Market Participant performance will be managed
Will define the processes and techniques to be used on Market Participants based on the risk that they pose to the market

## Slide 3: PRIDe in Gas Model
The use of any techniques under this model is the decision and discretion of the PAC based on the information it receives through the PARR and the PAFA with the PAF
A risk that presents a significant impact to Settlement would necessitate the use of a stronger control
Whereas a risk that presents a smaller impact to Settlement would necessitate the use of a weaker control

## Slide 4: PRIDe Model
Technique Purpose | Techniques Description
Prevent the possibility of negative outcomes before they occur | Monitor data for patterns proactively for both party and industry performance decline Educate a Party (or group of parties) where reporting shows parties to be falling short of a performance standard or is impacting negatively on Settlement allocation or reconciliation Engage stakeholders on a regular and informed basis Develop processes for parties to declare adherence to obligations
Remedy negative outcomes through resolution processes | Require a Party to assess an identified performance issue and propose a resolution plan for approval by the PAC Require the PAFA or an industry working group to assess an industry performance issue and propose a resolution plan for approval by the PAC Escalation to the UNCC or Authority
Incentivise positive actions | Peer comparison reporting Industry education sessions Engage stakeholders on a regular and informed basis Liquidated Damages
Detect conduct that requires additional investigation | Performance monitoring and reporting Audit and investigation

## Slide 5: PRIDe Model
Technique Purpose | Techniques Description
engage with industry | Communicate with all stakeholders on a regular and informed basis
educate Market Participants | Inform and instruct Market Participants on what level of performance is expected in the market
evolve with industry | Maintain relevance as the framework needs to adjust to changing requirements and industry environments
 | Monitor industry behaviour (and changes in behaviour) Work with Market Participants to understand the methodology and their responsibilities Work proactively with the Market Participants to identify potential improvements and innovations

## Slide 6: Workshop to define and finalise Project Plan dates
Project Plan contains indicative dates
PAC to agree on dates and milestones based on:
  Comfort and appetite for scale of proposed change
  Urgency of implementation timescales
  Complexity of proposed techniques to be implemented
  Schedule of key date availability

## Slide 7: Workshop to define and finalise Project Plan dates
 | All dates are indicative |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Start | Finish | 2018 |  |  |  |  |  |  | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  | 
Indicative PRIDe Project Plan | Tue 12/06/18 | Mon 03/02/20 | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December
Steering and Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Present Project plan | Tue 12/06/18 | Tue 12/06/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to agree PRIDe Project Plan | Tue 12/06/18 | Tue 12/06/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to agree how industry will be kept up to date on implementation progress | Tue 12/06/18 | Tue 12/06/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Engagement, Education and Evolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Define "Engagement, Education and Evolution" approach | Tue 10/07/18 | Wed 11/07/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC workshop to assess how to improve industry performance through "Engagement, Education and Evolution" | Tue 10/07/18 | Tue 10/07/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to agree on approach to take forward | Tue 10/07/18 | Tue 10/07/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC workshop to draft wording for potential modifications | Tue 10/07/18 | Tue 10/07/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to agree on modification sponser | Tue 10/07/18 | Tue 10/07/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
UNC Modification process | Mon 13/08/18 | Mon 01/04/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Implementation date | Mon 01/04/19 | Mon 01/04/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Prevent |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to define "Prevent" approach and purpose | Tue 11/09/18 | Tue 11/09/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC workshop to assess where there are opportunities to improve performance through prevention | Tue 11/09/18 | Tue 11/09/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to agree on "Prevent" approach to take | Tue 11/09/18 | Tue 11/09/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC workshop to draft wording for potential modifications | Tue 11/09/18 | Wed 12/09/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to agree on modification sponser | Tue 11/09/18 | Wed 12/09/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Modification raised | Tue 11/09/18 | Tue 11/09/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
UNC Modification process | Mon 17/09/18 | Wed 01/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Implementation date | Wed 01/05/19 | Wed 01/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Commence Prevent mechanism on a prioritisation basis | Wed 01/05/19 | Wed 01/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Detect |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to define "Detect" approach and purpose | Tue 07/05/19 | Tue 07/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC workshop to assess where there are opportunities to improve performance through detection | Tue 07/05/19 | Tue 07/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to agree on "Detect" approach to take | Tue 07/05/19 | Tue 07/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC workshop to draft wording for potential modifications | Tue 07/05/19 | Wed 08/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to agree on modification sponser | Tue 07/05/19 | Wed 08/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Modification raised | Tue 07/05/19 | Tue 07/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
UNC Modification process | Thu 20/06/19 | Mon 03/02/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Implementation date | Mon 03/02/20 | Mon 03/02/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Commence Detect mechanism on a prioritisation basis | Mon 03/02/20 | Mon 03/02/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Incentive |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to define "Incentive" approach and purpose | Tue 11/09/18 | Wed 12/09/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC workshop to assess where there are opportunities to improve performance through incentives | Tue 11/09/18 | Tue 11/09/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to agree on on appeals process | Tue 11/09/18 | Wed 12/09/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to agree on "Incentive" approach to take | Tue 11/09/18 | Tue 11/09/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC workshop to draft wording for potential modifications | Tue 11/09/18 | Wed 12/09/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to agree on modification sponser | Tue 11/09/18 | Wed 12/09/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Modification raised | Tue 11/09/18 | Tue 11/09/18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
UNC Modification process | Mon 17/09/18 | Wed 01/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Implementation date | Wed 01/05/19 | Wed 01/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Commence Incentive mechanism on a prioritisation basis | Wed 01/05/19 | Wed 01/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Remedy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to define "Remedy" approach and purpose | Tue 07/05/19 | Tue 07/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC workshop to assess where there are opportunities to improve performance through remedy | Tue 07/05/19 | Tue 07/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to agree on on appeals process | Tue 07/05/19 | Tue 07/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC to agree on "Remedy" approach to take | Tue 07/05/19 | Tue 07/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PAC workshop to draft wording for potential modifications | Tue 07/05/19 | Tue 07/05/19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
UNC Modification process | Thu 20/06/19 | Mon 03/02/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Implementation date | Mon 03/02/20 | Mon 03/02/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Commence Remedy mechanism on a prioritisation basis | Mon 03/02/20 | Mon 03/02/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 8: Prevent technique
Used as a first course of action to consider when presented with a risk to Settlement
Technique is always used for managing risks
It contains the use of the PARR and production of performance reports on a monthly basis
Industry performance would be monitored based on PARR reporting
Engagement with industry on performance monitoring
Education provided as necessary

## Slide 9: Detect technique
Used to further investigate and audit areas of interest
Drill down into data to find determine materiality of issues
Determine root cause if not already known via data analysis or engagement with parties
Monitoring of issue via ad-hoc developed anonymised reports
Option for issues not captured in the PARR reports to be presented and discussed
  Issues can be captured from:
    PAC members
    Raised at other sub committees
    Raised by industry Parties

## Slide 10: Incentivise technique
Used for persistent performance issues and encouraging positive behaviours
PAC receives non anonymised report data with names of all parties contributing to issues captured in PARR reports
PAC receives non anonymised report data with names of all parties contributing to persisting issues not captured in PARR reports
PAC discussion on
  Significance of issue on the market
  Use of liquated damages based on performance
  Exit conditions for parties to exit from liquated damages

## Slide 11: Remedy technique
Used as a last resort once other techniques have been exhausted
Used to monitor party resolution plans based on PAC exit conditions
PAFA to provide updates on resolution plan progress at agreed frequency to PAC
PAC discussion on next steps based on lack of improvement
  Escalation to UNCC
  Escalation to Authority
  Expulsion from UNC

## Slide 12: PAFA@Gemserv.com
Nirav Vyas