## Slide 1: Future Release 3.0 – Release 3 Industry Impacts & Recommendation
13th June 2018

## Slide 2: context
Xoserve were requested to assess the industry wide impact for Release 3 changes and understand if delays with one or more parties could impact the deployment of the change as part of the planned November Go Live.
A CR wise Go/No Go recommendation based on the Xoserve assessment was also requested.
This exercise has been carried out and our findings/recommendations are attached in subsequent slides.
Summary -
  13 changes have been deemed to carry no overall industry impacts and are recommended as “carry on” deployment if all other exit criteria are met;
  1 change (Cadent Billing - DN Sales (Outbound Services) is deemed a critical change with impacts to most parties in the Industry

## Slide 3: Release 3 Industry Impacts & Recommendation (1)
Existing Change Proposal Number | Change Request Title | Service Areas Impacted |  |  |  |  | Industry impacts & ~Xoserve Recommendation
 |  | Shipper Users | Transporters |  |  |  | 
 |  |  | National Grid NTS | Distribution |  |  | 
 |  |  |  | DN Operators & Independent Gas Transporters | DN Operators | Independent Gas Transporters | 
XRN4534 | Amendment to RGMA Validation Rules for Meter Asset Installation Date | Yes | No | No | No | No | No Industry wide impact if some parties are not ready we recommend a 'Go' ahead with R3 deployment
XRN4454 | Cadent Billing - DN Sales (Outbound Services) | Yes** | Yes | Yes (Cadent) | Yes (Cadent) | No | NGT and Cadent are principal parties- if one/two/ of the parties are not ready then change should not Go Live as part of R3
XRN4273 | Introducing IHD (In-Home Display) | Yes | No* | Yes | Yes | Yes | Parties need to create IHD statuses within their system; goes out in portfolio files, recommend change deployment even if some parties are not ready
XRN3656 | Read Validation Tolerances | Yes | No | No | No | No | Greater acceptance of Reads into Xos. Systems if some parties are not ready we will still go ahead with R3 deployment
XRN4453 | File Format Should Have Changes | Yes | Yes | Yes | Yes | Yes | No Industry wide impact ; if some parties are not ready we recommend a 'Go' with R3 deployment
XRN4431 | Reads failing market breaker tolerance to be accepted for correct date following AQ Correction | Yes | No | No | No | No | No Industry wide impact ; if some parties are not ready we recommend a 'Go' with R3 deployment
XRN4481 | Resolution of penny mismatches within invoice supporting information for Core invoices. | Yes** | No | Yes** | Yes** | Yes** | Xoserve Internal change- no real external impact as Market parties are recipients only

## Slide 4: Release 3 Industry Impacts & Recommendation (2)
Existing Change Proposal Number | Change Request Title | Service Areas Impacted |  |  |  |  | Industry impacts & ~Xoserve Recommendation
 |  | Shipper Users | Transporters |  |  |  | 
 |  |  | National Grid NTS | Distribution |  |  | 
 |  |  |  | DN Operators & Independent Gas Transporters | DN Operators | Independent Gas Transporters | 
XRN4337 | To change the optionality of the Supply Point confirmation reference for the T51 file | Yes | No | No | No | No | No Industry wide impact ; if some parties are not ready we recommend a 'Go' with R3 deployment
XRN4495 | Energy Tolerance Rejection code | Yes | No | No | No | No | No Industry wide impact ; if some parties are not ready we recommend a 'Go' with R3 deployment
XRN4539 | New File Level Rejection | Yes | Yes | Yes | Yes | Yes | No Industry wide impact ; if some parties are not ready we recommend a 'Go' with R3 deployment
XRN4443 | File Format Changes Aug 16 Unique Sites (deferred items from CR252) | Yes | No | No | No | No | No Industry wide impact ; if some parties are not ready we recommend a 'Go' with R3 deployment
XRN4458 | Class 4 CSEPS Reconciliation Variance Identification | Yes | No | No | No | Yes* | No Industry wide impact ; if some parties are not ready we recommend a 'Go' with R3 deployment
XRN4486 | Meter Type O = Oriffice to be an acceptable value in file formats and reports | Yes | Yes | Yes | Yes | Yes | Very few instance of Meter Type "o", if some parties are not ready we will still go ahead with R3 deployment
XRN4538 | Insertion of Maximum Number of Occurrences in Meter Inspection Date Notice (MID) File. | Yes | No | No | No | No | Xoserve Internal Parameterised change- no real external impact
* To be confirmed
** Recipients only