## Slide 1: Release 3 Plan Options Decision
23rd July 2018

## Slide 2: Objective
The objective of this exercise is to
  Protect delivery trajectory of industry prioritised change within Release 3 for the committed Go Live Date
  Deliver a quality plan for the remainder of scope that is delivery assured
Aim of these slides is to:
  Recap on previously provided options for R3 delivery to mitigate risk and parallelism within the R3 plan
  Collate industry preferences to ensure the most suitable delivery option is picked for Xoserve and Industry
We would like ChMC to
  To approve the preferred option to allow Release 3 to proceed with the ‘preferred’ delivery option

## Slide 3: Current Plan
The options presented at DSG have been re-evaluated against the latest Project status (slippage accounted for) and the latest plan forecasts have been taken into account while presenting the Xoserve recommended view for this committee’s consideration
Delay period
Additional period required to complete phase(s)

## Slide 4: Options summary
Option | Confidence RAG | Implications | Key considerations
Option 1: Current Plan (Continue As-Is) |  | Track 1 build is complete and testing is on track giving greater certainty in deliverability of 13 CRs for 2nd Nov Go Live The current plan for XRN 4454 has encountered delays in requirements and further build slippage making the current delivery date not achievable | Preservation of delivery for part release (13 CRs) Quality and replan considerations for delivering XRN 4454
Option 2: Continue As–Is with extended MT for XRN 4454 (Cadent/NGT) Change |  | Extended MT impacts delivery of other CRs within Release The current plan for XRN 4454 has encountered delays in requirements and further build slippage mean extended MT unsuitable. | Extended MT for XRN 4454 will impact rest of Release (see appendix) Same as above
Option 3: Move Release 3 delivery to Contingency Date (30th Nov 2018) |  | Delivery continues within R3 Contingency timelines (30th Nov ‘18) Parallelism in plan is not mitigated in this option for Cadent CR - Insufficient plan time within this option to meet contingent date | Risk to full release delivery later in the plan XRN 4454 unlikely to achieve this date with a later replan expected adding to uncertainty in R3 delivery
Option 4: Split Release 3 delivery into two tracks (For Nov ‘ 18 and Feb’19 delivery) - Track 1 13 CRs delivered on 2nd Nov 18 - Track 2 Cadent/NGT CR (XRN 4454) on 1st Feb ’19 |  | Opportunity to deliver 13 industry priority CRs on planned R3 Go Live date (build complete for these CRs) Independent Trajectory for XRN 4454 (NGT/Cadent Separation) for delivery at earliest opportunity (Feb ’19) | Track 1 build is complete and testing is on track giving greater certainty in deliverability of 13 CRs for 2nd November 2018 2 track approach adds fuller testing of different CRs and greater quality certainty for both streams
T1
T1
T2
Another industry proposed option of continue As-is with no Market Trials within release has been evaluated and not recommended due to limited benefits and potential higher ‘quality risk’ considerations
T2
T2
T1
T2
T1
T1 = delivery of Track 1 (13 CRs)
T2 = Delivery of XRN 4454

## Slide 5: Option 4: Split Release 3 delivery into two tracks
# | Proposed Option | Advantage(s) | Disadvantage(s) | Contingency
1 | Split Release 3 delivery into two tracks GREEN | Opportunity to deliver 13 industry priority CRs on planned R3 Go Live date (build is complete for these CRs) Controlled Trajectory for XRN 4454 independent of 13 CRs Fuller testing of XRN 4454 Adds greater quality certainty for both sets of CRs | 2 Go Live points Some elements of parallelism (e.g. PIS period for 13 CRs with MT for XRN 4454 is being undertaken) Potential cost implications may exist for this option | Contingency for 13 CRs is 30th November ’18 Contingency for XRN 4454 is 1st March ‘19 based on earliest billing window available.
This is the project recommended option
Delay period
Additional period required to complete phase(s)

## Slide 6: Options summary
The latest round of planning forecasts have shown a greater slippage of build and testing forecasts for XRN 4454
These phase forecasts have been taken into account while presenting the Xoserve recommended view for this committee’s consideration (Option 4)
This plan option geared towards earliest delivery dates for most of R3 scope while ensuring plan certainty for remaining scope, contingency scenarios have been thought through and presented within the slides

## Slide 7: Next Steps
R3 Plan options for ChMC consideration and feedback requested
Options to be presented to DSG on 16th July for a detailed discussion for their recommendation
Decision sought by w/c 23rd July to enable Xoserve and market participants to sufficiently prepare for subsequent MT and deployment trajectories (request for Extraordinary ChMC)

## Slide 8: Appendices

## Slide 9: Option 1: Current Plan (Continue As-Is)
# | Proposed Option | Advantage(s) | Disadvantage(s) | Contingency
1 | Option 1: Current Plan (Continue As-Is) RED | All CRs for Release 3 are delivered together for the original Release 3 date Track 1 (13 CRs) have completed build and are on track in Testing making this track achievable for original Go Live timelines | Insufficient plan time to complete XRN 4454 for 02nd November 2018 | 1st February 2019
Delay period
Additional period required to complete phase(s)

## Slide 10: Option 2: Current Plan with extended MT
# | Proposed Option | Advantage(s) | Disadvantage(s) | Contingency
1 | Option 2: Current Plan with extended MT RED | Opportunity to CRs for Release 3 are delivered together for the original Release 3 date | The current plan for XRN 4454 has encountered delays in requirements and further build slippage mean extended MT unsuitable. All CRs pushed out to Feb 2019 delivery | N/A
Delay period
Additional period required to complete phase(s)

## Slide 11: Option 3: Move Release 3 delivery to Contingency Date
# | Proposed Option | Advantage(s) | Disadvantage(s) | Contingency
1 | Move Release 3 delivery to Contingency Date (30th Nov ’18) RED | All CRs for Release 3 are delivered together 4 weeks contingency used by R3 | Plan outside Release date for all parties Delivery of 13 CRs will be impacted due to lateness of XRN 4454 (late replan) | Contingency is 1st Feb 2019
Plan also considered splitting XRN 4454 to deliver billing elements for Go live date – this was not recommended due to limited gains and greater rework
Delay period
Additional period required to complete phase(s)