## IP - In Analysis
UK Link Modification Implementation Plan - In Analysis
Functional Changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
4622 | NA | Incrementing Reads on Isolation Supply Meter Points | 1839.3 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 14/02/2018 Deferred | Rejected at ChMC on 14th February. Xoserve are awaiting further clarification from the parties who rejected the change. XRN4645 has been raised - propose to remove from implementation plan as this is on the Change Register
Documentation changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | AML Schedule Proposal | 1839.1 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 14/02/2018 - rejected | Rejected at ChMC on 14th February. Xoserve to produce additional information - Cost vs benefit for further discussion. Further industry discussions to be held for both defects and requirements.
4542 | NA | AQ Transparency Reporting – reports to ensure transparency of the AQ across the Market | TBC | 2018-05-11 | 25/05/2018 | 01/06/2018 | x |  |  |  |  | 2018-06-13 | Expected to be delivered end of June
4328 | NA | IGT Elected Sites Reporting- Reports to capture where the Electing Shipper is not the last confirmed shipper | TBC | 2018-05-11 | 25/05/2018 | 01/06/2018 | x |  |  |  |  | 2018-06-13 | Expected to be delivered by 10th August
NA | 0632 | Shipper asset details reconciliation | TBC | 2018-05-11 | 25/05/2018 | 01/06/2018 | x |  |  |  |  | 2018-07-10 | To be delivered in July in line with the modification. CP to detail method of delivery etc.

## IP - For Approval - Design
UK Link Modification Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4685 | NA | Confirmation of the scope of delivery and planned deployment date of Minor Release Delivery ‘Drop 1’ | 1972.6 | 2018-06-15 | 2018-06-29 | 2018-07-03 | X | [5 empty] | 2018-07-11 | TBC | 3 representation comments received, 2 in support, 1 requesting deferral of new rejection code implementation until a major release. Change Managers to decide whether to implement on 14th July or in a major release. All other changes have no external impact.
NA | NA | Ability to Accept Extended Reading Indexes of up to 12 Characters | 1972.7 | 2018-06-15 | 2018-06-29 | 2018-07-03 | X |  |  |  | X |  | 2018-07-11 | 2019-03-01 | 2 representation comments, both seeking further clarity, both in support of the change.
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4453 | NA | Confirmation of File Format Changes and clarification on Version Control | 1946.8 | 2018-05-11 | 2018-05-25 | 2018-06-04 | X |  |  |  |  | 1961 | NA | R3 | 2 x representation comments received. Both comments sought alternative options. DSG need to discuss and propose a solution

## IP - Approved Last Meeting
UK Link Modification Implementation Plan - Approved on 13th June
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4354 | NA | Request for New DNO Report to identify the nested CSEPs Hierarchy | 1946.1 | 2018-05-11 | NA | NA |  | X |  |  |  | NA | 2018-06-13 | 2018-06-16 | No comments received
NA | NA | Update to Rejection Code List | 1946.4 | 2018-05-11 | 2018-05-25 | 2018-06-04 | X |  |  |  |  | 1961 | 2018-06-13 | TBC (ChMC to discuss) | 2 x representation comments. Both seeking a release as soon as possible. This is documentation only for Xoserve at zero cost therefore this can be implemented at a date to suit ChMC
4449 | NA | PSR Requirements – Supplier report | 1946.5 | 2018-05-11 | 2018-05-25 | 2018-06-04 | X |  |  |  |  | 1961 | 2018-06-13 | R2 | 1 x representation comment asking for a new data item within the report. this will require its own Change Proposal as a new requirement
4542 | NA | Changes to the Shipper Portfolio Report | 1946.7 | 2018-05-11 | 2018-05-25 | 2018-06-04 | X |  |  |  |  | 1961 | 2018-06-13 | 2018-06-01 | No comments received. Retrospective approval as the first report has been run
Documentation Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4449 | NA | Amendment of CDSP Retention Policy | 1946.9 | 2018-05-11 | 2018-05-25 | 2018-06-04 | X | X | X | X | X | 1961 | 2018-06-13 | R2 | 1 x representation comment asking for broader and consistent use of language

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
7368 | Gemini and Gemini Exit Disaster Recovery Failback Test | 2018-07-15 | 03:00 UK BST | 2018-07-15 | 07:30 UK BST | Annual test to prove disaster recovery capabilities and procedures for Gemini and Gemini Exit (Should it be necessary to fail back to the primary site, the outage window will be extended to 12:30 UK BST). | 2018-07-11
NA | UK Link & CMS Disaster Recovery test 2018 | 03/08/2018 10/08/2018 | TBC | 05/08/2018 12/08/2018 | TBC | To test and confirm disaster recovery processes and procedures for the UK Link application. 2 outages will be required over the weekend, times to be confirmed. | 09/05/2018 New dates notified 13/06/2018