## Slide 1: 2019 Release Planning Options inc Modification 0621 / GB Charging Project DSC Change Management Committee update
July 2018

## Slide 2: MOD0621 - Update for DSC ChMC
At last month’s DSC ChMC we explained that detailed analysis of requirements associated to EU GB Charging Project (CP4376) were due to conclude end of June 2018
As part of MOD0621, consequential changes to UK Link systems are required
As part of the analysis phase we have explored Release options . It is our recommendation that this Project is delivered September 2019 - this aligns to dates that have been shared with the industry at Transmission Workgroup & Gas Ops Forum
As September 2019 doesn’t align to the Major Release dates for the R&N platform for we believe an Adhoc Major Release will be needed
Alternative delivery options have been discounted as these introduce greater complexity and increased risk of successful delivery in the timescales available
Options to revise 2019 Releases to align to September 2019 are possible if these are supported by Customers

## Slide 3: 2019 Release Planning – High Level Options
No | Option Detail | Feb 19 | June 19 | *Sept 19 | Nov 19
1 | Feb 19 -scope to be finalised Sept 19 – including June release candidates with the recommendation to deliver Gemini & UK Link Changes for MOD621 together |  |  |  | 
2 | Feb 19 – scope to be finalised June 19 – to include all June 19 release candidates (exc MOD621) Sept 19 - MOD621 - recommendation to deliver Gemini & UK Link changes for MOD621 together |  |  |  | 
3 | Feb 19 – scope to be finalised Sept 19 – to include all June 19 release candidates inc MOD621 - recommendation to deliver Gemini & UK Link changes together Nov 19 – scope to be prioritised and agreed with ChMC |  |  |  | 
4 | Feb 19- scope to be finalised June 19 - to include all release candidates (exc MOD621) Sept 19 - MOD621 - recommendation to deliver Gemini & UK Link changes for MOD621 together Nov 19 – scope to be prioritised and agreed with ChMC |  |  |  | 
*Sept 19 release is outside of standard UNC agreed release dates

## Slide 4: Requirements of ChMC and next steps:
To provide views on preference for Release Schedule for 2019
Acceptance that a release will be required for September 2019
Xoserve to determine impacts of various release options and provide feedback to ChMC