## Sheet1
Data as of 09/07/18 (extracted from Change Register)
Ref | Change Title | Change Type | Xoserve Proposed Indicative Prioritsation Score | Proposed Release | Xoserve Lead | Primary Application Impacted | Business Process Impact | Change Driver | Comments
4642 | Address Maintainance Solution | CR (Internal change funded by Xoserve) | 44% | Jun-19 / Sept-19 | Simon Harris / Dave Ackers | ISU | SPA | License Condition | in capture phase
4621 | Suspension of the Validation between Meter Index and Uncoverted Converter Index | CP | 26% | Jun-19 / Sept-19 | Dave Addison | ISU | Reads | ChMC endorsed Change Proposal | In capture phase
3667a | Provision of Formula Year AQ | CR (Internal) | 47% | Jun-19 / Sept-19 | Emma Smith | ISU | SPA | Xoserve Internal CR (business improvement initiative) | In capture phase
4670 | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | CR (Internal) | 18.02% | Jun-19 / Sept-19 | Karen Marklew | ISU | Reads | Xoserve Internal CR (business improvement initiative) | In capture phase
4665 | Creation of new End User Categories | CP | 46% | 2019-02-01 | Emma Smith | ISU | Invoicing | ChMC endorsed Change Proposal
4044 | Extension of ‘Must Read’ process to include Annual Read sites | CP | 35% | Jun-19 / Sept-19 | Andy Clasper | ISU | RGMA | ChMC endorsed Change Proposal | In capture phase
4676 | Reconciliation Issues with reads recorded between D1 - D5 | CR (Internal) | 62% | Jun-19 / Sept-19 | Emma Smith / Rachel Martin | ISU | Reads | Xoserve Internal CR (business improvement initiative) | in capture phase (to moved to CP as potentially externally impacting)
4679 | Requiring a meter reading following a change of local distribution zone and exit zone | CP | 37% | Jun-19 / Sept-19 | Dave Addison | ISU | Reads | ChMC endorsed Change Proposal | Expectation MOD will be withdrawn and CP will progress
4687 | PSR Updates for large domestic sites | CP | 35% | Jun-19 / Sept-19 | Ellie Rogers | ISU | SPA | ChMC endorsed Change Proposal | In capture phase
4690 | Actual read following estimated transfer read calculating AQ of 1 | CP | 37% | Jun-19 / Sept-19 | Emma Smith | ISU | AQ | ChMC endorsed Change Proposal | In capture phase
4691 | CSEPs: IGT and GT File Formats (CGI files) | CP | 32% | Jun-19 / Sept-19 | invite lead | ISU | other | ChMC endorsed Change Proposal | out for consultation
4692 | CSEPs: IGT and GT File Formats (CIN files) | CP | 32% | Jun-19 / Sept-19 | invite lead | ISU | Other | ChMC endorsed Change Proposal | out for consultation
4693 | CSEPs: IGT and GT File Formats Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | CP | 32% | Jun-19 / Sept-19 | invite lead | ISU | Other | ChMC endorsed Change Proposal | out for consultation
4694 | CSEPs: IGT and GT File Formats (create new data validations) | CP | 32% | Jun-19 / Sept-19 | invite lead | ISU | Other | ChMC endorsed Change Proposal | out for consultation
4686 | Smart Metering Report | CP | 29% | Jun-19 / Sept-19 | Rachel Hinsley | BW | RGMA | ChMC endorsed Change Proposal | In capture phase
4645 | incrementing reads submitted for an isolated Supply Meter Point (RGMA Flows) | CR (Internal) | 37% | Jun-19 / Sept-19 | Rachel Hinsley | ISU | Invoicing | Xoserve Internal CR (business improvement initiative) | In capture phase