## Slide 1: Change Assurance Dashboard
June 2018

## Slide 2: Change Assurance Dashboard
Summary Comments
R2 Health check complete with Yellow RAG
R3 Health check complete with Red RAG and a number of recommendations to address
Transform US Lessons Learnt draft report circulated with Exec for input
Transform US Network and Desktop Assurance underway
Dependency on ongoing Capability development in CIO Portfolio office to implement Stage gate methodology and project reporting tool
Chart: Project specific versus future learning
| Project | Future
Scope | 2 | 0
Governance | 1 | 1
Approach and Plan | 1 | 1
Team | 0 | 0
Chart: Priority findings by Project
| R2 | R3 | TU N&D | Strategic Sourcing
CA4 | 3 | 4 | 0 | 0
CA3 | 3 | 4 | 0 | 0
CA2 | 0 | 7 | 0 | 0
CA1 | 0 | 1 | 0 | 0
Assurance status | Numbers
Complete | 2
Underway | 2
Scoping | 1
At Risk | 0
Not due yet | 5

## Slide 3: Change Assurance Dashboard
Area | Date | Change Project | RAYG by Area | CA1 – CA4 | Summary
Programme Delivery | May 2018 | UK Link R2 – Health check | Overall Business Case Team Sponsorship Plan Governance Customer Scope and Solution Other | CA1 CA2 CA3 CA4 | Overall status is yellow indicating Project is in reasonable health with minor issues that could represent a low risk to the Project’s overall success. Project is well run with clear business case, plan and reporting. Team is aligned and process is on track for go live. There were 6 summary points identified through the on following areas: Scope documentation, testing approach, business change, business implementation planning, multi release documentation approach and general documentation
 | June 2018 | UK Link R3 – Health check | Overall Business Case Team Sponsorship Plan Governance Customer Scope and Solution Other | CA1 CA2 CA3 CA4 | The key issue is that of the Cadent billing change and the consequential impact on the remainder of the release if the changes remain as a single implementation. Options should be developed that mitigate that impact and safeguard the delivery of the project outcomes. Significant risks lie around the robustness of the plans and the controls within the project. Some of this has been a result of resource constraints and reassignments to other priorities and so it is recommended that additional resource is sourced to support the project. The plans need to be reviewed, validated and formally re-baselined. Stage gates need to be clearly called out in the plan and strictly adhered to with entry and exit criteria approved, evidence formally logged and approvals recorded. It should be noted that , although a formal stage gate was not completed, approval of the design artefacts was gained and change by change they progressed into Build. Some of the challenges met by both R2 & 3 are the result of the lack of maturity of the UK Link SAP release process; work is progressing within the R&N platform to mature these processes and particularly our capability to ensure that the capacity of a release is not exceeded at the point at which we agree the scope.
3
3
1
7
4
4
2
0
BL
FC
BL – Baseline breakdown of Health check findings
FC – Forecast of Health check findings following completion of short term remedial actions

## Slide 4: Update on UK Link R3 Health check
Since the report was shared with the project an action plan has been established and three findings have completed remedial actions
The action plan has been reviewed to establish its effectiveness in remediating the findings
A forecast position in respect of the findings has been added to the dashboard which shows the expected position after 2 months
Change Assurance will continue to monitor the completion of remedial actions
A further health check is planned prior to entering Market Trials

## Slide 5: Change Assurance Dashboard
Area | Date | Change Project | RAYG by Area | CA1 – CA4 | Summary
Programme Delivery | June 2018 | UK Link R3 – Stage Gate | Overall Phase Completion Next Phase Readiness | CA1 CA2 CA3 CA4 | The project has successfully passed through its implementation gate review There remain three open assurance findings , two are longer term actions which are related to the improvement of Change Lifecycle for UK Link Releases , one is planned for completion by the end of PIS (Xoserve benefits realisation) There remain minor actions needed to be fully ready from PIS exit , but plans exist for their timely completion
2
1

## Slide 6: R3 Change Assurance Report Action Plan
Responses categories:
  Completed actions: already done.
  Short term actions: to be completed within next 2 months.
  Long term actions: to be completed within next 6 months.
Key issue 1: Delay in build of Cadent billing changes due to requirements delays. Proposed project pause for replanning.
  Completed actions: 4 delivery options worked up and shared with customers.
  Short Term actions:
    Preferred delivery option to be agreed at the DSC change committee.
    Plan to be updated to reflect the agreed delivery option.
    Updated plan to be baselined.
  Long Term Plan:
    Obtain agreement that requirements provided outside time window will be pushed to subsequent releases.
Key issue 2: Evidence for stage gate approval not provided.
  Short term actions:
    Evidence for stage gate criteria acceptance to be provided.
    Definition, criteria and required evidence for future stage gates to be reviewed and communicated.

## Slide 7: R3 Change Assurance Report Action Plan
Key issue 3: Risk around robustness of plans and controls within the project due to resource constraints.
  Completed actions:
    Transfer of resources to R3 team to provide capacity for addressing control gaps.
    New interim R&N Platform Director in place to provide closer support.
    PID updated and out for approval.
    Regular RAID review meetings put in place.
  Short term actions:
    Further resources to be transferred from R2 & externally.
    SharePoint meeting manager to be employed as control log for audit trail of actions & decisions.
    Product Descriptions for remaining products to be reviewed and employed.
Key issue 4: Immaturity of the UK Link SAP release process.
  Long Term Plan:
    Terms of Reference for governance meetings to be reviewed and updated.
    Review R&N platform team capabilities and structure to improve resilience.
    Skill up existing team & fill resourcing gaps.
    Propose new release methodology.

## Slide 8: Maturity of Future Release Capability
Level 1
Heroic Efforts: Ad-hoc, inconsitent processes. Success based upon individual effort.
Level 2
Repeatable: Basic processes established & repeated for similar projects.
Level 3
Defined: All processes well defined, standardised & integrated. Consistent practices in place.
Level 4
Managed: Processes clearly quantified & strategic analysis undertaken on process data.
Level 5
Continuous Improvement: Proactive process improvement through qualitative feedback.
High Risk
Low Quality
Low Risk
High Quality
Reactive
Managed
Proactive
Release 4
Release 5