## Summary
Totals by Budget Area (£,000's) | [10 empty] | Current Year Value of Work Done Split By Customer Class
|  |  | Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | RAG Status
Summary (by Budget Area) | Expenditure Type | Approved Budget Value 18/19 | Total Approved Value | Estimated Cost at Completion | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Current Year Total vs Budget | Estimated Cost at Completion vs. Total Approved Value | Transmission Network Operator | Distribution Network Operator | DNs & IGTs | IGT's | Shippers
DSC Change Budget | External | 2206.68 | 2379.2291 | 1877.5262 | 508.504 | 402.9501 | 966.0721 | 0 | G | G | 117.0164 | 88.2936 | 41.5499 | 0 | 156.0903
| Internal |  |  | 396.886 | 119.055 | 74.518 | 203.313 | 0 | NA | NA | 42.1653 | 6.8 | 3.2 | 0 | 22.3527
| Total |  |  | 2274.4122 | 627.559 | 477.4681 | 1169.3851 | 0 | NA | NA | 159.1816 | 95.0936 | 44.7499 | 0 | 178.443
Note that project expenditure & budget values shown do not include margin | [8 empty] | Green - At or below target
Internal costs are not deducted from budget (unless otherwise notified) | [8 empty] | Red - Above target
Details of Changes
| Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year
Project Line Level Changes | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Current Year Value of Work Done | Change in Current Year Value of Work Remaining | Change in Future Financial Years Value of Work Remaining
4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - External [O] | 0 | 26.7 | 0 | 0 | 26.7 | 0
This section summarises any value change between this report and the previous report. Positive values indicate an increase since the last report, negative indicates a decrease.

## Detail
Values in £0,000s | [5 empty] | Values pertaining to the Total Cost of the Project |  |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | Percentage to Customer Class |  |  |  |  | Current Year Actual Cost by Customer Class (£0,000's) | [8 empty] | Comparison Formulae |  | 6 | 8 | 9 | 11 | 12 | 13 | 14 | 25
Budget Pot Reference | Project Ref No | Project Title | Senior Project Manager | High Level Process Stage | Expenditure Type | Total Approved Value | Estimated Cost at Completion | RAG | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | CCR Status | Comments | SORT FIELD 1 | SORT FIELD 2 | Matcher | Project Line | High Level Process Stage | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Value of Work Done (Current Year) | Change in Value of Work Remaininng (Current Year) | Change in Value of Work Remaining (Future Financial Years) | CCN Status | Any Value Change? | This Year Spend Change? | Master Change Flag | (Negative means old value is lower) | Cell Colour Code
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Delivery | External [O] | 1449.1201 | 948.0177 | 501.1024 | 468.029 | 259.687 | 220.3017 | 0 | 47% | 3% | 34% | 16% | 0% | 122.0529 | 7.7906 | 88.2936 | 41.5499 | 0 |  |  | D | 83 | 4361External [O] | 4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - External [O] | SAME | 0 | 26.7 | 0 | 0 | 26.7 | 0 | SAME | YES | 26.7 | TRUE |  | 0
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Delivery | Internal [O] | 368.9906 | 151.555 |  | 119.055 | 20 | 12.5 | 0 | 47% | 3% | 34% | 16% | 0% | 9.4 | 0.6 | 6.8 | 3.2 | 0 |  |  | D | 84 | 4361Internal [O] | 4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - Internal [O] | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Delivery | Total [O] | 1818.1107 | 1099.5727 |  | 587.084 | 279.687 | 232.8017 | 0 | 47% | 3% | 34% | 16% | 0% | 131.4529 | 8.3906 | 95.0936 | 44.7499 | 0 |  |  | D | 85 | 4361Total [O] | 4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - Total [O] | SAME | 0 | 26.7 | 0 | 0 | 26.7 | 0 | SAME | YES | 26.7 | TRUE |  | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | External [O] | 903.259 | 903.2585 | 0.0005 | 40.475 | 143.2631 | 719.5204 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 34.0374 | 109.2258 | 0 | 0 | 0 |  |  | D | 126 | 4572External [O] | 4572 UKL Nov '18 Release [R3] (DSC CB) - External [O] | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | Internal [O] | 0 | 245.331 |  | 0 | 54.518 | 190.813 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 12.9527 | 41.5653 | 0 | 0 | 0 |  |  | D | 127 | 4572Internal [O] | 4572 UKL Nov '18 Release [R3] (DSC CB) - Internal [O] | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | Total [O] | 903.259 | 1148.5895 |  | 40.475 | 197.7811 | 910.3334 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 46.9901 | 150.791 | 0 | 0 | 0 |  |  | D | 128 | 4572Total [O] | 4572 UKL Nov '18 Release [R3] (DSC CB) - Total [O] | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | External | 1.5 | 1.4 | 0.1 | 0 | 0 | 1.4 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 261 | 4542External | 4542 Changes to Shipper Portfolio Report - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 262 | 4542Internal | 4542 Changes to Shipper Portfolio Report - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | Total | 1.5 | 1.4 |  | 0 | 0 | 1.4 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 263 | 4542Total | 4542 Changes to Shipper Portfolio Report - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | External | 8.75 | 8.75 | 0 | 0 | 0 | 8.75 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 264 | 4525External | 4525 Transparency of AQ Process - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 265 | 4525Internal | 4525 Transparency of AQ Process - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | Total | 8.75 | 8.75 |  | 0 | 0 | 8.75 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 266 | 4525Total | 4525 Transparency of AQ Process - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Delivery | External | 9.5 | 9 | 0.5 | 0 | 0 | 9 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 267 | 4328External | 4328 iGT Elected Shipper Sites Report - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 268 | 4328Internal | 4328 iGT Elected Shipper Sites Report - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Delivery | Total | 9.5 | 9 |  | 0 | 0 | 9 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 269 | 4328Total | 4328 iGT Elected Shipper Sites Report - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Delivery | External | 7.1 | 7.1 | 0 | 0 | 0 | 7.1 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 270 | 4354External | 4354 Nested CSEP Report for DNs - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 271 | 4354Internal | 4354 Nested CSEP Report for DNs - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Delivery | Total | 7.1 | 7.1 |  | 0 | 0 | 7.1 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 272 | 4354Total | 4354 Nested CSEP Report for DNs - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
Note on AM2: Max Pemberton: Checks whether the value for this years spend has actually changed, or just moved from forecast to actual