## Summary
Totals by Budget Area (£,000's) | [10 empty] | Current Year Value of Work Done Split By Customer Class
|  |  | Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | RAG Status
Summary (by Budget Area) | Expenditure Type | Approved Budget Value 18/19 | Total Approved Value | Estimated Cost at Completion | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Current Year Total vs Budget | Estimated Cost at Completion vs. Total Approved Value | Transmission Network Operator | Distribution Network Operator | DNs & IGTs | IGT's | Shippers
DSC Change Budget | External | 2206.68 | 2379.2291 | 1899.4742 | 508.504 | 842.8871 | 548.0831 | 0 | G | G | 280.2646 | 169.2109 | 76.2875 | 0 | 317.1242
| Internal |  |  | 396.886 | 119.055 | 131.536 | 146.295 | 0 | NA | NA | 83.8055 | 7.65 | 3.6 | 0 | 36.4805
| Total |  |  | 2336.8352 | 668.034 | 974.4231 | 694.3781 | 0 | NA | NA | 364.0701 | 176.8609 | 79.8875 | 0 | 353.6046
Note that project expenditure & budget values shown do not include margin | [8 empty] | Green - At or below target
Internal costs are not deducted from budget (unless otherwise notified) | [8 empty] | Red - Above target
Details of Changes
| Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year
Project Line Level Changes | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Current Year Value of Work Done | Change in Current Year Value of Work Remaining | Change in Future Financial Years Value of Work Remaining
4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - External [O] | 0 | 25.1 | 0 | 0 | 25.1 | 0
This section summarises any value change between this report and the previous report. Positive values indicate an increase since the last report, negative indicates a decrease.

## Detail
Values in £0,000s | [5 empty] | Values pertaining to the Total Cost of the Project |  |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | Percentage to Customer Class |  |  |  |  | Current Year Actual Cost by Customer Class (£0,000's) | [8 empty] | Comparison Formulae |  | 6 | 8 | 9 | 11 | 12 | 13 | 14 | 25
Budget Pot Reference | Project Ref No | Project Title | Senior Project Manager | High Level Process Stage | Expenditure Type | Total Approved Value | Estimated Cost at Completion | RAG | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | CCR Status | Comments | SORT FIELD 1 | SORT FIELD 2 | Matcher | Project Line | High Level Process Stage | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Value of Work Done (Current Year) | Change in Value of Work Remaininng (Current Year) | Change in Value of Work Remaining (Future Financial Years) | CCN Status | Any Value Change? | This Year Spend Change? | Master Change Flag | (Negative means old value is lower) | Cell Colour Code
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Closedown | External [O] | 1449.1201 | 969.9657 | 479.1544 | 468.029 | 476.7967 | 25.14 | 0 | 47% | 3% | 34% | 16% | 0% | 224.0945 | 14.3039 | 162.1109 | 76.2875 | 0 |  |  | D | 83 | 4361External [O] | 4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - External [O] | SAME | 0 | -3.2 | 0 | 140 | -143.2 | 0 | SAME | YES | -3.2 | TRUE |  | 0
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Closedown | Internal [O] | 368.9906 | 151.555 |  | 119.055 | 22.5 | 10 | 0 | 47% | 3% | 34% | 16% | 0% | 10.575 | 0.675 | 7.65 | 3.6 | 0 |  |  | D | 84 | 4361Internal [O] | 4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - Internal [O] | SAME | 0 | 0 | 0 | 10 | -10 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Closedown | Total [O] | 1818.1107 | 1121.5207 |  | 587.084 | 499.2967 | 35.14 | 0 | 47% | 3% | 34% | 16% | 0% | 234.6695 | 14.9789 | 169.7609 | 79.8875 | 0 |  |  | D | 85 | 4361Total [O] | 4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - Total [O] | SAME | 0 | -3.2 | 0 | 150 | -153.2 | 0 | SAME | YES | -3.2 | TRUE |  | 0
B.BP18-020.1 | 4635 | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service | P. Duvvuri | Delivery | External | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 126 | 4572External [O] | 4572 UKL Nov '18 Release [R3] (DSC CB) - External [O] | SAME | 0 | 0 | 0 | 102.8 | -102.8 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4635 | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service | P. Duvvuri | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 127 | 4572Internal [O] | 4572 UKL Nov '18 Release [R3] (DSC CB) - Internal [O] | SAME | 0 | 0 | 0 | 27.3 | -27.3 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4635 | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service | P. Duvvuri | Delivery | Total | 0 | 40.475 |  | 40.475 | 0 | 0 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 128 | 4572Total [O] | 4572 UKL Nov '18 Release [R3] (DSC CB) - Total [O] | SAME | 0 | 0 | 0 | 130 | -130 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | External [O] | 903.259 | 903.2585 | 0.0005 | 40.475 | 348.8404 | 513.9431 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 82.8797 | 265.9607 | 0 | 0 | 0 |  |  | D | 261 | 4542External | 4542 Changes to Shipper Portfolio Report - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | Internal [O] | 0 | 245.331 |  | 0 | 109.036 | 136.295 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 25.9055 | 83.1305 | 0 | 0 | 0 |  |  | D | 262 | 4542Internal | 4542 Changes to Shipper Portfolio Report - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | Total [O] | 903.259 | 1148.5895 |  | 40.475 | 457.8764 | 650.2381 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 108.7852 | 349.0912 | 0 | 0 | 0 |  |  | D | 263 | 4542Total | 4542 Changes to Shipper Portfolio Report - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | External | 1.5 | 1.4 | 0.1 | 0 | 1.4 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 1.4 | 0 | 0 | 0 | 0 |  |  | D | 264 | 4525External | 4525 Transparency of AQ Process - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 265 | 4525Internal | 4525 Transparency of AQ Process - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | Total | 1.5 | 1.4 |  | 0 | 1.4 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 1.4 | 0 | 0 | 0 | 0 |  |  | D | 266 | 4525Total | 4525 Transparency of AQ Process - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | External | 8.75 | 8.75 | 0 | 0 | 8.75 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 8.75 | 0 | 0 | 0 | 0 |  |  | D | 267 | 4328External | 4328 iGT Elected Shipper Sites Report - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 268 | 4328Internal | 4328 iGT Elected Shipper Sites Report - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | Total | 8.75 | 8.75 |  | 0 | 8.75 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 8.75 | 0 | 0 | 0 | 0 |  |  | D | 269 | 4328Total | 4328 iGT Elected Shipper Sites Report - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Closedown | External | 9.5 | 9 | 0.5 | 0 | 0 | 9 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 270 | 4354External | 4354 Nested CSEP Report for DNs - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Closedown | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 271 | 4354Internal | 4354 Nested CSEP Report for DNs - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Closedown | Total | 9.5 | 9 |  | 0 | 0 | 9 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 272 | 4354Total | 4354 Nested CSEP Report for DNs - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Closedown | External | 7.1 | 7.1 | 0 | 0 | 7.1 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 7.1 | 0 | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Closedown | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Closedown | Total | 7.1 | 7.1 |  | 0 | 7.1 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 7.1 | 0 | 0
Note on AM2: Max Pemberton: Checks whether the value for this years spend has actually changed, or just moved from forecast to actual