## Slide 1: DSC Change Committee Summary – 12th September
4 new change proposals raised and approved
  XRN4725 – New read reason type for Line in the Sand estimate readings – Approved
  XRN4738 – Shipper Portfolio update of the proposed Formula Year AQ/SOQ – Approved
  XRN4752 – Meter read performance - Approved
  XRN4753 – CMS Increase in information provided in .QCL response file - Approved
Solution/Delivery option approval
  XRN4717 – use of up to date forecast weather data in the first NDM nominations run – deferred approval to next meeting
  XRN4676 – Reject cyclic reads D-5 to D-1 at Shipper Transfer - approved
CCR approval
  XRN4667- DSC Service Description Table cosmetic changes to Service Lines May 2018 - approved
  XRN4009 – Billing History by all NTS capacity/commodity related charges (applicable dates in 2014 to Nexus implementation date) - approved
  XRN4110 – creation of a service to release domestic consumer data to PCW’s (Price comparison websites) and TPI’s (third party intermediaries) - Approved

## Slide 2: DSC Change Committee Summary – 12th September
Release Updates:
  Release 2
    Post Implementation Support period has been extended to 2nd November, however expect to close down sooner.
  Release 3
    Delivery split into the 2 delivery tracks
      Track 1 – 13 changes
      Track 2 – Cadent Billing change
    Both tracks are on plan and therefore shown GREEN (for delivery)
  Market trials has commenced
Future release June 2019
    Further discussion around scope of June 2019 release, expect to approved scope t 10th October Change Management Committee

## Slide 3: DSC Change Committee Summary – 12th September
CSS consequential change update
XRN4695UIG Taskforce update
  https://www.gasgovernance.co.uk/sites/default/files/ggf/2018-09/8.%20XRN4695%20UIG%20Taskforce%20Update.pptx
AOB items
  Process to initiate CP following MOD approval – discussion
  IX Update (same material shared in CoMC meeting)