## IP - In Analysis
UK Link Modification Implementation Plan - In Analysis
Functional Changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | AML Schedule Proposal | 1839.1 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 14/02/2018 - rejected | Rejected at ChMC on 14th February. Xoserve to produce additional information - Cost vs benefit for further discussion. Further industry discussions to be held for both defects and requirements.
NA | NA | Change Pack Publication | 2008.2 | 2018-07-13 | 2018-07-27 | 2018-08-03 | X | X | X | X | X | NA | No approval required in August. Feedback was received - proposed to be discussed at DSG on Monday 6th August and further changes to be proposed based on DSG outcomes

## IP - For Approval - Design
UK Link Modification Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4525 | NA | Transparency of Rolling AQ Reports | 2043.5 | 2018-08-10 | 2018-08-24 | NA | X |  |  |  |  | NA | 2018-09-12 | 15th Working day each month from September 2018 | The CP confirmed the delivery and mechanism for the suite of reports. No representation comments were received.
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | Change Management Committee important dates 2019 | 2043.1 | 2018-08-10 | 2018-08-24 | 2018-08-30 | X | X | X | X | X | 2060 | 2018-09-12 | NA | Communication detailing ChMC dates, change pack dates, DSG dates and the three industry proposed release dates: Friday 1st March 2019 Friday 28th June 2019 Friday 1st November 2019 1 representation received confirming release dates

## IP - Approved Last Meeting
UK Link Modification Implementation Plan - Approved on 23rd July
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | GB Charging Part A | 2008.1 | 2018-07-13 | 2018-07-27 | NA |  |  | X |  |  | NA | 2018-08-08 | 2018-11-18 | No representations received. Issued for 'information only'.
Documentation Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
NA | Gemini and UK Link Portal | 2018-09-09 | 03:00:00 UK BST | 2018-09-09 | 07:00 UK BST (contingency 08:00) | Activity is to upgrade the perimeter Checkpoint firewalls that provides security to Xoserve applications: Contact Management System (CMS), Gemini, PRISMA, Extended Product 1 (XP1), UK Link Network, Data Communications Company (DCC), Enhanced File Transfer (EFT) and UK Link Portal. | 2018-08-08
N/A Request Number - Impacted System is CMS |  | Fail Over: 15/09/2018 | Midnight | 2018-09-16 07:00 | 07:00 UK BST (contingency 07:00 23/09/2018) | Xoserve will be conducting a scheduled Disaster Recovery (DR) exercise for the CMS Application which will be carried out during the CMS Maintenance window, with activities following the below schedule: | 2018-08-08
|  | Failback: 16/09/2018 | Midnight | 2018-09-17 | 07:00 UK BST (contingency 07:00 24/09/2018) | Xoserve will be conducting a scheduled Disaster Recovery (DR) exercise for the CMS Application which will be carried out during the CMS Maintenance window, with activities following the below schedule: | 2018-08-08