## Intro Page
Xoserve Change Delivery Plan on a Page |  | Legend
|  | XXX | Completed Task
| The attached plans give a view of the all change currently being managed by Xoserve via mutiple delivery platforms, UK link, Gemini, and Data. |  | Forcast Activity
| Tab 1 - provides all UK Link impacting change, release 2 & 3 are currently in delivery, releases June-19 and Nov-19 have not yet had the scope for inclusion in the release agreed, therefore any change detailed in these releases are placeholders only. Also sets out potential delivery timelines for CSS (Central Switching Services) and UIG (unidentified Gas). At present RAASP is considered for inclusion in November 2019 release |  | Baseline Activity
| Tab 2 - lists all current live change that feeds into the plans in this publication |  | Potential Actibity
| Tab 3 - Provides a 'look ahead' 2 year view of change for UK Link | RAG | Activity at risk
|  | RAG | Activity with potential risk
|  | RAG | Activity on Track
|  | RAG | Activity under replan/Review

## UK Link_Live_Changes
XRN Ref | High-Level Status | R&N Release Allocation | Change Title | Change Type | Delivery Status | Change Lifecycle Status | Xoserve Proposed Indicative Prioritisation Score | July'17 Change Demand Backlog ChMC Priority | July'17 Change Demand Backlog SDG Priority | Xoserve Platform Owner | Origination Date | Change Originator | Xoserve Project Manager | R&N Release Number | Previous UK Link CR Ref | Delivery Team | ClearQuest Ticket (Minor Enhancement Delivery) | Current Delivery Implementation Forecast Date | Actual Delivery Implementation Date | Customer Requested Implementation Date | Primary Application Impacted | Business Process Impact | Flash IA: Perceived Delivery Effort | Workaround Available? | Workaround Accountability | Workaround Frequency | No. of Xoserve FTEs required to service the workaround | Workaround Complexity? | Workaround Lifespan | Change Driver | Change Beneficiary | Shipper Impact | Network Impact | iGT Impact | Primary Impacted DSC Service Area | Number of DSC Service Areas impacted | Change Improvement Scale (Size of proposed change) | Customer System Changes Required? | Customer Testing Likely Required? | Customer Training Required? | Safety of Supply at risk? | Financial Loss Incurred to Customer? | Customer Switching at risk? | ChMC CP Approval date | ChMC EQR Approval date | ChMC BER Approval date | ChMC CCR Approval date
4760 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Profiling for all defects & CRs that impact AQs and Corrected consumption | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 27.03% |  |  | R & N | 2018-09-10 | Eamonn Darcy | Mark Tullett |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-11-01 | ISU | AQ | 30-60 days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | TRUE | High | FALSE | FALSE | No Date | No Date
4738 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Shipper portfolio update of proposed Formula Year AQ/SOQ | CP | LIVE | A5 - CP in capture with DSG | 16.22% |  |  | R & N | 2018-08-14 | Simon Harris | Simon Harris |  |  | Third Party SI / Service Provider |  | No Date | No Date | No Date | Other | Other | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | 2018-09-12
4740 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | AQ Calculation for Class 4 sites with AMR Fitted | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 33.63% |  |  | R & N | 2018-08-15 | Karen Marklew | Emma smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-10-31 | ISU | AQ | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | FALSE | FALSE | TRUE | Service Area 23: Internal | FALSE | FALSE | FALSE | One | TRUE | High | FALSE | FALSE | No Date | No Date
4742 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Incorrect AQ calculations due to migrated consumption | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 33.63% |  |  | R & N | 2018-08-15 | Karen Marklew | Emma smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-10-31 | ISU | AQ | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | FALSE | FALSE | FALSE | Two to Five | TRUE | High | FALSE | FALSE | No Date | No Date
4753 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | CMS – Increase information provided in .QCL response file | CP | LIVE | A6 - CP in solution consultation | 18.62% |  |  | R & N | 2018-08-31 | John Cooper/Brookfield Utilities | Paul Orsler |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2019-06-01 | CMS | SPA | 60-100 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 2: Provide Query Management | TRUE | TRUE | TRUE | One | FALSE | Medium | FALSE | FALSE | No Date | 2018-09-12
4755 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Tool to calculate Incorrect AQ calculations created by defects | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 33.63% |  |  | R & N | 2018-09-03 | Eamonn Darcy | Mark Tullett |  |  | Third Party SI / Service Provider | XO3703 | No Date | No Date | 2018-10-15 | ISU | AQ | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | FALSE | FALSE | FALSE | TRUE | Service Area 23: Internal | FALSE | FALSE | FALSE | Two to Five | TRUE | High | FALSE | FALSE | No Date | No Date
4735 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Automation of adhoc Amendment invoice Summary report | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 31.83% |  |  | R & N | 2018-08-06 | Dan Donovan | Mark Tullett | 50 |  | Minor Enhancements Team | XO3696 | No Date | No Date | 2018-09-28 | ISU | Invoicing | 0-30 days | TRUE | Xoserve | Monthly | One | Low | 2018-12-25 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | TRUE | Medium | FALSE | FALSE | No Date | No Date
4708 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Ability to assess change impact on individual customers | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 24.02% |  |  | R & N | 2018-06-26 | Linda Whitcroft | Linda Whitcroft |  |  | Xoserve Resource |  | No Date | No Date | 2019-06-01 | Other | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | TRUE | FALSE | TRUE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
1154 | 1. Start-Up (Progressing through change governance) | R1.0 (Nexus) | UK Link Programme (Archiving) | CP | LIVE | C2 - Delivery Business Case awaiting IRC/XEC/Board Approval | 33.63% |  |  | R & N | 2008-03-03 | Chris Smith | Neil Morgan | 1 |  | Third Party SI / Service Provider |  | 2018-09-16 | No Date | 2017-06-01 | Other | Other | 100+days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | TRUE | Service Area 23: Internal | FALSE | FALSE | FALSE | All | FALSE | High | FALSE | FALSE | No Date | No Date
4513 | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | Change to validation of address fields | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 24.62% |  |  | R & N | 2017-10-25 | Richard Cresswell | Christina Francis | 2 | UKLP IADBI359 | Third Party SI / Service Provider |  | 2018-06-29 | 2018-07-01 | 2018-06-29 | CMS | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | FALSE | FALSE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | 2017-10-11 | 2017-10-11
4721 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | SMP monthly AQ calculations – triggered new AQ/EUC | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 45.65% |  |  | R & N | 2018-07-30 | Mark Summersmith | Mark Tullett |  |  | Minor Enhancements Team | XO3698 | No Date | No Date | 2018-09-17 | Gemini | AQ | 30-60 days | TRUE | Xoserve | Monthly | Five to Ten | High | 2018-09-30 | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | TRUE | Medium | TRUE | TRUE | No Date | No Date
4303 | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | Remove ‘n’ as an allowable value from the .SFN file in ‘Fault corrected’ field and remove as allowable value from AMT & SAP ISU. | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 33.63% | TBP | Low | R & N | 2016-10-18 | Dean Johnson | Christina Francis | 2 | UKLP267 | Third Party SI / Service Provider |  | 2018-06-29 | 2018-07-01 | 2018-05-01 | ISU | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | All | FALSE | High | FALSE | FALSE | 2017-10-11 | 2017-10-11
2831.5b | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | Changes to the upper parameter of the XDO partial refresh file. Post Nexus (R2) | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 23.42% | TBP | High | R & N | 2017-02-07 | Jon Follows | Christina Francis | 2 | UKLP292 | Third Party SI / Service Provider |  | 2018-06-29 | 2018-07-01 | 2018-06-29 | ISU | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Participant | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | Two to Five | FALSE | Medium | FALSE | FALSE | 2017-10-11 | 2017-10-11
3995a | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | Energy Theft Tip-off Service Data Provision | CP | LIVE | F1 - CCR/Closedown document in progress | 33.63% | TBP | High | R & N | 2016-03-15 | Alex Ross-Shaw | Christina Francis | 2 | UKLP222 | Third Party SI / Service Provider |  | 2018-06-29 | 2018-07-01 | 2018-06-29 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | All | FALSE | High | FALSE | FALSE | 2017-10-11 | 2017-10-11
4288 | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | DDS/DDU file amendment | CP | LIVE | F1 - CCR/Closedown document in progress | 24.62% | Low | High pending discussions with all Networks | R & N | 2015-10-14 | Matt Smith | Christina Francis | 2 | UKLP IADBI147 | Third Party SI / Service Provider |  | 2018-06-29 | 2018-07-01 | 2018-06-29 | ISU | SPA | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | 2017-10-11 | 2017-10-11
4716 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Increased Field Length – ‘Updated by’ data item | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 9.009% |  |  | R & N | 2018-07-17 | Matt Smith | Emma smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | No Date | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date
4717 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Use of up to date Forecast weather data in first NDM Nominations Run | CP | LIVE | A6 - CP in solution consultation | 16.82% |  |  | R & N | 2018-07-20 | Louise Hellyer (Total Gas & Power) | Simon Harris |  |  | Third Party SI / Service Provider |  | No Date | No Date | No Date | ISU | Other | 0-30 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 15: Demand Estimation | FALSE | FALSE | FALSE | One | FALSE | High | FALSE | FALSE | No Date | No Date
4669 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | Class 1 & 2 Energy Comparison Report | CR (Internal) | LIVE | D1 - Change in delivery | 45.65% |  |  | R & N | 2018-05-14 | Carole Elwell | Mark Tullett | 50 |  | Minor Enhancements Team | XO3680 | 2018-11-30 | No Date | 2018-06-01 | ISU | Invoicing | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | All | TRUE | High | FALSE | FALSE | No Date | No Date
4514 | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | MIV File Changes for MUR Invoice - CMS | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 33.63% |  |  | R & N | 2017-10-25 | Richard Cresswell | Christina Francis | 2 | UKLP IADBI367 | Third Party SI / Service Provider |  | 2018-06-29 | 2018-07-01 | 2018-06-29 | CMS | Invoicing | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | All | FALSE | High | FALSE | FALSE | 2017-10-11 | 2017-10-11
4671 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | Class 2 Energy Updates from UKL to Gemini via CON file | CR (Internal) | LIVE | D1 - Change in delivery | 45.65% |  |  | R & N | 2018-05-14 | Jo Tedd | Mark Tullett | 50 |  | Minor Enhancements Team | XO3681 | 2018-09-16 | No Date | 2018-07-01 | ISU | Invoicing | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | All | TRUE | High | FALSE | FALSE | No Date | No Date
4316 | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | Meter Point Details Report & Sector Breakdown Report | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 33.63% | TBP | Low | R & N | 2017-04-07 | Mark Cockayne | Christina Francis | 2 | UKLP315 | Third Party SI / Service Provider |  | 2018-06-29 | 2017-07-01 | 2018-05-01 | BW | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | 2017-10-11 | 2017-10-11
4449 | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | PSR requirements – Vulnerable Customer data requirements | CP | LIVE | F1 - CCR/Closedown document in progress | 24.02% | High | High | R & N | 2016-11-11 | Steve Nunnington | Christina Francis | 2 | UKLP273 | Third Party SI / Service Provider |  | 2018-06-29 | 2018-07-01 | 2018-06-29 | ISU | SPA | 31-100days | FALSE | [5 empty] | SPAA Change Proposal | Multiple Market Participants | FALSE | TRUE | FALSE | FALSE | FALSE | Service Area 22: Specific Services | FALSE | FALSE | FALSE | Two to Five | FALSE | High | FALSE | FALSE | 2017-10-11 | 2017-10-11
4249 | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | Address Maintenance Solution | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 33.63% |  |  | R & N | 2017-03-22 | Steve Ganney | Christina Francis | 2 |  | Third Party SI / Service Provider |  | 2018-06-29 | 2018-07-01 | 2018-06-29 | ISU | SPA | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | All | FALSE | High | FALSE | FALSE | 2017-10-11 | 2017-10-11
4528 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | The word ‘PLOT’ as a prefix | CR (Internal) | LIVE | D1 - Change in delivery | 27.63% |  |  | R & N | 2017-11-07 | Mike Orsler/Emma Smith | Mark Tullett | 50 |  | Minor Enhancements Team | XO3592 | 2018-10-30 | No Date | 2018-03-23 | Other | Other | 0-30days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4299 | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | Reports required under UNC TPD V16.1 in Nexus (reports required by Mod 520A) | CP | LIVE | F1 - CCR/Closedown document in progress | 33.63% | High | High | R & N | 2016-08-12 | Steve Nunnington | Christina Francis | 2 | UKLP251 | Third Party SI / Service Provider |  | 2018-06-29 | 2018-07-01 | 2018-05-01 | BW | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | All | FALSE | High | FALSE | FALSE | 2017-10-11 | 2017-10-11
4554 | 3. Change delivered, awaiting closure approval/sign-off | Minor Enhancement Delivered Change | Amendment Invoice validation Reports | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 26.43% |  |  | R & N | 2017-12-05 | Vicky Spiller | Mark Tullett | 50 |  | Minor Enhancements Team | XO3613 | 2018-08-10 | 2018-08-10 | 2018-06-30 | ISU | Invoicing | 0-30days | TRUE | Xoserve | Monthly | One | High | 2019-12-01 | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4524 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | Change to generation logic of RDP data flows to include all recorded iGT Supply Points within UK Link systems | CR (Internal) | LIVE | D1 - Change in delivery | 23.42% |  |  | R & N | 2017-10-31 | Paul Orsler | Mark Tullett | 50 |  | Minor Enhancements Team | XOS3657 | 2018-11-30 | No Date | 2018-11-09 | ISU | Other | 30-60 days | FALSE | [5 empty] | License Condition | Multiple Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | FALSE | FALSE | FALSE | Two to Five | FALSE | Low | FALSE | TRUE | No Date | No Date
4304 | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | Amend referral rules for class 2 smaller LSP’s | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 33.63% | TBP | Medium | R & N | 2016-11-03 | Dean Johnson | Christina Francis | 2 | UKLP270 | Third Party SI / Service Provider |  | 2018-06-29 | 2018-07-01 | 2018-05-01 | ISU | SPA | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | All | FALSE | High | FALSE | FALSE | 2017-10-11 | 2017-10-11
4309 | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | Back billing for domestic (SSP) sites needs to be reflect thecorrect adjustment start date | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 33.63% | TBP | Low | R & N | 2016-01-19 | Dean Johnson | Christina Francis | 2 | UKLP287 | Third Party SI / Service Provider |  | 2018-06-29 | 2018-07-01 | 2018-05-01 | CMS | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | All | FALSE | High | FALSE | FALSE | 2017-10-11 | 2017-10-11
4563 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | Assurance of the Annual AQ activities | CR (Internal) | LIVE | D1 - Change in delivery | 36.64% |  |  | R & N | 2017-12-18 | Sue Prosser | Mark Tullett | 50 |  | Minor Enhancements Team | 3632 | 2018-09-08 | No Date | 2018-09-29 | ISU | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | FALSE | FALSE | FALSE | Two to Five | TRUE | High | FALSE | FALSE | No Date | No Date
3477 | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | Missing Key Data Item from iGT’s to Shippers (Plot Number) | CP | LIVE | F1 - CCR/Closedown document in progress | 24.62% | High | High | R & N | 2015-07-07 | Lee Chambers | Christina Francis | 2 | UKLP IADBI112 | Third Party SI / Service Provider |  | 2018-06-29 | 2018-07-01 | 2018-06-29 | BW | SPA | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | FALSE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | Two to Five | FALSE | High | FALSE | FALSE | 2017-10-10 | 2017-10-11
4595 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | SAP T-Code Access – Modification to ISU & BW Permissions for Data Office Aligned Resources | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 22.22% |  |  | R & N | 2018-01-23 | Steve Concannon | Mark Tullett | 50 |  | Minor Enhancements Team | XO3646 | No Date | No Date | 2018-02-28 | AMT | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
3283 | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | Recording of DN Siteworks’ / New Network Connection Reference in Central systems (ON HOLD PENDING NEW CO) | CP | LIVE | F1 - CCR/Closedown document in progress | 22.82% | Low | Low | R & N | 2013-12-16 | Joel Martin | Christina Francis | 2 | n/a | Third Party SI / Service Provider |  | 2018-06-29 | 2018-07-01 | 2018-06-29 | ISU | SPA | 31-100days | FALSE | [5 empty] | SPAA Change Proposal | One Market Participant | FALSE | TRUE | FALSE | FALSE | FALSE | Service Area 21: Data Flows and Services to Network Operators | FALSE | FALSE | FALSE | Two to Five | FALSE | Medium | FALSE | FALSE | 2017-10-11 | 2017-10-11
4482 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | SAP Meter Read Entry Screen | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 22.22% |  |  | R & N | 2017-05-30 | Emma Smith | Mark Tullett | 50 | UKLP IADBI333 | Minor Enhancements Team | XO3629 | No Date | No Date | 2018-07-27 | ISU | Reads | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
3386 | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | Create new “role” for CMS to cover all activities undertaken within a Distribution Network (ON HOLD PENDING NEW CO) | CP | LIVE | F1 - CCR/Closedown document in progress | 28.83% | Low | Low | R & N | 2014-05-08 | Jo Ferguson | Christina Francis | 2 | n/a | Third Party SI / Service Provider |  | 2018-06-29 | 2018-07-01 | 2018-06-29 | CMS | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | FALSE | TRUE | FALSE | FALSE | FALSE | Service Area 22: Specific Services | FALSE | FALSE | FALSE | Two to Five | FALSE | Medium | FALSE | FALSE | 2017-10-11 | 2017-10-11
4248 | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | Quarterly smart metering reporting for HS&E and GDNs (post Nexus R2) | CP | LIVE | F1 - CCR/Closedown document in progress | 28.23% | High | High | R & N | 2017-03-22 | Joanna Ferguson | Christina Francis | 2 | n/a | Third Party SI / Service Provider |  | 2018-06-29 | 2018-07-01 | 2018-06-29 | BW | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | FALSE | TRUE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | FALSE | FALSE | FALSE | Two to Five | FALSE | High | FALSE | FALSE | 2017-10-11 | 2017-10-11
4361 | 3. Change delivered, awaiting closure approval/sign-off | R2.0 (Jun'18) | Release 2 Delivery | CP | LIVE | F1 - CCR/Closedown document in progress | 21.02% |  |  | R & N | 2017-10-11 | Christina Francis | Christina Francis | 2 |  | Third Party SI / Service Provider |  | 2018-07-01 | 2018-07-01 | 2018-05-01 | ISU | Other | 100+days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 17: UK Link Services | FALSE | FALSE | FALSE | Two to Five | FALSE | High | FALSE | FALSE | 2017-10-11 | 2017-10-11
4539 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | New File Level Rejection | CR (Internal) | LIVE | D1 - Change in delivery | 22.82% |  |  | R & N | 2017-11-21 | Rachel Hinsley/Dave Addison | Padmini Duvvuri | 3 |  | Third Party SI / Service Provider |  | 2018-11-05 | No Date | 2018-11-01 | ISU | Invoicing | 0-30days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | FALSE | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | 2018-02-07 | No Date
4443 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | File Format Changes Aug 16 Unique Sites (deferred items from CR252) | CR (Internal) | LIVE | D1 - Change in delivery | 24.62% | TBP | Low | R & N | 2016-09-16 | Marie Berlin | Padmini Duvvuri | 3 | UKLP IADBI258 | Third Party SI / Service Provider |  | 2018-11-05 | No Date | 2018-06-01 | ISU | SPA | 31-100days | TRUE | Xoserve | No Workaround Frequency | No Xoserve FTEs | Low | 2018-12-31 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | TRUE | FALSE | TRUE | Two to Five | FALSE | Low | FALSE | FALSE | 2018-02-07 | No Date
4725 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | New read reason type for LIS estimate readings | CP | LIVE | A5 - CP in capture with DSG | 17.42% |  |  | R & N | 2018-07-31 | Simon Harris | Rachel Hinsley |  |  | Xoserve Resource |  | No Date | No Date | 2019-04-01 | ISU | Reads | 30-60 days | TRUE | Xoserve | Annually | One | Low | 2019-03-01 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 3: Record/submit Data in Compliance with UNC | TRUE | TRUE | TRUE | Two to Five | FALSE | Medium | FALSE | FALSE | No Date | 2018-09-12
4727 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Changes to XDO / DXR File Timestamp generation logic ( Ticket ID - 838105 : SAP- XDO file timestamp issue) | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 37.24% |  |  | R & N | 2018-08-02 | Paul Orsler | Mark Tullett |  |  | Minor Enhancements Team | XO3699 | No Date | No Date | 2018-09-04 | ISU | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Group | FALSE | FALSE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | One | TRUE | High | FALSE | FALSE | No Date | No Date
4534 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Amendment to RGMA Validation Rules for Meter Asset Installation Date | CP | LIVE | D1 - Change in delivery | 49.25% |  |  | R & N | 2017-11-20 | Andrew Margan | Padmini Duvvuri | 3 |  | Third Party SI / Service Provider |  | 2018-11-05 | No Date | 2018-06-01 | ISU | No Process | 60-100 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | FALSE | FALSE | FALSE | One | TRUE | Medium | FALSE | FALSE | 2018-02-07 | 2018-01-10
4538 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Insertion of Maximum Number of Occurrences in Meter Inspection Date Notice (MID) File. | CR (Internal) | LIVE | D1 - Change in delivery | 16.22% |  |  | R & N | 2017-11-21 | Rachel Hinsley/Dave Addison | Padmini Duvvuri | 3 |  | Third Party SI / Service Provider |  | 2018-11-05 | No Date | 2018-11-09 | ISU | No Process | 0-30days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | 2018-02-07 | No Date
4541 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Read Design Gaps - Missing Overide Flags In RGMA and Retro Files Linked to Retro (4474) | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 22.82% | Low | Low - to be reviewed in 3 months time | R & N | 2015-02-10 | Emma Smith | Lee Chambers |  | UKLP IADBI073 | Third Party SI / Service Provider |  | 2019-06-28 | No Date | 2018-11-01 | ISU | RGMA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | FALSE | FALSE | FALSE | Two to Five | FALSE | Low | FALSE | FALSE | No Date | No Date
4474 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Delivery of Retro | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 25.23% | TBP | High | R & N | 2017-04-21 | Lee Chambers | Lee Chambers |  | UKLP IADBI319 | Third Party SI / Service Provider |  | 2019-06-28 | No Date | 2019-02-01 | ISU | Other | 31-100days | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Groups | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | FALSE | FALSE | FALSE | Five to Twenty | FALSE | Medium | FALSE | FALSE | No Date | No Date
4453 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | File Format Should Have Changes | CR (Internal) | LIVE | D1 - Change in delivery | 31.23% | TBP | Low | R & N | 2016-12-16 | Marie Berlin | Padmini Duvvuri | 3 | UKLP IADBI280v3 | Third Party SI / Service Provider |  | 2018-11-05 | No Date | 2018-06-01 | ISU | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | TRUE | FALSE | TRUE | Two to Five | FALSE | Low | FALSE | FALSE | 2018-02-07 | No Date
3656 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Read Validation Tolerances | CP | LIVE | D1 - Change in delivery | 25.23% | TBP | Low | R & N | 2014-12-24 | Michelle Downes | Padmini Duvvuri | 3 | UKLP IADBI060 | Third Party SI / Service Provider |  | 2018-11-05 | No Date | 2018-05-01 | ISU | RGMA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | 2018-02-07 | 2018-02-07
4454 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Cadent Billing - DN Sales (Outbound Services) | CP | LIVE | D1 - Change in delivery | 43.84% | TBP | High | R & N | 2016-12-16 | Linda Whitcroft | Padmini Duvvuri | 3 | UKLP IADBI281 | Third Party SI / Service Provider |  | 2018-11-05 | No Date | 2018-06-01 | ISU | Invoicing | 31-100days | TRUE | Both Xoserve & Customer | Daily | Two to Five | High | 2018-06-01 | MOD/Ofgem | Multiple Market Groups | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | TRUE | TRUE | TRUE | Two to Five | FALSE | High | FALSE | FALSE | 2018-02-07 | 2017-12-13
4273 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Introducing IHD (In-Home Display) Installed Status of Failed MOD614 | CP | LIVE | D1 - Change in delivery | 24.62% |  |  | R & N | 2017-05-10 | Alex Cebo | Padmini Duvvuri | 3 |  | Third Party SI / Service Provider |  | 2018-11-05 | No Date | 2018-06-01 | ISU | Other | 31-100days | FALSE | [5 empty] | SPAA Change Proposal | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | FALSE | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | 2018-02-07 | 2017-11-08
4556 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | Process to provide a report when Gas Safety Regulations requests return no MPRN’s | CP | LIVE | D1 - Change in delivery | 28.23% |  |  | R & N | 2017-12-06 | Andy Clasper | Matt Rider | 50 |  | Minor Enhancements Team | XO3614 | 2018-09-21 | No Date | 2018-02-23 | ISU | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | FALSE | TRUE | FALSE | FALSE | FALSE | Service Area 22: Specific Services | FALSE | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | 2018-01-10
4337 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | To change the optionality of the Supply Point confirmation reference for the T51 file | CR (Internal) | LIVE | D1 - Change in delivery | 28.83% |  |  | R & N | 2017-07-24 | Sue prosse/Emma Lyndon | Padmini Duvvuri | 3 |  | Third Party SI / Service Provider |  | 2018-11-05 | No Date | 2018-04-01 | ISU | SPA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | 2018-02-07 | No Date
4688 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Brownfield AQ Corrections | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 30.63% |  |  | R & N | 2018-06-04 | Lee Jackson | Mark Tullett |  |  | Minor Enhancements Team | XO3687 | No Date | No Date | 2018-07-01 | ISU | AQ | 30-60 days | TRUE | Xoserve | Daily | One | High | 2019-01-31 | Xoserve Internal CR (business improvement initiative) | One Market Participant | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4495 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Energy Tolerance Rejection code | CR (Internal) | LIVE | D1 - Change in delivery | 22.82% |  |  | R & N | 2017-06-28 | Nick Timm | Padmini Duvvuri | 3 | UKLP IADBI356 | Third Party SI / Service Provider | 3627 | 2018-11-05 | No Date | 2018-11-01 | ISU | Reads | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | TRUE | TRUE | TRUE | One | FALSE | Low | FALSE | FALSE | 2018-02-07 | No Date
4186 | 3. Change delivered, awaiting closure approval/sign-off | Out for industry sponsorship/approval to reject | UK Link Future Release Analysis | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 10.21% |  |  | R & N | 2017-01-30 | Jane Rocky | Lee Chambers |  |  | Third Party SI / Service Provider |  | 2017-10-11 | 2017-11-16 | No Date | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4431 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Reads failing market breaker tolerance to be accepted for correct date following AQ Correction | CR (Internal) | LIVE | D1 - Change in delivery | 31.83% | TBP | High | R & N | 2016-05-04 | Emma Smith | Padmini Duvvuri | 3 | UKLP IADBI202 | Third Party SI / Service Provider |  | 2018-11-05 | No Date | 2018-10-01 | ISU | Reads | 31-100days | TRUE | External Customer | Daily | No Xoserve FTEs | Low | 2018-12-31 | MOD/Ofgem | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | TRUE | TRUE | TRUE | Two to Five | FALSE | Low | FALSE | FALSE | 2018-02-07 | No Date
4458 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Class 4 CSEPS Reconciliation Variance Identification | CR (Internal) | LIVE | D1 - Change in delivery | 16.22% | TBP | Medium | R & N | 2017-01-26 | Karen Marklew | Padmini Duvvuri | 3 | UKLP IADBI289 | Third Party SI / Service Provider |  | 2018-11-05 | No Date | 2018-12-31 | ISU | Reads | 31-100days | TRUE | Both Xoserve and Customer | No Workaround Frequency | No Xoserve FTEs | LOW | 2018-12-31 | ChMC endorsed Change Proposal | One Market Group | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | 2018-02-07 | No Date
4486 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Meter Type O = Oriffice to be an acceptable value in file formats and reports | CR (Internal) | LIVE | D1 - Change in delivery | 23.42% |  |  | R & N | 2017-06-05 | Emma Smith | Padmini Duvvuri | 3 | UKLP IADBI338 | Third Party SI / Service Provider |  | 2018-11-05 | No Date | 2018-06-01 | ISU | SPA | 31-100days | TRUE | Both Xoserve and Customer | No Workaround Frequency | No Xoserve FTEs | Low | 2018-12-31 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | TRUE | TRUE | TRUE | One | FALSE | Low | FALSE | FALSE | 2018-02-07 | No Date
4481 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Resolution of penny mismatches within invoice supporting information for Core invoices. | CR (Internal) | LIVE | D1 - Change in delivery | 31.23% |  |  | R & N | 2017-05-30 | Kiran Kumar | Padmini Duvvuri | 3 | UKLP IADBI332 | Third Party SI / Service Provider |  | 2018-11-05 | No Date | 2018-06-01 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | FALSE | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | 2018-02-07 | No Date
4572 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Retail & Network Release 3 | CP | LIVE | D1 - Change in delivery | 19.22% |  |  | R & N | 2018-01-03 | Padmini Duvvuri | Padmini Duvvuri | 3 |  | Third Party SI / Service Provider |  | 2018-11-05 | No Date | 2018-10-31 | ISU | No Process | 100+ days | FALSE | [5 empty] | ChMC endorsed Change Proposal | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 17: UK Link Services | FALSE | FALSE | FALSE | Five to Twenty | FALSE | High | FALSE | FALSE | 2018-02-07 | No Date
4484 | 3. Change delivered, awaiting closure approval/sign-off | MR Drop 1 | Remove restriction on nominated SOQ (as per MOD 445 | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 30.03% |  |  | R & N | 2017-06-06 | Bhupinder Basra | Matt Rider | Jul2018 | UKLP IADBI336 | Third Party SI / Service Provider |  | 2018-07-14 | 2018-07-14 | 2018-10-01 | ISU | SPA | 31-100days | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Groups | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | FALSE | FALSE | FALSE | Two to Five | FALSE | Medium | FALSE | FALSE | No Date | No Date
4496 | 3. Change delivered, awaiting closure approval/sign-off | MR Drop 1 | iGT Address Amendments - SAP | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 28.23% |  |  | R & N | 2017-06-30 | Richard Cresswell | Matt Rider | Jul2018 | UKLP IADBI358 | Third Party SI / Service Provider |  | 2018-07-14 | 2018-07-17 | 2018-12-31 | ISU | SPA | 31-100days | TRUE | Xoserve | Daily | One | High | 2018-12-31 | ChMC endorsed Change Proposal | One Market Group | FALSE | FALSE | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | FALSE | FALSE | FALSE | Two to Five | FALSE | Medium | FALSE | FALSE | No Date | No Date
4469 | 3. Change delivered, awaiting closure approval/sign-off | MR Drop 1 | UMR Hierarchy Amendment in AMT | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 25.83% | TBP | Low | R & N | 2017-03-27 | Karen Marklew | Matt Rider | Jul2018 | UKLP IADBI309 | Third Party SI / Service Provider | 3628 | 2018-07-14 | 2018-08-14 | 2018-10-01 | AMT | Reads | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | FALSE | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
4480 | 3. Change delivered, awaiting closure approval/sign-off | MR Drop 1 | Capacity reconciliation charge (MOD445) calculation functionality | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 42.04% |  |  | R & N | 2017-05-30 | Kiran Kumar | Matt Rider | Jul2018 | UKLP IADBI331 | Third Party SI / Service Provider |  | 2018-07-14 | 2018-07-14 | 2018-10-01 | ISU | Other | 31-100days | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Groups | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | FALSE | FALSE | FALSE | Two to Five | TRUE | Medium | FALSE | FALSE | No Date | No Date
4685 | 3. Change delivered, awaiting closure approval/sign-off | MR Drop 1 | Retail & Network Minor Release – Drop 1 – July-18 | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 21.02% |  |  | R & N | 2018-05-29 | Matt Rider | Matt Rider | Jul2018 |  | Third Party SI / Service Provider |  | 2018-07-14 | 2018-07-14 | 2018-07-14 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | TRUE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date
4670 | 1. Start-Up (Progressing through change governance) | 2019-06-01 | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | CR (External Impacting) | LIVE | A5b - Undergoing Solution Impact Assessment | 18.62% |  |  | R & N | 2018-05-14 | Karen Marklew | Emma smith | Jun2019 |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-11-01 | ISU | Reads | 30-60 days | TRUE | Xoserve | Monthly | One | Medium | 2019-01-31 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | TRUE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4687 | 1. Start-Up (Progressing through change governance) | 2019-06-01 | PSR updates for large domestic sites | CP | LIVE | A5b - Undergoing Solution Impact Assessment | 23.42% |  |  | R & N | 2018-06-04 | Ellie Rogers | Emma smith | Jun2019 |  | Third Party SI / Service Provider |  | No Date | No Date | 2019-02-01 | ISU | SPA | 60-100 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | FALSE | TRUE | FALSE | Two to Five | FALSE | Medium | FALSE | FALSE | No Date | No Date
4690 | 1. Start-Up (Progressing through change governance) | 2019-06-01 | Actual read following estimated transfer read calculating AQ of 1 | CP | LIVE | A5b - Undergoing Solution Impact Assessment | 28.83% |  |  | R & N | 2018-06-04 | James Rigby (Npower) | Emma smith | Jun2019 |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-08-01 | ISU | AQ | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | 2018-07-11
4691 | 1. Start-Up (Progressing through change governance) | 2019-06-01 | CSEPs: IGT and GT File Formats (CGI Files) | CP | LIVE | A5b - Undergoing Solution Impact Assessment | 19.22% |  |  | R & N | 2018-06-05 | Richard Pomroy (Wales & West Utilities) | Emma smith | Jun2019 |  | Third Party SI / Service Provider |  | No Date | No Date | No Date | ISU | Other | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | FALSE | TRUE | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | TRUE | FALSE | TRUE | Two to Five | FALSE | Medium | FALSE | FALSE | No Date | No Date
4692 | 1. Start-Up (Progressing through change governance) | 2019-06-01 | CSEPs: IGT and GT File Formats (CIN Files) | CP | LIVE | A5b - Undergoing Solution Impact Assessment | 19.22% |  |  | R & N | 2018-06-05 | Richard Pomroy (Wales & West Utilities) | Emma smith | Jun2019 |  | Third Party SI / Service Provider |  | No Date | No Date | No Date | ISU | Other | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | FALSE | TRUE | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | TRUE | FALSE | TRUE | Two to Five | FALSE | Medium | FALSE | FALSE | No Date | No Date
4693 | 1. Start-Up (Progressing through change governance) | 2019-06-01 | CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | CP | LIVE | A5b - Undergoing Solution Impact Assessment | 19.22% |  |  | R & N | 2018-06-05 | Richad Pomroy (Wales & West Utilities) | Emma smith | Jun2019 |  | Third Party SI / Service Provider |  | No Date | No Date | No Date | ISU | Other | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | FALSE | TRUE | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | TRUE | FALSE | TRUE | Two to Five | FALSE | Medium | FALSE | FALSE | No Date | No Date
4587 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | Test of the Bulk upload facility | CR (Internal) | LIVE | D1 - Change in delivery | 45.65% |  |  | R & N | 2018-01-22 | Dawn Gallacher | Mark Tullett | 50 |  | Minor Enhancements Team | XO3648 | 2018-11-30 | No Date | 2018-04-30 | ISU | SPA | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | TRUE | FALSE | Two to Five | TRUE | High | FALSE | TRUE | No Date | No Date
4591 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | Out for industry sponsorship/approval to reject | FOF environment for GDE Lookup tables in SAP BW | CR (Internal) | LIVE | X1 - Xoserve propose change not required | 22.22% |  |  | R & N | 2018-01-23 | Julie Bretherton | Simon Harris |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-06-30 | BW | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4593 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Removal of Backbiling Exceptions (BB02, BB04, BB05) | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 26.43% |  |  | R & N | 2018-01-23 | Jo Duncan | Mark Tullett | 50 |  | Minor Enhancements Team | XO3645 | No Date | No Date | 2018-06-30 | ISU | Invoicing | 0-30 days | TRUE | Xoserve | Daily | One | Medium | 2018-06-30 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4674 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Corrective meter exchange to be reflective on DES | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 19.22% |  |  | R & N | 2018-05-17 | Sue Wagstaff | Emma Smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-12-01 | Other | SPA | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4694 | 1. Start-Up (Progressing through change governance) | 2019-06-01 | CSEPs: IGT and GT File Formats (Create new data validations ) | CP | LIVE | A5b - Undergoing Solution Impact Assessment | 19.22% |  |  | R & N | 2018-06-05 | Richard Pomroy (Wales & West Utilities) | Emma smith | Jun2019 |  | Third Party SI / Service Provider |  | No Date | No Date | No Date | ISU | Other | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | FALSE | TRUE | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | TRUE | FALSE | TRUE | Two to Five | FALSE | Medium | FALSE | FALSE | No Date | No Date
4677 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Daily report to identify mismatches in Amendment supporting information (ASP & AML files) | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 40.24% |  |  | R & N | 2018-05-21 | Dan Donovan | Matt Rider |  |  | Third Party SI / Service Provider | XO3683 | 2018-07-30 | No Date | 2018-07-31 | BW | Invoicing | 30-60 days | TRUE | Xoserve | Monthly | Ten Plus | High | 2018-07-31 | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | Two to Five | FALSE | High | FALSE | FALSE | No Date | No Date
4676 | 1. Start-Up (Progressing through change governance) | 2019-06-01 | Reconciliation issues with reads recorded between D-1 to D-5. | CR (External Impacting) | LIVE | A8 - CP high level solution approved at ChMC | 52.85% |  |  | R & N | 2018-05-21 | Rachel Martin | Emma smith | Jun2019 |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-07-31 | ISU | Reads | 30-60 days | TRUE | Xoserve | Monthly | Two to Five | High | 2018-12-03 | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | TRUE | FALSE | FALSE | Five to Twenty | TRUE | High | FALSE | FALSE | No Date | 2018-09-12
4044 | 1. Start-Up (Progressing through change governance) | 2019-06-01 | Extension of ‘Must Read’ process to include Annual Read sites | CP | LIVE | A5b - Undergoing Solution Impact Assessment | 31.23% |  |  | R & N | 2017-12-05 | Andy Clasper | Julie Bretherton | Jun2019 |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-01 | ISU | RGMA | 0-30days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 22: Specific Services | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | 2018-01-10
4621 | 1. Start-Up (Progressing through change governance) | 2019-11-01 | Suspension of the Validation between Meter Index and Uncoverted Converter Index | CP | LIVE | A6 - CP in solution consultation | 19.22% | 0% | 0% | R & N | 2018-02-27 | Rachel Hinsley | Dave Addison | Nov2019 | 176 & 182 | Third Party SI / Service Provider |  | No Date | No Date | 2019-02-01 | ISU | Reads | 100+ days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | TRUE | TRUE | TRUE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
4713 | 1. Start-Up (Progressing through change governance) | 2019-11-01 | Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | CP | LIVE | A5b - Undergoing Solution Impact Assessment | 16.82% |  |  | R & N | 2018-07-16 | Emma Smith (on behalf of James Rigby - Npower) | Ellie Rogers | Nov2019 |  | Third Party SI / Service Provider |  | 2018-11-01 | No Date | 2019-11-01 | ISU | Reads | 60-100 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | TRUE | TRUE | TRUE | Two to Five | FALSE | Medium | FALSE | FALSE | No Date | 2018-07-11
4679 | 1. Start-Up (Progressing through change governance) | 2019-11-01 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | CP | LIVE | A5c - Solution Impact Assessment Review | 28.23% |  |  | R & N | 2018-05-22 | Dave Addison | Emma smith | Nov2019 |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-08-01 | ISU | Reads | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | TRUE | TRUE | TRUE | One | FALSE | Medium | FALSE | FALSE | No Date | 2018-07-11
4642 | 1. Start-Up (Progressing through change governance) | 2019-11-01 | Address Maintenance Solution | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 35.44% |  |  | R & N | 2018-04-03 | Nandini Kundu | Simon Harris | Nov2019 |  | Third Party SI / Service Provider |  | 2018-10-01 | No Date | 2018-10-01 | ISU | SPA | 60-100 days | FALSE | [5 empty] | License Condition | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4378 | 3. Change delivered, awaiting closure approval/sign-off | Solman | Solution Manager Upgrade | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 22.22% |  |  | R & N | 2017-10-02 | Smitha Pichrikat | Neil Morgan |  |  | Third Party SI / Service Provider |  | 2018-04-16 | 2018-04-16 | 2018-04-03 | ISU | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4575 | 3. Change delivered, awaiting closure approval/sign-off | R&N Minor Release/Impact Assessment (Mar'18) | Introduction of a R&N Minor Release Delivery Mechanism | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 22.22% |  |  | R & N | 2018-01-09 | Lee Chambers | Matt Rider |  |  | Third Party SI / Service Provider |  | 2018-05-15 | 2018-05-15 | 2018-05-15 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4645 | 1. Start-Up (Progressing through change governance) | 2019-11-01 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | CR (External Impacting) | LIVE | A5a - Solution Development | 27.63% |  |  | R & N | 2018-04-03 | Rachel Hinsley | Rachel Hinsley | Nov2019 |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-11-02 | ISU | Invoicing | 60-100 days | TRUE | Xoserve | Daily | One | High | 2018-11-02 | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | TRUE | TRUE | TRUE | Two to Five | FALSE | Medium | FALSE | FALSE | No Date | No Date
4574 | 2. Change sanction/approved and in project delivery | R&N New Environment (Apr'18) | Provision of a New Project Track UK Link Environment | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | R & N | 2018-01-08 | Lee Chambers | Lee Chambers |  |  | Third Party SI / Service Provider |  | 2018-09-01 | No Date | 2018-06-15 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4584 | 1. Start-Up (Progressing through change governance) | CSS | Central Switching Services | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 15.62% |  |  | R & N | 2018-01-17 | Andy Earnshaw | Smitha Pichrikat |  |  | Third Party SI / Service Provider |  | 2022-02-28 | No Date | 2020-12-01 | Other | Other | 100+ days | FALSE | [5 empty] | MOD/Ofgem | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4627 | 1. Start-Up (Progressing through change governance) | CSS | Consequential Central Switching Services | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 26.43% |  |  | R & N | 2018-03-09 | Andy Earnshaw | Smitha Pichrikat |  |  | Third Party SI / Service Provider |  | 2020-06-01 | No Date | 2020-06-01 | ISU | SPA | 100+ days | FALSE | [5 empty] | License Condition | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | TRUE | TRUE | TRUE | Five to Twenty | FALSE | High | FALSE | TRUE | No Date | No Date
4612 | 2. Change sanction/approved and in project delivery | MR Drop 2 | RGMA Activity on Transfer Date | CR (Internal) | LIVE | D1 - Change in delivery | 45.65% |  |  | R & N | 2018-02-20 | John Harris | Matt Rider | Sep2018 |  | Third Party SI / Service Provider |  | 2018-09-10 | No Date | 2018-04-01 | ISU | Reads | 100+ days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | TRUE | TRUE | FALSE | Two to Five | TRUE | High | FALSE | TRUE | No Date | No Date
4576 | 2. Change sanction/approved and in project delivery | MR Drop 2 | Class 4 Transfer Reads not visible to shippers in DES | CP | LIVE | D1 - Change in delivery | 26.43% |  |  | R & N | 2018-01-09 | Alison Cross | Matt Rider | Sep2018 |  | Third Party SI / Service Provider | XO3630 | 2018-09-14 | No Date | 2018-09-30 | BW | Portal | 30-60 days | TRUE | External Customer | Monthly | One | Low | 2018-03-30 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | 2018-03-07
4658 | 2. Change sanction/approved and in project delivery | AQ Bands Increase | Read validation – increasing outer tolerance value for specific AQ bands for Class 3 & 4 Meter Points | CP | LIVE | D1 - Change in delivery | 40.84% |  |  | R & N | 2018-04-25 | Emma Smith | Padmini Duvvuri |  |  | Third Party SI / Service Provider |  | 2018-11-05 | No Date | 2018-06-01 | ISU | Reads | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | TRUE | TRUE | TRUE | One | TRUE | Medium | FALSE | TRUE | No Date | 2018-11-02
4699 | 2. Change sanction/approved and in project delivery | MR Drop 2 | Minor Release Drop 2 – Sept-18 | CR (Internal) | LIVE | D1 - Change in delivery | 15.02% |  |  | R & N | 2018-06-12 | Julie Bretherton | Matt Rider | Sep2018 |  | Third Party SI / Service Provider |  | 2018-10-27 | No Date | 2018-11-06 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | TRUE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date
4665 | 1. Start-Up (Progressing through change governance) | 2019-09-27 | Creation of new End User Categories | CP | LIVE | A10 - ICAF - Capture complete, awaiting CIO PM assignment | 37.24% |  |  | R & N | 2018-05-02 | Emma Smith | Emma smith | Sep2019 |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-10-01 | ISU | Invoicing | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 15: Demand Estimation | TRUE | TRUE | TRUE | Two to Five | TRUE | Medium | FALSE | FALSE | No Date | 2018-07-11
4711 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Feasibility Study to Analyse Alignment of Release Dates for Electricity and Gas | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 33.63% |  |  | R & N | 2018-07-02 | Padmini Duvvuri | Catrin Morgan |  |  | Xoserve Resource |  | No Date | No Date | 2018-07-31 | ISU | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE |  | FALSE | High | FALSE | FALSE | No Date | No Date

## UK Link_2yr_view
Change Allocation | Count of XRNs
Solution Manager Update (Feb'18) | 1
Release Nov 19 | 5
Release Sep 19 | 1
Release Jun 19 | 9
Release Feb 19 | 0
R3.0 (Nov'18) | 15
R2.0 (Jun'18) | 17
R1.0 (Nexus) | 1
R&N New Environment (Apr'18) | 1
R&N Minor Release/Impact Assessment (Mar'18) | 1
Out for industry sponsorship/approval to reject | 2
Internal req Gathering (Capture) | 15
Minor Enhancement Delivered Change | 15
CSS | 2
Candidate for Minor Release Drop 2 | 3
Candidate for Minor Release Drop 1 | 5
AQ Bands Increase | 1
Closedown | 0
Grand Total | 94
Please filter in column C within the 'R&N_Live_Changes' tab to view specific XRNs

## Sheet4 (hidden)
Row Labels | Count of XRN Ref
(blank)
2019-11-01 | 5 | X
2019-09-27 | 1 | X
2019-06-01 | 9 | X
Solman | 1 | X
R3.0 (Nov'18) | 15 | X
R2.0 (Jun'18) | 17 | X
R1.0 (Nexus) | 1 | X
R&N New Environment (Apr'18) | 1 | X
R&N Minor Release/Impact Assessment (Mar'18) | 1 | X
Out for industry sponsorship/approval to reject | 2 | x
MR Drop 2 | 3 | X
MR Drop 1 | 5 | X
Minor Enhancement Delivered Change | 15 | x
Internal Requirements Gathering (Capture) | 15 | x
CSS | 2 | X
AQ Bands Increase | 1 | X
Grand Total | 94

## Gemini & Data Stream POAP (hidden)
Gemini
Data Platform

## Gemini & Data Stream_Live_Chang (hidden)
XRN Ref | High-Level Status | R&N Release Allocation | Change Title | Change Type | Delivery Status | Change Lifecycle Status | Xoserve Proposed Indicative Prioritisation Score | July'17 Change Demand Backlog ChMC Priority | July'17 Change Demand Backlog SDG Priority | Xoserve Platform Owner | Origination Date | Change Originator | Xoserve Project Manager | R&N Release Number | Previous UK Link CR Ref | Delivery Team | ClearQuest Ticket (Minor Enhancement Delivery) | Current Delivery Implementation Forecast Date | Actual Delivery Implementation Date | Customer Requested Implementation Date | Primary Application Impacted | Business Process Impact | Flash IA: Perceived Delivery Effort | Workaround Available? | Workaround Accountability | Workaround Frequency | No. of Xoserve FTEs required to service the workaround | Workaround Complexity? | Workaround Lifespan | Change Driver | Change Beneficiary | Shipper Impact | Network Impact | iGT Impact | Primary Impacted DSC Service Area | Number of DSC Service Areas impacted | Change Improvement Scale (Size of proposed change) | Customer System Changes Required? | Customer Testing Likely Required? | Customer Training Required? | Safety of Supply at risk? | Financial Loss Incurred to Customer? | Customer Switching at risk? | ChMC CP Approval date | ChMC EQR Approval date | ChMC BER Approval date | ChMC CCR Approval date
4758 | 1. Start-Up (Progressing through change governance) |  | SMP monthly AQ calculations – triggered new AQ/EUC | CR (Internal) | LIVE | A9 - Internal change progressing through capture | #VALUE! |  |  | Data Office | 2018-09-07 | Mark Summersmith | Jo Duncan |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-10-01 | BW | Other | 0-30 days | TRUE | Xoserve | Monthly | No Xoserve FTEs | Low | No Lifespan Date | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | FALSE | High | FALSE | FALSE | No Date | No Date
4759 | 1. Start-Up (Progressing through change governance) |  | Alt Han Company (Alt Han Co) Request for Ongoing Provision of Supply Point Portfolio Information | CR (ASR) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 29.43% |  |  | Data Office | 2018-09-10 | Richard Johnson | Jo Duncan |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-11-30 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | TRUE | Low | FALSE | FALSE | No Date | No Date
4761 | 1. Start-Up (Progressing through change governance) |  | Request for data to support an industry modification | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 24.02% |  |  | Data Office | 2018-09-10 | Rachel Hinsley | Jo Duncan |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-30 | BW | No Process | 0-30 days | FALSE | [5 empty] | MOD/Ofgem | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | FALSE | Medium | FALSE | FALSE | No Date | No Date
4739 | 1. Start-Up (Progressing through change governance) |  | Standard Testing Toolset | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 9.61% |  |  | T & SS | 2018-08-15 | Jon Follows | Jon Follows |  |  | Third Party SI / Service Provider |  | No Date | No Date | No Date | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | TRUE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | FALSE | Low | FALSE | FALSE | No Date | No Date
4741 | 1. Start-Up (Progressing through change governance) |  | National Grid Transmission and Deloittes Audit Reporting Suite (AS20180410) | CR (ASR) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 11.41% |  |  | Data Office | 2018-08-14 | Fiona Mills | Jo Duncan |  |  | Xoserve Resource | XOS3700 | No Date | No Date | 372092 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | FALSE | Medium | FALSE | FALSE | No Date | No Date
4743 | 1. Start-Up (Progressing through change governance) |  | MAM Reconciliation Report (TP20180406 - SPAA – Supplier Performance Schedule 22) | CR (ASR) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 35.44% |  |  | Data Office | 2018-08-20 | Emma Partlett | Jo Duncan |  |  | Xoserve Resource | XO3701 | No Date | No Date | 2018-11-02 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | Multiple Market Groups | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | FALSE | TRUE | FALSE | Five to Twenty | TRUE | High | FALSE | FALSE | No Date | No Date
4744 | 2. Change sanction/approved and in project delivery |  | Tansform US - IX Server Replacement | CR (Internal) | LIVE | D1 - Change in delivery | 9.61% |  |  | T & SS | 2018-08-20 | Annie Griffith | Michael Dickson |  |  | Xoserve Resource |  | No Date | No Date | No Date | IX | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE |  | FALSE | Medium | FALSE | FALSE | No Date | No Date
4745 | 1. Start-Up (Progressing through change governance) |  | Data modelling CLC process | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 19.22% |  |  | Data Office | 2018-08-20 | Mike Orsler/Tahera Choudhury | Alex Sharp |  |  | Xoserve Resource |  | 2018-12-31 | No Date | 2018-09-30 | IX | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4749 | 1. Start-Up (Progressing through change governance) |  | Analysis for the provision of data services to Third Parties | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 14.41% |  |  | Data Office | 2018-08-29 | Mark Pollard | Emma smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2019-01-31 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4750 | 1. Start-Up (Progressing through change governance) |  | Analysis for a Dual Fuel Enquiry Service | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 16.22% |  |  | Data Office | 2018-08-29 | Mark Pollard | Emma smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-11-30 | BW | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4751 | 1. Start-Up (Progressing through change governance) |  | UIG Shipper Dashboards & Internal Dashboards | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 21.62% |  |  | Data Office | 2018-08-29 | Michele Downes | Anthony Baker |  |  | Xoserve Resource |  | No Date | No Date | 2018-10-15 | BW | Other | No Delivery Effort | TRUE | Xoserve | Monthly | One | Medium | 2018-12-31 | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | TRUE | Two to Five | FALSE | High | FALSE | FALSE | No Date | No Date
4752 | 1. Start-Up (Progressing through change governance) |  | Meter Read Performance | CP | LIVE | A5 - CP in capture with DSG | 25.83% |  |  | Data Office | 2018-08-31 | Rachel Hinsley | Jo Duncan |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-30 | BW | Reads | 0-30 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 3: Record/submit Data in Compliance with UNC | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | 2018-09-12
4754 | 1. Start-Up (Progressing through change governance) |  | Monthly GT / IGT Supply Point Count to be supplied to SPAA Code Administrator | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 21.62% |  |  | Data Office | 2018-09-03 | Paul Orsler | Paul Orsler |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-10-31 | BW | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | FALSE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4756 | 1. Start-Up (Progressing through change governance) |  | Reporting Balanced Scorecard via BIRST | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 21.62% |  |  | Data Office | 2018-09-03 | Sabah Hussain | Jo Duncan |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-28 | Birst | Other | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 2018-12-31 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4734 | 2. Change sanction/approved and in project delivery |  | Capture Process Model (internal process) | CR (Internal) | LIVE | D1 - Change in delivery | 16.22% |  |  | Data Office | 2018-08-08 | Emma Smith | Susan Helders |  |  | Xoserve Resource |  | 2018-10-31 | No Date | 2018-10-31 | Other | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4730 | 1. Start-Up (Progressing through change governance) |  | SPAA – Supplier Performance Report (TP20180395) | CR (ASR) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 20.42% |  |  | Data Office | 2018-08-07 | Michael Orsler/Emma Partlett | Jo Duncan |  |  | Xoserve Resource | XO3702 | No Date | No Date | 2018-11-01 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | Multiple Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
4731 | 2. Change sanction/approved and in project delivery |  | Capture Process Model | CR (Internal) | LIVE | D1 - Change in delivery | 24.62% |  |  | Data Office | 2018-08-07 | Steve Nunnington | Susan Helders |  |  | Xoserve Resource |  | No Date | No Date | 2018-09-07 | Other | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4646 | 2. Change sanction/approved and in project delivery |  | Amendment to plot to postal report | CR (Internal) | LIVE | D1 - Change in delivery | 30.63% |  |  | Data Office | 2018-04-10 | Tahera Choudhury | Jo Duncan | 50 |  | Minor Enhancements Team | XO3678 | 2018-11-26 | No Date | 2018-05-04 | BW | SPA | 0-30 days | FALSE | [5 empty] | MOD/Ofgem | One Market Group | FALSE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4623 | 2. Change sanction/approved and in project delivery |  | XEC Customer Dashboard Development | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | Data Office | 2018-02-05 | James Verdon | Jo Duncan | 0 |  | Xoserve Resource |  | 2018-11-30 | No Date | 2018-05-11 | Birst | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4702 | 1. Start-Up (Progressing through change governance) |  | Opportunity 1: Switching Performance dashboard (s) to enable supplier incentivisation | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 24.02% |  |  | Data Office | 2018-06-18 | Rebecca Roden | Jo Duncan |  |  | Xoserve Resource |  | No Date | No Date | 2019-05-31 | Other | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4703 | 1. Start-Up (Progressing through change governance) |  | Opportunity 2: Duel fuel enquiry service to deliver improved consumption estimations | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 33.63% |  |  | Data Office | 2018-06-18 | Rebecca Roden | Mark Pollard |  |  | Xoserve Resource |  | No Date | No Date | 2018-05-31 | Other | AQ | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | TRUE | TRUE | TRUE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4706 | 1. Start-Up (Progressing through change governance) |  | (ASR) National Grid Gas – Test Support & Consultancy on Connectivity between Xoserve & Gemini | CR (ASR) | LIVE | A9 - Internal change progressing through capture | 20.42% |  |  | T & SS | 2018-06-25 | Greg Causon | Nicola Patmore |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-30 | Gemini | Other | 100+ days | FALSE | [5 empty] | Additional or 3rd Party Service Request | No Change Beneficiary | FALSE | TRUE | FALSE | FALSE | TRUE | Service Area 24: Additional Service Request or Third Party Request | TRUE | TRUE | TRUE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4169 | 2. Change sanction/approved and in project delivery |  | To update functionality in Gemini to ensure that all Cash Call Notices and TemplaRequest for Project Management resource to manage the analysis and resolution of the issues with the Amendment invoicees reflect UNC Section X and Energy Balancing Credit Rul | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | T & SS | 2017-01-09 | Loraine O’Shaughnessy | Mark Tullett | 50 |  | Minor Enhancements Team | XO3452 | 2018-11-02 | No Date | 2018-09-13 | Gemini | Other | 0-30days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4672 | 3. Change delivered, awaiting closure approval/sign-off |  | Extension of PCW API Service to Suppliers | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 25.23% |  |  | Data Office | 2018-05-14 | Mark Pollard | Mark Pollard |  |  | Xoserve Resource |  | 2018-06-29 | 2018-06-29 | 2018-06-29 | Other | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4673 | 3. Change delivered, awaiting closure approval/sign-off |  | Identification of Short Haul in Non-standard Sites Reports | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 29.43% |  |  | Data Office | 2018-05-14 | Thomas Rooney | Jo Duncan |  |  | Xoserve Resource |  | 2018-08-24 | 2018-08-24 | 2018-06-30 | BW | Other | 0-30 days | TRUE | Xoserve | Monthly | Two to Five | Low | 2019-02-28 | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | FALSE | FALSE | FALSE | Two to Five | FALSE | Medium | FALSE | FALSE | No Date | No Date
4729 | 2. Change sanction/approved and in project delivery |  | Addition of data items to VOL Enhanced Report | CR (ASR) | LIVE | D1 - Change in delivery | 23.42% |  |  | Data Office | 2018-08-03 | Greg Causon | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-30 | No Date | 2018-09-01 | No Application | No Process | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | FALSE | Low | FALSE | FALSE | No Date | No Date
4639 | 2. Change sanction/approved and in project delivery |  | Customer KVI Reporting | CR (Internal) | LIVE | D1 - Change in delivery | 37.84% |  |  | Data Office | 2018-03-27 | Michele Downes | Jo Duncan |  |  | Xoserve Resource |  | 2018-10-31 | No Date | 2018-05-01 | Birst | Other | 0-30 days | TRUE | Xoserve | Daily | One | Medium | 2018-04-27 | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 19: Network Operator and User Relationship Management | FALSE | FALSE | FALSE | All | FALSE | High | FALSE | FALSE | No Date | No Date
4714 | 2. Change sanction/approved and in project delivery |  | Birst Reporting for Strategy House Embedding | CR (Internal) | LIVE | D1 - Change in delivery | 33.63% |  |  | Data Office | 2018-07-16 | Jo Duncan | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-28 | No Date | 2018-08-17 | Birst | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4619 | 2. Change sanction/approved and in project delivery |  | SAP BW MPRL Delta Table Creation | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | Data Office | 2018-02-26 | Steve Concannon | Fay Morris | 50 |  | Minor Enhancements Team | XO3665 | 2018-11-09 | No Date | 2018-08-30 | BW | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4718 | 1. Start-Up (Progressing through change governance) |  | BW Universe Changes Deployment | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 27.63% |  |  | Data Office | 2018-07-20 | Jo Duncan | Jo Duncan |  |  | Minor Enhancements Team | XO3693 | No Date | No Date | 2018-08-31 | BW | Other | 0-30 days | TRUE | Xoserve | Monthly | Two to Five | High | 2018-12-31 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4724 | 1. Start-Up (Progressing through change governance) |  | Removal of Asset Status codes DM and FA from file format documentation (impact assessment required) | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 25.23% |  |  | Data Office | 2018-07-31 | Ellie Rogers | Rebecca Roden |  |  | Xoserve Resource |  | No Date | No Date | 2018-09-10 | ISU | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
4683 | 2. Change sanction/approved and in project delivery |  | Class 3 & 4 Energy Comparison Report | CR (Internal) | LIVE | D1 - Change in delivery | 36.64% |  |  | Data Office | 2018-05-25 | Jo Tedd | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-28 | No Date | 2018-07-01 | Gemini | Invoicing | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | Two to Five | TRUE | Medium | FALSE | FALSE | No Date | No Date
4684 | 1. Start-Up (Progressing through change governance) |  | SAP BW Accelerator: Table Migration | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 16.82% |  |  | Data Office | 2018-05-29 | Fay morris | Fay Morris |  |  | Third Party SI / Service Provider |  | 2019-02-01 | No Date | 2019-02-01 | BW | Other | 100+ days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4666 | 2. Change sanction/approved and in project delivery |  | Changes to Gemini system to provide Business User access to Class 1 & 2 Energy values, to view & update & include additional data items in existing system generated reports | CR (Internal) | LIVE | D1 - Change in delivery | 40.84% |  |  | T & SS | 2018-05-04 | Jo Tedd | Hannah Reddy |  |  | Third Party SI / Service Provider | XO3676 | No Date | No Date | 2018-05-31 | Gemini | Invoicing | 60-100 days | TRUE | Xoserve | Daily | One | Medium | 2018-12-28 | Xoserve Internal CR (business improvement initiative) | One Market Participant | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | Two to Five | TRUE |  | FALSE | FALSE | No Date | No Date
4542 | 2. Change sanction/approved and in project delivery |  | Changes to the Shipper Portfolio Summary Report (new fields and removal of fields no longer applicable) | CP | LIVE | D1 - Change in delivery | 23.42% |  |  | Data Office | 2017-11-24 | Emma Smith | Jo Duncan |  |  | Xoserve Resource | XO3605 | 2018-11-30 | No Date | 2018-11-01 | BW | Other | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 2019-01-30 | ChMC endorsed Change Proposal | One Market Participant | TRUE | FALSE | FALSE | FALSE | TRUE | Service Area 18: Provision of User Reports and Information | FALSE | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | 2018-04-11 | 2018-01-10
4525 | 3. Change delivered, awaiting closure approval/sign-off |  | Transparency of the Rolling AQ Process | CP | LIVE | F1 - CCR/Closedown document in progress | 28.83% |  |  | Data Office | 2017-10-31 | Shane Preston/Rachel Hinsley | Jo Duncan |  |  | Xoserve Resource | XOS3584 | 2018-07-31 | 2018-07-31 | 2018-05-25 | BW | SPA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | FALSE | TRUE | Service Area 18: Provision of User Reports and Information | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | 2018-04-11 | 2018-02-07
2831.5a | 3. Change delivered, awaiting closure approval/sign-off |  | Smart Metering UNC MOD 430 DCC Testing and Trialling Pre Nexus | CP | LIVE | F1 - CCR/Closedown document in progress | 28.23% |  |  | T & SS | 2015-12-22 | Jo Feguson | Jon Follows |  |  | Third Party SI / Service Provider |  | 2017-03-31 | 2017-03-31 | 2017-03-31 | Other | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | TRUE | TRUE | FALSE | TRUE | Service Area 17: UK Link Services | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4686 | 1. Start-Up (Progressing through change governance) |  | Smart Metering Report | CP | LIVE | A5a - Solution Development | 28.83% |  |  | Data Office | 2018-06-04 | Liam Percy (CNG) | Emma smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-01 | BW | RGMA | 0-30 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | FALSE | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
4712 | 1. Start-Up (Progressing through change governance) |  | HR and Finance Birst Reporting | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 22.22% |  |  | Data Office | 2018-07-09 | Paul O’Toole | Jo Duncan |  |  | Third Party SI / Service Provider |  | 2018-09-28 | No Date | 2018-08-17 | Birst | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4594 | 2. Change sanction/approved and in project delivery |  | Customer Inclusion for BIRST Exceptions | CR (Internal) | LIVE | D1 - Change in delivery | 23.42% |  |  | Data Office | 2018-01-23 | Jo Duncan/Thomas Elce | Jo Duncan |  |  | Xoserve Resource |  | 2019-02-28 | No Date | 2018-03-23 | Birst | Other | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 2018-03-30 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4580 | 2. Change sanction/approved and in project delivery |  | Shipper Performance Birst Dashboard (by Data Cleansing Topic) | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | Data Office | 2018-01-16 | James Verdon | Jo Duncan |  |  | Xoserve Resource |  | 2018-12-31 | No Date | 2018-08-10 | Other | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4726 | 1. Start-Up (Progressing through change governance) |  | Mod 0431 process enhancements | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 34.83% |  |  | Data Office | 2018-08-01 | Tahera Choudhury | Charlie Haley |  |  | Xoserve Resource |  | No Date | No Date | 2018-11-01 | BW | SPA | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 2018-11-01 | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE |  | TRUE | High | FALSE | FALSE | No Date | No Date
4328 | 3. Change delivered, awaiting closure approval/sign-off |  | Report of iGT Meter Points where the confirming shipper is not the elected shipper | CP | LIVE | F1 - CCR/Closedown document in progress | 31.23% |  |  | Data Office | 2017-07-05 | Emma Smith | Jo Duncan | 50 |  | Minor Enhancements Team | XOS3615 | 2018-08-10 | 2018-08-10 | 2018-08-10 | BW | SPA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | TRUE | TRUE | FALSE | TRUE | Service Area 18: Provision of User Reports and Information | FALSE | FALSE | FALSE |  | FALSE | Medium | FALSE | FALSE | 2018-03-07 | 2017-07-13
4426 | 2. Change sanction/approved and in project delivery |  | Impact Assessment on changes to Market Intelligence report and Change of Supplier reporting suite ahead of Ofgem RFI | CR (Internal) | LIVE | D1 - Change in delivery | 42.04% | TBP | High | Data Office | 2016-04-28 | Paul Orsler | Jo Duncan |  | UKLP IADBI192 | Xoserve Resource |  | 2018-09-29 | No Date | 2018-07-30 | BW | Other | 31-100days | FALSE | [5 empty] | CMA Order | All UK Gas Market Participants | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4611 | 1. Start-Up (Progressing through change governance) |  | Replacement/Upgrade of Demand Estimation Systems and Processes | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 25.83% |  |  | Data Office | 2018-02-20 | Fiona Cottam | Fay Morris |  |  | Third Party SI / Service Provider |  | 2019-02-28 | No Date | 2019-03-01 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4655 | 1. Start-Up (Progressing through change governance) |  | Electronic CRM system to Capture Customer Contact Details and Email Conversations | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 22.22% |  |  | T & SS | 2018-04-24 | Adam Jones | Dene Williams |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-06-01 | Other | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4610 | 1. Start-Up (Progressing through change governance) |  | ASR Request - Reporting to SPAA Secretariat in Support of SPAA Schedule 25 – Management of Prepayment Activities | CR (ASR) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 26.43% |  |  | Data Office | 2018-02-20 | Greg Causon | Jo Duncan |  |  | Minor Enhancements Team | XO3679 | No Date | No Date | 2018-06-30 | BW | SPA | 60-100 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | Multiple Market Participants | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | FALSE | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
3676 | 3. Change delivered, awaiting closure approval/sign-off |  | Amendment to the AQ &SOQ File and Field Length | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 19.22% | 0% | 0% | T & SS | 2015-03-24 | Jo Tedd/ Dan Donovan | Mark Tullett | 50 | UKLP IADBI080 | Minor Enhancements Team | XO3598 | 2018-05-08 | 2018-05-08 | 2018-10-01 | Gemini | SPA | 0-30days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4493 | 3. Change delivered, awaiting closure approval/sign-off |  | BIRST Connect integration | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 22.22% |  |  | Data Office | 2017-06-26 | Steve Concannon | Emma Rose | 50 | UKLP IADBI353 | Third Party SI / Service Provider |  | 2018-01-26 | 2018-01-26 | 2017-11-30 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4596 | 2. Change sanction/approved and in project delivery |  | Setup of File Transfer mechanism from BO to IX | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | Data Office | 2018-01-23 | Steve Concannon | Fay Morris | 50 |  | Minor Enhancements Team | XO3647 | 2018-09-22 | No Date | 2018-04-30 | IX | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4689 | 2. Change sanction/approved and in project delivery |  | Aggregate Energy AQ Report | CR (Internal) | LIVE | D1 - Change in delivery | 23.42% |  |  | Data Office | 2018-06-04 | Lee Jackson | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-29 | No Date | 2018-07-01 | BW | AQ | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Participant | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4473 | 1. Start-Up (Progressing through change governance) |  | Sybase NLS Solution Design Gap | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 22.22% | TBP | Low | Data Office | 2017-04-11 | Lee Chambers | Jo Duncan |  | UKLP IADBI317 | Third Party SI / Service Provider |  | No Date | No Date | 2018-06-01 | BW | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4354 | 3. Change delivered, awaiting closure approval/sign-off |  | Request for New DNO Report Nested CSEPs Hierarchy Report | CP | LIVE | F2 - CCR awaiting ChMC approval | 27.03% |  |  | Data Office | 2017-09-01 | Cadent Gas /Emma Smith | Jo Duncan | 50 |  | Minor Enhancements Team | XOS3577 | 2018-05-15 | 2018-05-15 | 2018-02-23 | BW | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | FALSE | TRUE | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | FALSE | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | 2018-03-07 | 2017-10-10
4634 | 1. Start-Up (Progressing through change governance) |  | Data Catalogue | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 14.41% |  |  | Data Office | 2018-03-21 | Rachel Hinsley | Dave Addison |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2019-02-01 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | Two to Five | FALSE | Medium | FALSE | FALSE | No Date | No Date
4567 | 2. Change sanction/approved and in project delivery |  | Amendment to plot to postal report | CR (Internal) | LIVE | D1 - Change in delivery | 24.62% |  |  | Data Office | 2018-01-02 | Tahera Choudhury | Jo Duncan |  |  | Xoserve Resource |  | 2018-11-30 | No Date | 2018-02-28 | BW | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4571 | 2. Change sanction/approved and in project delivery |  | MAM and MAP asset data analysis and reporting | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | Data Office | 2018-01-03 | Andy Miller | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-29 | No Date | 2018-03-23 | BW | Reads | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4570 | 2. Change sanction/approved and in project delivery |  | BW Reports - RA/ RANTS Reporting Logic | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | Data Office | 2017-01-03 | Michael Maguire | Jo Duncan | 50 |  | Minor Enhancements Team | XO3639 | 2018-10-08 | No Date | 2018-01-31 | BW | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4590 | 2. Change sanction/approved and in project delivery |  | SLSP - Incorrect Seasonal Large Supply Point charging | CR (Internal) | LIVE | D1 - Change in delivery | 40.84% |  |  | Data Office | 2018-01-12 | Carole Elwell | Mark Tullett | 50 |  | Minor Enhancements Team | XO3644 | 2018-11-30 | No Date | 2018-08-31 | ISU | Invoicing | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 2018-03-31 | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | FALSE | TRUE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | Two to Five | TRUE | Medium | FALSE | FALSE | No Date | No Date
4592 | 2. Change sanction/approved and in project delivery |  | BIRST work item inclusion & multiple daily updates | CR (Internal) | LIVE | D1 - Change in delivery | 26.43% |  |  | Data Office | 2018-01-23 | Jo Duncan | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-28 | No Date | 2018-06-29 | Birst | SPA | 0-30 days | TRUE | Xoserve | Daily | One | Medium | 2018-03-30 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4636 | 2. Change sanction/approved and in project delivery |  | ASR – AS20180277 ENGIE Enhanced Portfolio shipper pack (VOL) | CR (ASR) | LIVE | D1 - Change in delivery | 25.23% |  |  | Data Office | 2018-03-26 | Greg Causon | Jo Duncan |  |  | Xoserve Resource |  | 2018-11-30 | No Date | 2018-05-25 | Other | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | FALSE | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
4638 | 2. Change sanction/approved and in project delivery |  | ASR – NGS Asset AS20180274 | CR (ASR) | LIVE | D1 - Change in delivery | 25.23% |  |  | Data Office | 2018-03-26 | Greg Causon | Jo Duncan |  |  | Xoserve Resource |  | 2018-11-30 | No Date | 2018-06-29 | Other | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | FALSE | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
4653 | 1. Start-Up (Progressing through change governance) |  | National Grid Transmission iConversion Project | CR (ASR) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 25.23% |  |  | T & SS | 2018-04-24 | Greg Causon | Emma Rose |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-01 | Gemini | Other | 30-60 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | FALSE | TRUE | FALSE | FALSE | TRUE | Service Area 24: Additional Service Request or Third Party Request | TRUE | TRUE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
3667a | 1. Start-Up (Progressing through change governance) |  | Provision of Prospective Formula Year AQ/SOQ and Historic RAQ to Proposing Users | CP | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 37.24% |  |  | Data Office | 2018-04-04 | James Rigby | Charlie Haley |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-12-01 | ISU | SPA | 60-100 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | TRUE | TRUE | FALSE | One | TRUE | Medium | FALSE | FALSE | No Date | 2018-04-11
4675 | 1. Start-Up (Progressing through change governance) |  | Digital signage Links for Birst Connectivity | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 22.22% |  |  | Data Office | 2018-05-17 | Jo Duncan | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-30 | No Date | 2018-06-30 | Birst | Other | No Delivery Effort | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4757 | 2. Change sanction/approved and in project delivery |  | UIG Issues: Read Performance and WAR Band Reports for Ofgem | CR (Internal) | LIVE | D1 - Change in delivery | 21.02% |  |  | Data Office | 2018-09-05 | Fiona Cottam | Anthony Baker |  |  | Xoserve Resource |  | No Date | No Date | No Date | BW | No Process | 0-30 days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | TRUE | High | FALSE | FALSE | No Date | No Date
3457 | 3. Change delivered, awaiting closure approval/sign-off |  | Solution to meet the obligations of UNC MOD 425V & UNC MOD455 | CP | LIVE | F1 - CCR/Closedown document in progress | 21.02% |  |  | T & SS | 2014-08-28 | Joanna Ferguson | Jon Follows |  |  | Third Party SI / Service Provider |  | 2015-07-09 | 2015-07-09 | 2000-02-02 | ISU | SPA | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | TRUE | FALSE | FALSE | TRUE | Service Area 1: Manage Supply Point Registration | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | 2015-01-19 | 2014-09-03
4110 | 3. Change delivered, awaiting closure approval/sign-off |  | Creation of a Service to Release Domestic Consumer Data to W’s & TPI’s | CP | LIVE | F2 - CCR awaiting ChMC approval | 21.02% |  |  | T & SS | 2016-10-12 | Jo Ferguson | Charlie Haley |  |  | Third Party SI / Service Provider |  | 2017-07-31 | 2017-07-31 | 2000-02-02 | ISU | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 24: Additional Service Request or Third Party Request | FALSE | FALSE | FALSE | Five to Twenty | FALSE | Medium | FALSE | FALSE | No Date | No Date
3390 | 3. Change delivered, awaiting closure approval/sign-off |  | Billing History by all NTS capacity / commodity related charges (2003 - 2013) | CP | LIVE | F1 - CCR/Closedown document in progress | 21.02% |  |  | T & SS | 2014-05-16 | Sean McGoldrick | Charlie Haley |  |  | Third Party SI / Service Provider |  | 2014-10-08 | 2014-10-08 | 2000-02-02 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 8: Credit Risk Management (including Cash Collection) and Management of Neutrality Accounting Processes | FALSE | FALSE | FALSE | Two to Five | FALSE | Medium | FALSE | FALSE | No Date | No Date
3428 | 3. Change delivered, awaiting closure approval/sign-off |  | Correction of CWV data on the National Grid Operational website as a result of incorrect weather flows for NE LDZ | CP | LIVE | F1 - CCR/Closedown document in progress | 21.02% |  |  | T & SS | 2014-06-18 | Joanna Ferguson | Charlie Haley |  |  | Third Party SI / Service Provider |  | 2014-06-23 | 2014-06-23 | 2000-02-02 | ISU | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 15: Demand Estimation | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4009 | 3. Change delivered, awaiting closure approval/sign-off |  | Billing History by all NTS capacity / commodity related charges (applicable dates in 2014 to Nexus implementation) | CP | LIVE | F2 - CCR awaiting ChMC approval | 21.02% |  |  | T & SS | 2016-04-12 | Beverley Viney | Charlie Haley |  |  | Third Party SI / Service Provider |  | 2017-07-19 | 2017-07-19 | 2016-06-30 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | TRUE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date
4043 | 3. Change delivered, awaiting closure approval/sign-off |  | DN Sales Outbound Services | CP | LIVE | F1 - CCR/Closedown document in progress | 27.03% |  |  | T & SS | 2016-05-26 | Chris Warner | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-07-31 | 2018-06-29 | 2016-10-01 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | FALSE | TRUE | FALSE | FALSE | TRUE | Service Area 19: Network Operator and User Relationship Management | FALSE | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
4149 | 2. Change sanction/approved and in project delivery |  | NG Gateway Migration | CP | LIVE | D1 - Change in delivery | 27.03% |  |  | T & SS | 2016-11-28 | Beverley Viney | Nicola Patmore |  |  | Third Party SI / Service Provider |  | 2018-10-15 | No Date | 2018-03-31 | Other | Other | 100+days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | FALSE | TRUE | FALSE | FALSE | TRUE | Service Area 19: Network Operator and User Relationship Management | FALSE | FALSE | FALSE | One | FALSE | High | FALSE | FALSE | No Date | 2017-07-19
4376 | 2. Change sanction/approved and in project delivery |  | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | CP | LIVE | D1 - Change in delivery | 19.22% |  |  | T & SS | 2017-09-22 | Chris Gumbley/Darren Lond | Nicola Patmore |  |  | Third Party SI / Service Provider |  | 2018-11-18 | No Date | 2019-01-01 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | FALSE | TRUE | FALSE | FALSE | TRUE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | 2017-10-12
4550 | 1. Start-Up (Progressing through change governance) |  | Gemini Re-platform | CP | LIVE | C1 - Delivery Business Case/BER in progress | 9.009% |  |  | T & SS | 2017-12-04 | Phil Hobbins | Hannah Reddy |  |  | Third Party SI / Service Provider |  | 2020-01-01 | No Date | 2020-01-01 | Gemini | No Process | 60-100 days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 20: UK Link Gemini System Services | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | 2017-12-13
4632 | 2. Change sanction/approved and in project delivery |  | Analysis for Gemini Enhancements | CP | LIVE | D1 - Change in delivery | 28.23% |  |  | T & SS | 2018-03-19 | Celine Reddin/Beverley Viney | Hannah Reddy |  |  | Third Party SI / Service Provider |  | 2018-10-31 | No Date | 2018-09-20 | Gemini | Other | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 20: UK Link Gemini System Services | FALSE | FALSE | FALSE | One | FALSE | High | FALSE | FALSE | 2018-05-09 | 2018-04-11
3151.1 | 3. Change delivered, awaiting closure approval/sign-off |  | Business to Xoserve to Business File Transfer Capability | CP | LIVE | F1 - CCR/Closedown document in progress | 21.02% |  |  | T & SS | 2014-01-16 | Lee Chambers | Jon Follows |  |  | Third Party SI / Service Provider |  | 2014-09-29 | 2014-09-29 | 2014-04-01 | Other | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | TRUE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date
3143 | 2. Change sanction/approved and in project delivery |  | COR3143 - Decommission XFTM & Server Farm & re-direct NG files Phase 1 | CP | LIVE | D1 - Change in delivery | 21.02% |  |  | Data Office | 2013-08-06 | Khawar Ahmed | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-10-26 | No Date | 2015-10-27 | Other | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | TRUE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date
3447 | 2. Change sanction/approved and in project delivery |  | COR3447 - XP1 Decommissioning | CP | LIVE | D1 - Change in delivery | 21.02% |  |  | Data Office | 2014-07-08 | Chris Fears | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-10-26 | No Date | 2000-02-02 | Other | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date
4216 | 3. Change delivered, awaiting closure approval/sign-off |  | API Platform Implementation | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 22.22% |  |  | Data Office | 2017-02-03 | Gareth Hepworth | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-06-20 | 2018-06-20 | 2017-12-10 | BW | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 23: Internal | FALSE | TRUE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4349 | 2. Change sanction/approved and in project delivery |  | Control-M/EM, Server and agent upgrade for Gemini and CMS | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | T & SS | 2017-08-18 | Annie Griffith | Emma Rose |  |  | Third Party SI / Service Provider |  | 2018-12-29 | No Date | 2018-07-31 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4324 | 2. Change sanction/approved and in project delivery |  | Checkpoint Hardware Upgrade | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | T & SS | 2017-06-29 | Chris Fears | Emily Pickard |  |  | Third Party SI / Service Provider |  | 2018-08-26 | No Date | 2017-12-01 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4325 | 2. Change sanction/approved and in project delivery |  | Cisco Security Upgrade | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | T & SS | 2017-06-29 | Chris Fears | Emily Pickard |  |  | Third Party SI / Service Provider |  | 2018-08-26 | No Date | 2018-02-02 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4562 | 2. Change sanction/approved and in project delivery |  | Testing Lifecyle Improvements | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | T & SS | 2017-12-18 | Andy Simpson | Jon Follows |  |  | Third Party SI / Service Provider |  | 2018-12-31 | No Date | 2018-03-31 | Other | No Process | No Delivery Effort | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4440 | 2. Change sanction/approved and in project delivery |  | Npower MPRN Information report | CR (ASR) | LIVE | D1 - Change in delivery | 25.23% |  |  | Data Office | 2016-08-04 | Emma Partlett | Jo Duncan |  | UKLP IADBI246 | Xoserve Resource |  | 2018-11-30 | No Date | 2018-04-27 | BW | Other | 31-100days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
2831.2 | 3. Change delivered, awaiting closure approval/sign-off |  | DSP Gateway Mechanism Analysis & Design | CP | LIVE | F1 - CCR/Closedown document in progress | 25.23% |  |  | T & SS | 2012-11-21 | Joanna Ferguson | Jon Follows |  |  | Third Party SI / Service Provider |  | 2014-04-16 | 2014-04-16 | No Date | Other | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | All UK Gas Market Participants | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date
3151 | 3. Change delivered, awaiting closure approval/sign-off |  | Communications Link Solution for Provision of Smart Meter Data from iGT's to Xoserve | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 22.22% |  |  | T & SS | 2013-08-15 | Lee Chambers | Jon Follows |  |  | Third Party SI / Service Provider |  | 2014-09-01 | 2014-09-01 | 2014-04-30 | ISU | Other | 100+days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
2831.4 | 3. Change delivered, awaiting closure approval/sign-off |  | Smart Metering UNC MOD 430: DCC User Gateway Network | CP | LIVE | F1 - CCR/Closedown document in progress | 9.009% |  |  | T & SS | 2014-03-13 | Jo Ferguson | Jon Follows |  |  | Third Party SI / Service Provider |  | 2016-09-22 | 2017-09-22 | No Date | ISU | Other | 100+days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | TRUE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date
4635 | 2. Change sanction/approved and in project delivery |  | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service (Number) | CP (Non System Impacting) | LIVE | D1 - Change in delivery | 13.21% |  |  | T & SS | 2018-03-21 | Charlie Hayley | Charlie Haley |  |  | Xoserve Resource |  | 2018-09-01 | No Date | No Date | Other | Portal | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | FALSE | FALSE | FALSE | Two to Five | FALSE | High | FALSE | FALSE | No Date | 2018-06-13
4647 | 2. Change sanction/approved and in project delivery |  | IS Operations - Service Management Performance Birst Dashboards | CR (Internal) | LIVE | D1 - Change in delivery | 24.62% |  |  | Data Office | 2018-04-13 | Luke Moise | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-14 | No Date | 2018-05-15 | Birst | Other | 0-30 days | TRUE | Xoserve | Daily | One | Low | 2018-05-15 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4650 | 1. Start-Up (Progressing through change governance) |  | M-Number DVD Automation | CR (External Impacting) | LIVE | A5 - CP in capture with DSG | 33.63% |  |  | Data Office | 2018-04-17 | Mark Pollard | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-09-28 | No Date | 2018-05-31 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | TRUE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4656 | 2. Change sanction/approved and in project delivery |  | Customer Instant Feedback Mechanism for KVI Reporting | CR (Internal) | LIVE | D1 - Change in delivery | 27.03% |  |  | T & SS | 2018-04-24 | Adam Jones | Dene Williams |  |  | Third Party SI / Service Provider |  | 2018-09-01 | No Date | 2018-06-01 | Other | Other | 30-60 days | TRUE | Xoserve | Daily | Two to Five | Low | 2018-12-28 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4700 | 1. Start-Up (Progressing through change governance) |  | Provision of data to Suppliers via API | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 22.22% |  |  | Data Office | 2018-06-18 | Mark Pollard | Simon Harris |  |  | Xoserve Resource |  | No Date | No Date | 2018-09-28 | BW | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Group | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 23: Internal | TRUE | TRUE | FALSE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4710 | 2. Change sanction/approved and in project delivery |  | ASR – POW to be added to Eon Reports | CR (ASR) | LIVE | D1 - Change in delivery | 25.23% |  |  | Data Office | 2018-07-02 | Greg Causon | Charlie Haley |  |  | Xoserve Resource |  | 2018-08-24 | 2018-08-24 | 2018-08-07 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | FALSE | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4747 | 1. Start-Up (Progressing through change governance) |  | Npower Smart Meter Upgrade Notification Report (AS20180412) | CR (ASR) | LIVE | A9 - Internal change progressing through capture | 31.23% |  |  | Data Office | 2018-08-24 | Greg Causon | Charlie Haley |  |  | Xoserve Resource |  | No Date | No Date | 2018-11-01 | Other | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | FALSE | FALSE | FALSE | One | TRUE | Medium | FALSE | FALSE | No Date | No Date
4748 | 1. Start-Up (Progressing through change governance) |  | Birst Dashboard Development for Process Federation | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 22.22% |  |  | Data Office | 2018-08-28 | Susan Helders | Jo Duncan |  |  | Xoserve Resource |  | No Date | No Date | 2018-09-15 | Birst | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4552 | 1. Start-Up (Progressing through change governance) |  | ‘Front end’ development of new Company Intranet | CR (Internal) | LIVE | C1 - Delivery Business Case/BER in progress | 22.22% |  |  | T & SS | 2017-12-05 | Sarah Bridge | Emma Rose |  |  | Third Party SI / Service Provider |  | 2018-11-30 | No Date | 2017-06-30 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | TRUE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4625 | 3. Change delivered, awaiting closure approval/sign-off |  | Retrospective - Change of Supply API Prototype Development for British Gas | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 15.62% |  |  | Data Office | 2018-02-05 | Iain Snookes | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-08-30 | 2018-08-30 | 2018-12-31 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Participant | TRUE | FALSE | FALSE | FALSE | TRUE | Service Area 23: Internal | TRUE | TRUE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
4633 | 2. Change sanction/approved and in project delivery |  | New website for Xoserve | CR (Internal) | LIVE | D1 - Change in delivery | 19.82% |  |  | T & SS | 2018-03-19 | Sarah Bridge | Andrew Poolton |  |  | Third Party SI / Service Provider |  | 2019-01-31 | No Date | 2018-12-31 | Other | Other | 100+ days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | TRUE | FALSE | TRUE | Service Area 23: Internal | FALSE | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4695 | 2. Change sanction/approved and in project delivery |  | Investigating causes and contributors to levels and volatility of Unidentified Gas | CP (Non System Impacting) | LIVE | D1 - Change in delivery | 43.24% |  |  | Data Office | 2018-06-05 | Rachel Hinsley | Charlie Haley |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-07-31 | Other | Other | 100+ days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 3: Record/submit Data in Compliance with UNC | FALSE | FALSE | FALSE | One | TRUE | High | FALSE | FALSE | 2018-06-13 | 2018-06-13
4626.1 | 2. Change sanction/approved and in project delivery |  | Provision of an alternative Consumer Enquiry Service (MNumber) PHASE ONE Web Portal Implementation | CR (Internal) | LIVE | D1 - Change in delivery | 27.63% |  |  | Data Office | 2018-03-09 | Dave Acker | Charlie Haley |  |  | Third Party SI / Service Provider |  | 2018-09-01 | No Date | 2018-08-01 | Other | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | TRUE | FALSE | TRUE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | FALSE | FALSE | FALSE | Two to Five | FALSE | High | FALSE | FALSE | No Date | No Date
4626.2 | 1. Start-Up (Progressing through change governance) |  | Provision of an alternative Consumer Enquiry Service (Mnumber) - PHASE TWO Non-Web Portal Implementation | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 27.63% |  |  | T & SS | 2018-03-09 | Dave Ackers | Dene Williams |  |  | Third Party SI / Service Provider |  | 2019-07-31 | No Date | 2018-08-01 | Other | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | TRUE | FALSE | FALSE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | FALSE | FALSE | FALSE | Two to Five | FALSE | High | FALSE | FALSE | No Date | No Date
4626.3 | 1. Start-Up (Progressing through change governance) |  | Provision of an alternative Consumer Enquiry Service (MNumber) PHASE THREE Web Portal xEnhancements | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 9.009% |  |  | Data Office | 2018-08-13 | Dave Ackers | Charlie Haley |  |  | Third Party SI / Service Provider |  | No Date | No Date | No Date | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date