## Slide 1: Xoserve IX Refresh
Customer Update
30/10/2018

## Slide 2: IX Refresh Update
Welcome to the October update for the IX Refresh Project. As expected with a project of this nature we continue to engage and take advice from our security team to ensure we are keeping up with the current industry and wider security landscapes.
As a result we have decided that we are at the right stage before the rollout to undertake additional penetration testing to ensure the delivered solution adheres to industry best practice for security and data protection.
This testing will take priority over the Proof of Concept (PoC) and the pilot site which have been moved to January.
Taking the additional testing and the change freezes over December and early January into account, we expect the timelines for physical server and router installations to be impacted by up to eight weeks.
We will continue to provide regular communication throughout this period
If you require anything further please contact box.xoserve.IXEnquiries@xoserve.com
October Milestones Achieved
Phase One and Phase Two customer’s work packages raised with Gamma
Phase Three and Four customers details provided to Gamma (work packages in preparation)
30 sites have had phone lines installed
24 customers received appointments for phone line installations
31 customers contacted for outstanding site surveys. 19 are now remaining
Engagement with security experts regarding penetration testing

## Slide 3: IX Refresh Update
Three Month Timeline
November
Customers to be contacted for outstanding surveys
Penetration testers to be engaged to establish testing scope
Phone line installations to continue
December
Penetration testing to be completed
Phone line installations to continue
January
Proof of Concept (PoC) will be tested at our supplier’s data centre
Pilot - IX solution will then be installed at the pilot site
Phone line installations to continue
You will be contacted by Gamma before either your Network survey or phone line installation takes place (dependant on the complexity and IX option required).

## Slide 4
November
December
January
February
March
October
Proof of Concept
Pilot Site
Phase One
Network and Router Installation
Server Installation
Phase Two
Phase Three
Phase Four
Remaining Sites
(Where surveys are outstanding)
Penetration Testing
TBC
Timeline