## Slide 1: EUC Project Timelines
Key Upcoming Dates:
Design Change Packs, Extraordinary Issue Date – 21st December
  10 Day Review Period Completion (Excluding Bank Holidays) – 9th January
  5 Day Xoserve Response Period Completion – 16th January
  5 Day Notice of ChMC Materials – 17th January
Design Change Packs Approved – 24th January 2019 at Extraordinary ChMC
6 Month Notice of July 31st Implementation – 31st January
BER Approved – 9th January at ChMC

## Slide 2: EUC
29th October 2018 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Mobilisation: Mobilisation activities are underway to plan for the Design phase. Resources are being forecasted for the duration of the delivery, whilst a further detailed analysis/ impact assessment of the change is being undertaken, to help plan out the necessary Design activities Funding: As the high-level costs have been provided in the HLSOIAs, customers have been asked whether an EQR is necessary, and whether a BER, outlining the full delivery costs for EUC, would be sufficient. The BER will be provided to ChMC for approval by January 9th Design: Design preparation is underway. Design will begin w/c Nov 12th . Design Changes packs will be issued on the 21st of December A baselined plan for all subsequent lifecycle stages will be provided during the Design phase, and will be provided to the ChMC on December 12th |  |  | 
Risks and Issues | Currently tracking green from a risk perspective given that the project has only just mobilized. All risks will be regularly monitored throughout the project lifecycle |  |  | 
Cost | High-level, estimated, costs for the change was provided within the HLSOIAs. The BER is set to be approved by ChMC on January 9th |  |  | 
Resources | Weekly monitoring of SME resources ongoing |  |  |