## Slide 1: DSC Change Committee Summary – 10th October
7 New change proposals raised and approved
  XRN4747 – npower smart meter upgrade notification report – Approved
  XRN4769 – updates to Service description table – Approved
  XRN4770 – NDM Sample data – MOD0654 delivery - Approved
  XRN4772 – Composite weather variable (CWV improvements) – Approved
  XRN4777 – Contact details updates – Approved
  XRN4779 – UNC Modification 0657S – adding AQ reporting to the PARR schedule reporting suite – Approved
  XRN4780 – Inclusion of Meter Asset Provider identity (MAP ID) in the UK Link system (CSS Consequential change) - Approved
Solution/Delivery option approvals
  XRN4687 – PSR updates for large domestic sites – Approved for June 2019 release
  XRN4670 – Reject a replacement read where the read provided is identical to the already held in UK Link for the same date – Approved for June 2019 release
  XRN 4690 – Actual read following estimated transfer read calculating AQ of 1 – Approved for minor release (expected delivery by March 2019)
  XRN4691 – XRN4694 – CSEP IGT & GT file format change – Deferred to Nov 18 ChMC
  XRN4717 – Use of up to date forecast weather data in the first NDM nominations run – Approved for minor release (expected delivery by March 2019)

## Slide 2: DSC Change Committee Summary – 10th October
Release Updates:
  Release 2 (delivered June 2018)
    In process of close down activities with CCR expected at November 2018 ChMC
  Release 3 (due to be delivered 2nd November 2018)
    Delivery split into the 2 delivery tracks
      Track 1 – 13 changes
      Track 2 – Cadent Billing change
    1 change from track 1 (XRN4534 – amendment to RGMA validation rules) has encountered issues in regression testing and therefore will not be delivered with track 1 changes, amended implementation date to be confirmed in November 18 ChMC
  June 2019 release
    Scope for June 2019 release was approved
      There are only 3 changes in scope and therefore it was agreed that although the release will be delivered to the major release timeline market trials would not be required due to reduced scope

## Slide 3: DSC Change Committee Summary – 10th October
CSS consequential change update
XRN4695 UIG Taskforce update
Amendment invoice update
AOB items
  IX Update (same material shared in CoMC meeting)
  Implementation date for Modification 0654
  M number Portal