## Project Plan 2018-19
This Project Plan uses the convention that quarters are categorised using the calendar year. E.G. Q1 is Jan-Mar
|  |  |  | 2018 |  |  | 2019 | [11 empty] | 2020
| Status | Date | Date Complete | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January
Steering and Control
PAC member elections |  | Q3 2018
End of PAF year review |  | Q3 2018
End of year evaluation of the PAFA |  | Q2 2018
Performance Reports
Review Performance Reports and whether they are still fit for purpose, investigating what additional reporting elements are required |  | Dec 18 - Jan 19
Present changes to the PARR reports to the PAC for agreement |  | 2019-01-01
PARR report amendments presented to UNCC (if UNC mod 660 is approved) |  | Jan-Feb-19
Risk Register
PAC review and update |  | Q4 2018
Industry consultation |  | Q1 2019
Risk Model
Risk Model data update |  | Dec 2018 - Jan 2019
Report to PAC on suitability of model following data update |  | 2019-02-01
Finalisation of the risk model |  | 2019-03-01
Industry consultation on updated Risk Model |  | Q2 2019
PAC Development
Further define and develop incentive regime |  | Q3 2018 - Q2 2019
Assess other techniques for the PAF (Detective, Preventive, Remedy) |  | Q1 2019
Commence incentive/control mechanisms on a prioritisation basis |  | Q3 2018
UNC Mod Development
Mod 660s - Amendment to PARR permissions to allow PAC to update with UNCC approval |  | Q2 2018 - Q4 2018
Mod 0664 - Transfer of sites with Low Read Submission Performance from Class 2 and 3 into class 4 |  | Q3 2018 - Q2 2019
Mod 0672 - Incentivise Product Class 4 Read Performance |  | Q3 2018 - Q2 2019
Mod 0674 - Performance Assurance Techniques and Controls |  | Q4 2018 - Q2 2019