## Slide 1: Amendment Invoice Task Force Progress Report
7th November 2018

## Slide 2: Background
Amendment Invoice Issues – What’s the issue?
  A number of functional defects and integration issues are causing presentation issues and charge calculation issues within the AMS invoice, resulting in presentation issues where data is missing or incorrect within the supporting data and incorrect charge calculations which are excluded from the invoice until a fix is deployed.
  Delays in issuing the amendment invoice supporting information files and additional correction files required to enable customers to validate the charges issued
What is Xoserve doing about the issues?
  A taskforce consisting of business process and technical experts are working together to fix the issues
  Resources have been increased for both the technical team and the business. The team will focus on defect resolution, resolving exclusions and releasing reconciliation charges
  Defect and exclusion resolution plans have been produced and will be tracked, these will be published
  From October an update on progress will be provided to Contract Management Committee (CoMC) and Change Management Committee (ChMC) monthly

## Slide 3: Task Force Focus Areas (Workstreams)
There are 4 Primary Focus areas (Streams of work)
  Business as Usual (BAU)
    Maintaining the quality of the invoice, and improving the workaround process for issuing supporting AML and ASP files.
  Technical Design Review and Root Cause Analysis (RCA)
    Detailed technical review to identify any process improvements, and understand the root cause of functional defect
  Defect Resolution
    Managing the resolution of defects associated with the Amendment invoice and supporting files, including data correction and release of reconciliation charges (exclusions).
  Customer Engagement and support
    Provide regular updates to Customers
    Engage with Customers to understand the impact that the issue is having on each organisation and work together to find ways to provide additional support.

## Slide 4: Amendment Task Force: dashboard
Overall RAG status:*
R
*R = programme objectives at risk and no agreed plan to resolve; A = programme objectives at risk, with agreed plan in place to resolve; G = on track.
Executive Summary | RAG | 
The Amendment Invoice Taskforce is currently at Amber status due to the number of defects outstanding and the volume of exclusions. Issues also experienced with the July and August invoices. The resources of the team have increased, both technical and business, to resolve the defects and release the reconciliation charges currently excluded from the invoice. The scope of the taskforce includes 32 defects as at 1st September 2018 and all exclusions associated with the defects. Aim of the team is to resolve the defects by end of November 2018 and release reconciliation charges in the November invoice issued in December. Any defects identified after 1st September will continue to be prioritised and resolved as BAU. A full time Customer Liaison Manager has been assigned to ensure customers are actively updated with progress and involved with solution options. Reporting will be provided monthly at DSC committee meetings and published on Xoserbve.com. | RCA | R
 | Defects & Exclusion | G
 | BAU | A
Progress since last month - key milestones | Workstream | Date | Status
AML Scheduling Plan | RCA | 05/10/18 | Completed
POC for single AML/ASP file Plan | RCA | 05/10/18 29/10/18 | Completed
Deploy fixes for 6 defects (9 were planned) | Defect & Exclusions | 31/10/18 | Completed
UBID Phase 2 Deployment | RCA | 05/10/18 13/10/18 | Completed
Release charges for 3639 Excluded MPRNs (defects deployed) | Defect & Exclusions | 31/10/2018 | Completed
Priorities for next month – key milestones | Workstream | Date | Status
Exception Analysis (Procedure Update) | RCA | 05/10/19 10/11/18 | In progress
Exclusion Analysis (Procedure Update) | RCA | 28/09/18 10/11/18 | In progress
AML Scheduling Plan Approval | RCA | 20/11/18 | In progress
PoC for single AML/ASP File Approval to Proceed | RCA | 20/11/18 | In progress
Automation of Offline ASP Mismatch files | RCA | 12/10/18 23/11/18 | In progress
Deploy fixes for 13 defects | Defects & Exclusions | 30/11/18 | In progress
Release Charges for Excluded MPRNs c29k (for defects deployed) | Defect & Exclusions | 31/10/18 | In progress
Exception Analysis (Procedure Update) | RCA | 05/10/19 10/11/18 | In progress
Executive Summary | RAG | 
The Amendment Invoice Taskforce is currently at Red status due to the incorrect UIG charge issued for 3 consecutive months on the Amendment invoice (July, August & September). The scope of the taskforce includes 32 defects as at 1st September 2018 and all exclusions associated with the defects. Aim of the team is to resolve the defects by end of November 2018 and release reconciliation charges in the November invoice issued in December. Any defects identified after 1st September will continue to be prioritised and resolved as BAU. Defect resolution progressing well. UBID phase 2 implemented on target and initial assessment is a significant decrease in mismatches on the invoice.. The number of reductions will be provided following analysis, due end of November 2018. | RCA | A
 | Defects & Exclusion | A
 | BAU | A

## Slide 5: Amendment Invoice – Resolution Plan
Sep
Oct
Nov
Dec
Jan
Feb
2018
2019
Defects
Eliminate Backlog (32 @ 1/9)
BAU @ M+1
Exclusions
Eliminate Backlog to 31/10
BAU @ M+1
Offline Automation
ASP Correction file
Design & RCA
UBID P1
P2
Benefits Delivery
Mismatch reduction will be measured & reported, visible for Sept Invoice Cycle
Accelerated Offline file production + backlog reduction
1
1
2
2
3
3
Mismatch & Exclusion reduction, will be measured & reported
4
4
All new defects fixed by end of following month (M+1)
Solution Work Packages
5
5
Number of system, scheduling and procedure changes – delivering final set of mismatch fixes

## Slide 6
  Task Force Workstream Updates

## Slide 7: BAU Stream Update
Area | Action | Progress
ASP Mismatch Files | Reduce the delay issuing mismatch files Remove manual error within the files | Backlog of files is reducing slowly. Due to an increase in class 3 activity, the size of the ASP file has increased for some customers. This has created additional work to process the data and resulted in delays issuing the mismatch files From October (September billing period), the aim was for the ASP correction files to be issued prior to invoice payment due date (with the exception of some customers who receive larger files, these customers should be contacted directly). The implementation of the automated solution has been delayed so this deadline will be affected. Planned for 23rd November 2018.
July, August & September Amendment Invoice contained incorrect Unidentified Gas Reconciliation charge | Identify reason for the error Implement process improvement | The UIG share on the August and September Amendment Invoice are incorrect due to the wrong UIG weighting factors being applied to two End User Category (EUC) bands. The incorrect factors were also used for the UIG charge adjustment on the July invoice. The End User Category (EUC) bands affected are: EUC 02 and EUC 07 - all meter points in these EUC bands have been allocated UIG incorrectly following reconciliation. However, the energy for all EUC bands will require reapportionment to correct the energy position. An adjustment to correct positions will be issued to customers by 26th November 2018.

## Slide 8: RCA Stream Actions
Activity | Target Completion Date | Benefits | Target Status
Package 3A: Additional Analysis: Tools and Class 3 | 02/11/2018 | Additional analysis required before benefits are understood. Areas were identified during RCA work as potential reasons for mismatches | Completed
Package 3B: Additional Analysis: DM Rec Interface | 08/02/2019 |  | On target
Package 3C: Additional Analysis: AML Extraction Process | 11/01/2019 |  | On target
Package 4A: Exception Analysis: Procedure Update | 05/10/2018 30/11/2018 | Process improvements to ensure speedier closure of exceptions to release charges on the invoice and reduce mismatches | On target
Package 4B: Exclusion Analysis: Procedure Update | 28/09/2018 16/11/2018 |  | On target
Package 5A: Service Improvement CRs: Automation and Reporting | 28/12/2018 | Automated reporting internally to enable validation & invoice analysis prior to issue | On target
Package 5B: Service Improvement CRs: Automation and Reporting | 18/01/2019 |  | On target
Package 6: Code Review | 22/02/2019 | Identify any further improvements areas to reduce mismatches | On target
Package 7: AML Scheduling Plan *Previous date given was for production of the plans to deliver the activity (Phase 1) Phase 2 is the actual plan to deliver AML files | 05/10/18 31/12/18* | Delivery of file before payment due date | Complete On target
Package 8: Single AML/ASP file *Previous date given was for POC and delivery of the supporting plans to deliver activity (Phase 1) | 05/10/18 30/11/18* | Merge of files | Complete On target
SAP Automation of Offline ASP Mismatch files | 12/10/2018 23/11/2018 | Earlier delivery of files | On target
UBID Phase 1 | 25/08/2018 | Reduction in mismatches | Complete
UBID Phase 2 | 13/10/2018 |  | Complete

## Slide 9: Defect and Exclusions Resolution Plan
Defect Resolution Plan as at 6th November 2018
Exclusion Resolution Plan as at 30th October 2018
These documents will be updated, tracked and published weekly on Xoserve.com