## Slide 1: DSC Change Committee Summary – 7th November
8 New change proposals raised and approved
  XRN4785 – Single Sided Nomination Error Proofing (interim solution) – Approved
  XRN4786 – DSC Provision of Gemini Data to Ofgem – Approved
  XRN4795 – Amendments to PARR Scheduling (MOD520a) - Approved
  XRN4787 – Rescheduling of Single Sided Nomination (enduring solution) – Approved
  XRN4789 – Updating Shipper Reporting Packs – Approved
  XRN4790 – Introduction of winter read consumption reports & associated obligation (MOD0642) – Approved
  XRN4800 – TSO visibility of Systems balance at Interconnection Points – Approved
  XRN4801 – Additional information to be made visible in DES – Approved
1 New change proposal post initial review
  XRN4747 – Smart Meter upgrade notification report - Approved
8 Solution/Delivery option approvals
  XRN4653 – National Grid Transmission iConversion Project - Deferred
  XRN4706 – Test Support consultancy on connectivity between Xoserve and gemini – Approved into delivery
  XRN4691-94 – CSEPS IGT and GT file formats - Deferred
  XRN4725 – New read reason type for LIS estimate readings - Deferred
  XRN4770 – NDM Sample Data – Approved for inclusion in February 2019 major release

## Slide 2: DSC Change Committee Summary – 7th November
Release Updates:
  Release 2 (delivered June 2018)
    In process of close down activities
    CCR approval deferred to December 2018
  Release 3 (due to be delivered 2nd November 2018)
    Delivery split into the 2 delivery tracks
      Track 1 – 13 changes originally 12 +1 were successfully implemented on the 2nd November (plus 1 XRN4658 read validation increasing outer tolerance)
      Track 2 – Cadent Billing change on plan - Green
    1 change from track 1 (XRN4534 – amendment to RGMA validation rules) was not delivered as part of track 1, was removed from track 1 deliver following issues that arose during regression testing, due to delivered with track 2.
  June 2019 release
    Scope for June 2019 release was approved in October
      Plan for delivery on track – Green
  November 2019 release
    1 change removed from potential scope
    4 CSEP IGT/GT file format change may also be deferred from this release

## Slide 3: DSC Change Committee Summary – 7th November
Release Updates cont’d:
Updates/timelines were provided for other ‘minor’ / adhoc releases:
  Feb 2019 minor release – due to deliver 15th Feb 2019
    Includes 2 change proposals
      XRN4690 – Actual read following estimated transfer read calculating AQ1
      XRN4717 – use of the up to date forecast weather data in first NDM nomination run
  September 2019 adhoc release – due to deliver for 1st October
    Includes 2 change proposals
      XRN4665 – Creation of new end user categories
      XRN4376 – GB Charging (MOD0621)
  Change assurance update was also provided by Jane Rocky

## Slide 4: DSC Change Committee Summary – 7th November
CSS consequential change update
XRN4695 UIG Taskforce update
Amendment invoice update
Finance and Budget update
AOB items
  IX Update (same material shared in CoMC meeting)
  KVI Change Management Survey feedback
    https://www.gasgovernance.co.uk/sites/default/files/ggf/2018-11/15.2%20Xoserve%20KVI%20-%20Change%20Management%20Survey%20August%202018%20v3%20%282%29.pdf