## CMC_Summary
Totals by Budget Area (£,000's) | [10 empty] | Current Year Value of Work Done Split By Customer Class
|  |  | Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | RAG Status
Summary (by Budget Area) | Expenditure Type | Approved Budget Value 18/19 | Total Approved Value | Estimated Cost at Completion | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Current Year Total vs Budget | Estimated Cost at Completion vs. Total Approved Value | Transmission Network Operator | Distribution Network Operator | DNs & IGTs | IGT's | Shippers
DSC Change Budget | External | 2206.68 | 2829.2291 | 1739.5522 | 508.504 | 1137.3446 | 102.7886 | 0 | G | G | 589.9635 | 126.4739 | 56.176 | 0 | 364.7313
| Internal |  |  | 395.017 | 119.055 | 248.703 | 27.259 | 0 | NA | NA | 167.18 | 10.4145 | 4.901 | 0 | 66.2075
| Total |  |  | 2175.0442 | 668.034 | 1386.0476 | 130.0476 | 0 | NA | NA | 757.1435 | 136.8884 | 61.0769 | 0 | 430.9388
Note that project expenditure & budget values shown do not include margin | [8 empty] | Green - At or below target
Internal costs are not deducted from budget (unless otherwise notified) | [8 empty] | Red - Above target
Details of Changes
| Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year
Project Line Level Changes | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Current Year Value of Work Done | Change in Current Year Value of Work Remaining | Change in Future Financial Years Value of Work Remaining
4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - External [O] | 0 | 0 | 0 | 0 | 0 | 0
4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - Internal [O] | 0 | 0 | 0 | 0 | 0 | 0
This section summarises any value change between this report and the previous report. Positive values indicate an increase since the last report, negative indicates a decrease.

## CMC_Current
Values in £0,000s | [5 empty] | Values pertaining to the Total Cost of the Project |  |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | Percentage to Customer Class |  |  |  |  | Current Year Actual Cost by Customer Class (£0,000's) | [8 empty] | Comparison Formulae |  | 6 | 8 | 9 | 11 | 12 | 13 | 14 | 25
Budget Pot Reference | Project Ref No | Project Title | Senior Project Manager | High Level Process Stage | Expenditure Type | Total Approved Value | Estimated Cost at Completion | RAG | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | CCR Status | Comments | SORT FIELD 1 | SORT FIELD 2 | Matcher | Project Line | High Level Process Stage | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Value of Work Done (Current Year) | Change in Value of Work Remaininng (Current Year) | Change in Value of Work Remaining (Future Financial Years) | CCN Status | Any Value Change? | This Year Spend Change? | Master Change Flag | (Negative means old value is lower) | Cell Colour Code
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Closedown | External [O] | 1449.1201 | 810.0437 | 639.0764 | 468.029 | 351.0997 | 0 | 0 | 47% | 3% | 34% | 16% | 0% | 165.0169 | 10.533 | 119.3739 | 56.176 | 0 |  |  | F | 89 | 4361External [O] | 4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - External [O] | SAME | 0 | 0 | 0 | -150.8 | 150.8 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Closedown | Internal [O] | 368.9906 | 149.686 |  | 119.055 | 30.631 | 0 | 0 | 47% | 3% | 34% | 16% | 0% | 14.3966 | 0.91893 | 10.4145 | 4.901 | 0 |  |  | F | 90 | 4361Internal [O] | 4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - Internal [O] | SAME | 0 | 0 | 0 | 0.6 | -0.6 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Closedown | Total [O] | 1818.1107 | 959.7297 |  | 587.084 | 381.7307 | 0 | 0 | 47% | 3% | 34% | 16% | 0% | 179.4134 | 11.4519 | 129.7884 | 61.0769 | 0 |  |  | F | 91 | 4361Total [O] | 4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - Total [O] | SAME | 0 | 0 | 0 | -150.2 | 150.2 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4635 | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service | P. Duvvuri | Delivery | External | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 134 | 4635External | 4635 Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4635 | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service | P. Duvvuri | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 135 | 4635Internal | 4635 Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4635 | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service | P. Duvvuri | Delivery | Total | 0 | 40.475 |  | 40.475 | 0 | 0 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 136 | 4635Total | 4635 Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | External [O] | 903.259 | 903.2585 | 0.0005 | 40.475 | 759.9949 | 102.7886 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 180.5644 | 579.4305 | 0 | 0 | 0 |  |  | D | 137 | 4572External [O] | 4572 UKL Nov '18 Release [R3] (DSC CB) - External [O] | SAME | 0 | 0 | 0 | 205.6 | -205.6 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | Internal [O] | 0 | 245.331 |  | 0 | 218.072 | 27.259 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 51.8109 | 166.2611 | 0 | 0 | 0 |  |  | D | 138 | 4572Internal [O] | 4572 UKL Nov '18 Release [R3] (DSC CB) - Internal [O] | SAME | 0 | 0 | 0 | 54.5 | -54.5 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | Total [O] | 903.259 | 1148.5895 |  | 40.475 | 978.0669 | 130.0476 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 232.3753 | 745.6915 | 0 | 0 | 0 |  |  | D | 139 | 4572Total [O] | 4572 UKL Nov '18 Release [R3] (DSC CB) - Total [O] | SAME | 0 | 0 | 0 | 260.1 | -260.1 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4665 | EUC | L. Chambers | Closed | External | 450 | 0 | 450 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | Z | 149 | 4665External | 4665 EUC - External | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 1
B.BP18-020.1 | 4665 | EUC | L. Chambers | Closed | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | Z | 150 | 4665Internal | 4665 EUC - Internal | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 1
B.BP18-020.1 | 4665 | EUC | L. Chambers | Closed | Total | 450 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | Z | 151 | 4665Total | 4665 EUC - Total | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 2
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | External | 1.5 | 1.4 | 0.1 | 0 | 1.4 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 1.4 | 0 | 0 | 0 | 0 |  |  | D | 274 | 4542External | 4542 Changes to Shipper Portfolio Report - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 275 | 4542Internal | 4542 Changes to Shipper Portfolio Report - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | Total | 1.5 | 1.4 |  | 0 | 1.4 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 1.4 | 0 | 0 | 0 | 0 |  |  | D | 276 | 4542Total | 4542 Changes to Shipper Portfolio Report - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | External | 8.75 | 8.75 | 0 | 0 | 8.75 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 8.75 | 0 | 0 | 0 | 0 |  |  | D | 277 | 4525External | 4525 Transparency of AQ Process - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 278 | 4525Internal | 4525 Transparency of AQ Process - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | Total | 8.75 | 8.75 |  | 0 | 8.75 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 8.75 | 0 | 0 | 0 | 0 |  |  | D | 279 | 4525Total | 4525 Transparency of AQ Process - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Closedown | External | 9.5 | 9 | 0.5 | 0 | 9 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 9 | 0 | 0 | 0 | 0 |  |  | F | 280 | 4328External | 4328 iGT Elected Shipper Sites Report - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Closedown | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | F | 281 | 4328Internal | 4328 iGT Elected Shipper Sites Report - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Closedown | Total | 9.5 | 9 |  | 0 | 9 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 9 | 0 | 0 | 0 | 0 |  |  | F | 282 | 4328Total | 4328 iGT Elected Shipper Sites Report - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Closedown | External | 7.1 | 7.1 | 0 | 0 | 7.1 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 7.1 | 0 | 0 |  |  | F | 283 | 4354External | 4354 Nested CSEP Report for DNs - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Closedown | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | F | 284 | 4354Internal | 4354 Nested CSEP Report for DNs - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Closedown | Total | 7.1 | 7.1 |  | 0 | 7.1 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 7.1 | 0 | 0 |  |  | F | 285 | 4354Total | 4354 Nested CSEP Report for DNs - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
Note on AM2: Max Pemberton: Checks whether the value for this years spend has actually changed, or just moved from forecast to actual