## Slide 1: XRN4665 – EUC Release
04/12/18 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Design: Design workshops are currently in progress; and the plan is tracking to schedule to submit the Change Packs by the 21st of December Plan: Planning for Build & Test phases is in progress Funding: As agreed at the previous ChMC meeting, an EQR will not be provided for the EUC CP. The Project team are on-track to provide the BER to seek ChMC approval at the 09th January 19 meeting |  |  | 
Risks and Issues | Environment and Resource Constraints – There is a risk that due to multiple deliveries running in parallel (June 19, GB Charging, CSSC and EUC) that environment and resource constraints may become an issue from the Build phase onwards |  |  | 
Cost | The BER is on track to be issued to seek approval by ChMC at the 09th January 19 meeting |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 2: XRN 4665 - EUC Release Timelines
Key Milestone Dates:
Design Change Packs, Extraordinary Issue Date – 21st December 18
  10 Day Review Period Completion (Excluding Bank Holidays) – 09th January 19
  5 Day Xoserve Response Period Completion – 16th January 19
  5 Day Notice of ChMC Materials – 17th January 19
Design Change Packs Approved – Plan at 24th January 2019 Extraordinary ChMC
6 Month Notice of proposed 31st July Part A Implementation – 31st January 19
Seeking BER Approval at the 09th January 19 ChMC meeting

## Slide 3: XRN4732 - June 19 Release - Status Update
29th October 2018 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Detailed Design: Change Packs were distributed on the 23rd November as per the agreed plan date (XRNs: 4670, 4676 and 4687). The remaining design activities are tracking to plan to conclude Plan: Planning for Build start and testing (test approach/scenarios etc), at the end of Detailed Design the proposed June 19 implementation date will seek approval by the ChMC Funding: The Project team are on-track to provide the BER to seek ChMC approval at the 09th January 19 meeting |  |  | 
Risks and Issues | Environment and Resource Capacity – There is a risk that due to multiple deliveries running in parallel (June 19, GB Charging, CSSC and EUC) that environment and resource constraints may become an issue from the Build phase onwards |  |  | 
Cost | High-level, estimated, costs for each change were provided within the HLSOIAs. The BER is on track to seek approval by the ChMC at the 09th January 19 meeting |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 4: XRN4732 - June 19 Release Timelines
Key Milestone Dates:
Design Change Packs, Extraordinary Issued – 23rd November 18
  10 Day Review Period Completion – 07th December 18
  5 Day Xoserve Response Period Completion – 14th December 18
  5 Day Notice of ChMC Materials – 04th January 19
Design Change Packs Approved – 09th January 19
6 Month Notice of June 28th Implementation – 09th January 19
Seeking BER Approved at the 09th January 19 ChMC
09/01: Seek BER Approval at ChMC