## IP - In Analysis
UK Link Modification Implementation Plan - In Analysis
Functional Changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | AML Schedule Proposal | 1839.1 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 14/02/2018 - rejected | Rejected at ChMC on 14th February. Xoserve to produce additional information - Cost vs benefit for further discussion. Further industry discussions to be held for both defects and requirements.
NA | NA | Change Pack Publication | 2008.2 | 2018-07-13 | 2018-07-27 | 2018-08-03 | X | X | X | X | X | NA | Still undertaking discussions at DSG. We are looking at several distibution mechanisms and will test how the Change Pack process would work for each one. 30/10/2018 - The intention will be to include this within the scope of the new Xoserve website design plans.

## IP - For Approval - Design
UK Link Modification Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
3667a | N/A | XRN3667a Provision of Prospective Formula Year AQ/SOQ and Historic RAQ to Proposing Users (Design Approval) | 2140.6 - RJ - ES | 2018-11-09 | 2018-11-23 | 2018-11-30 | X |  |  |  |  | 2164 - RJ - ES | N/A | 01/02/2018 End of December 2018 | This is a Design Change Pack; this Change Pack received two responses, which were in support of the Design Specification.
4770 | 0654 | NDM Sample Data – Modification 0654 Delivery (Design Approval) | 2140.9 - RJ - ES | 2018-11-09 | 2018-11-23 | 2018-11-30 | X |  |  |  |  | 2164 - RJ - ES | N/A | 2019-03-01 | This is a Design Change Pack; this Change Pack received four responses, which were in support of the Design Specification.
4687 | N/A | PSR Updates for Large Domestic Sites | 2160.1 - SH - ES | 2018-11-27 | 2018-12-11 | TBC | X |  |  |  |  | 2174 - RJ - ES | N/A | 2018-06-28 | This is a Design Change Pack associated with the June 2019 Release.
4670 | N/A | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | 2157.2 - RJ - ES | 2018-11-23 | 2018-12-07 | TBC | X |  |  |  |  | 2171 - RJ - ES | N/A | 2018-06-28 | This is a Design Change Pack associated with the June 2019 Release.
4676 | N/A | Reconciliation issues with reads recorded between D-1 to D-5 | 2157.3 - RJ - ES | 2018-11-23 | 2018-12-07 | TBC | X |  |  |  |  | 2171 - RJ - ES | N/A | 2018-06-28 | This is a Design Change Pack associated with the June 2019 Release.
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
N/A | N/A | Release Implementation Dates | 2140.4 - RJ - ES | 2018-11-09 | 2018-11-23 | 2018-11-30 | X | X | X | X | X | 2164 - RJ - ES | 2018-12-12 | 2018-12-13 | We propose the November 2019 date is revised from 1st November 2019 to 8th November 2018 as the originally agreed November 2019 Release Date, approved in September 2018, does not follow the standard convention for UK Link Releases. Two responses were received, which supported this change.
N/A | N/A | Minor Changes to the UK Link Manual to reflect receipt of Service Desk contacts via Web portal | 2140.8 - RJ - ES | 2018-11-09 | 2018-11-23 | 2018-11-30 | X | X | X | X |  | 2164 - RJ - ES | 2018-12-12 | February 2019 Documentation Only Release | To support UK Link Users they may raise a Service Contact through a portal application as detailed in XCE1773 - New Portal for Submitting Service Desk Requests. The portal can be accessed here. The new portal is also accessible via the Quick Links on our website’s homepage and under the Contact Us section. We are proposing this change to support the amendment of UK Link Manual documents that refer to raising Service Contacts. We received two responses in support

## IP - Approved Last Meeting
UK Link Modification Implementation Plan - Approved on 23rd July
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | Description Change to the C41 for Clarification | 2102.1 - RJ - ES | 2018-10-12 | 2018-10-26 | 2018-10-29 | X |  |  |  |  | 2123 - RJ - PO | 2018-11-07 | Release 3 - 2nd November 2018 | We received one representation which approved this change in principle. This is an administative change, and Xoserve will ask ChMC to approve this change to be implemented as part of Release 3.

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description