## CMC_Summary
Totals by Budget Area (£,000's) | [10 empty] | Current Year Value of Work Done Split By Customer Class
|  |  | Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | RAG Status
Summary (by Budget Area) | Expenditure Type | Approved Budget Value 18/19 | Total Approved Value | Estimated Cost at Completion | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Current Year Total vs Budget | Estimated Cost at Completion vs. Total Approved Value | Transmission Network Operator | Distribution Network Operator | DNs & IGTs | IGT's | Shippers
DSC Change Budget | External | 1844 | 2897.8891 | 2089.5522 | 508.504 | 1296.171 | 81.3836 | 212.5786 | G | G | 668.3309 | 126.4739 | 56.176 | 0 | 445.1902
| Internal |  |  | 614.181 | 119.055 | 316.8757 | 41.5769 | 0 | NA | NA | 187.9626 | 10.4145 | 4.901 | 0 | 113.5975
| Total |  |  | 2744.2082 | 668.034 | 1613.0466 | 122.9605 | 349.2521 | NA | NA | 856.2936 | 136.8884 | 61.0769 | 0 | 558.7877
Note that project expenditure & budget values shown do not include margin | [8 empty] | Green - At or below target
Internal costs are not deducted from budget (unless otherwise notified) | [8 empty] | Red - Above target | [7 empty] | PIE VALUES |  | Sum 020.1 | 1850.2918
[17 empty] | Budget | 1850.3
[17 empty] | Budget Remaining | 0.0082357 | Tot DSC | 1850.2918
Details of Changes | [16 empty] | Potential Additional Spend | 472.7372 | Sums Estimated Cost Current Year IF: Budget is DSC Change Budget & Cost Type is External
| Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year | [13 empty] | VOWR for Approved Projects | 81.3836
Project Line Level Changes | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Current Year Value of Work Done | Change in Current Year Value of Work Remaining | Change in Future Financial Years Value of Work Remaining | [10 empty] | VOWD Transmission | 668.3309
[17 empty] | VOWD DNs | 126.4739
[17 empty] | VOWD Shippers | 445.1902
This section summarises any value change between this report and the previous report. Positive values indicate an increase since the last report, negative indicates a decrease. | [16 empty] | VOWD DNs & IGTs | 56.176
[16 empty] | LABEL > | VOWD iGTs | 0
Total VOWD £1296.2

## CMC_Current
Values in £0,000s | [5 empty] | Values pertaining to the Total Cost of the Project |  |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | Percentage to Customer Class |  |  |  |  | Current Year Actual Cost by Customer Class (£0,000's) | [8 empty] | Comparison Formulae |  | 6 | 8 | 9 | 11 | 12 | 13 | 14 | 25
Budget Pot Reference | Project Ref No | Project Title | Senior Project Manager | High Level Process Stage | Expenditure Type | Total Approved Value | Estimated Cost at Completion | RAG | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | CCR Status | Comments | SORT FIELD 1 | SORT FIELD 2 | Matcher | Project Line | High Level Process Stage | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Value of Work Done (Current Year) | Change in Value of Work Remaininng (Current Year) | Change in Value of Work Remaining (Future Financial Years) | CCN Status | Any Value Change? | This Year Spend Change? | Master Change Flag | (Negative means old value is lower) | Cell Colour Code
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Closedown | External [O] | 1449.1201 | 810.0437 | 639.0764 | 468.029 | 351.0997 | 0 | 0 | 47% | 3% | 34% | 16% | 0% | 165.0169 | 10.533 | 119.3739 | 56.176 | 0 |  |  | F | 89 | 4361External [O] | 4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - External [O] | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Closedown | Internal [O] | 368.9906 | 149.686 |  | 119.055 | 30.631 | 0 | 0 | 47% | 3% | 34% | 16% | 0% | 14.3966 | 0.91893 | 10.4145 | 4.901 | 0 |  |  | F | 90 | 4361Internal [O] | 4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - Internal [O] | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Closedown | Total [O] | 1818.1107 | 959.7297 |  | 587.084 | 381.7307 | 0 | 0 | 47% | 3% | 34% | 16% | 0% | 179.4134 | 11.4519 | 129.7884 | 61.0769 | 0 |  |  | F | 91 | 4361Total [O] | 4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - Total [O] | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4635 | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service | P. Duvvuri | Delivery | External | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 134 | 4635External | 4635 Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4635 | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service | P. Duvvuri | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 135 | 4635Internal | 4635 Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4635 | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service | P. Duvvuri | Delivery | Total | 0 | 40.475 |  | 40.475 | 0 | 0 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 136 | 4635Total | 4635 Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | External [C] | 903.259 | 903.2585 | 0.0005 | 40.475 | 862.7835 | 0 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 204.9856 | 657.7979 | 0 | 0 | 0 |  |  | D | 137 | 4572External [C] | 4572 UKL Nov '18 Release [R3] (DSC CB) - External [C] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | Internal [C] | 0 | 245.331 |  | 0 | 245.331 | 0 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 58.2873 | 187.0437 | 0 | 0 | 0 |  |  | D | 138 | 4572Internal [C] | 4572 UKL Nov '18 Release [R3] (DSC CB) - Internal [C] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | Total [O] | 903.259 | 1148.5895 |  | 40.475 | 1108.1145 | 0 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 263.2729 | 844.8416 | 0 | 0 | 0 |  |  | D | 139 | 4572Total [O] | 4572 UKL Nov '18 Release [R3] (DSC CB) - Total [O] | SAME | 0 | 0 | 0 | 130 | -130 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4665 | EUC | L. Chambers | Closed | External | 460.374 | 350 | 110.374 | 0 | 56.0377 | 81.3836 | 212.5786 | 100% | 0% | 0% | 0% | 0% | 56.0377 | 0 | 0 | 0 | 0 |  |  | Z | 151 | 4665External | 4665 EUC - External | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 1
B.BP18-020.1 | 4665 | EUC | L. Chambers | Closed | Internal | 229.293 | 219.164 |  | 0 | 40.9137 | 41.5769 | 136.6734 | 100% | 0% | 0% | 0% | 0% | 40.9137 | 0 | 0 | 0 | 0 |  |  | Z | 152 | 4665Internal | 4665 EUC - Internal | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 1
B.BP18-020.1 | 4665 | EUC | L. Chambers | Closed | Total | 689.667 | 569.164 |  | 0 | 96.9514 | 122.9605 | 349.2521 | 100% | 0% | 0% | 0% | 0% | 96.9514 | 0 | 0 | 0 | 0 |  |  | Z | 153 | 4665Total | 4665 EUC - Total | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 2
B.BP18-020.1 | 4732 | UKL - June 19 Release | L. Chambers | Live | External [C] | 58.286 | 0 | 58.286 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | N/A | 154 | 4732External [C] | 4732 UKL - June 19 Release - External [C] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4732 | UKL - June 19 Release | L. Chambers | N/A | Internal [C] | 39.9318 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | N/A | 155 | 4732Internal [C] | 4732 UKL - June 19 Release - Internal [C] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4732 | UKL - June 19 Release | L. Chambers | N/A | Total [C] | 98.2178 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | N/A | 156 | 4732Total [C] | 4732 UKL - June 19 Release - Total [C] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | External | 1.5 | 1.4 | 0.1 | 0 | 1.4 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 1.4 | 0 | 0 | 0 | 0 |  |  | D | 282 | 4542External | 4542 Changes to Shipper Portfolio Report - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 283 | 4542Internal | 4542 Changes to Shipper Portfolio Report - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | Total | 1.5 | 1.4 |  | 0 | 1.4 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 1.4 | 0 | 0 | 0 | 0 |  |  | D | 284 | 4542Total | 4542 Changes to Shipper Portfolio Report - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | External | 8.75 | 8.75 | 0 | 0 | 8.75 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 8.75 | 0 | 0 | 0 | 0 |  |  | D | 285 | 4525External | 4525 Transparency of AQ Process - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 286 | 4525Internal | 4525 Transparency of AQ Process - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | Total | 8.75 | 8.75 |  | 0 | 8.75 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 8.75 | 0 | 0 | 0 | 0 |  |  | D | 287 | 4525Total | 4525 Transparency of AQ Process - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Closedown | External | 9.5 | 9 | 0.5 | 0 | 9 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 9 | 0 | 0 | 0 | 0 |  |  | F | 288 | 4328External | 4328 iGT Elected Shipper Sites Report - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Closedown | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | F | 289 | 4328Internal | 4328 iGT Elected Shipper Sites Report - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Closedown | Total | 9.5 | 9 |  | 0 | 9 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 9 | 0 | 0 | 0 | 0 |  |  | F | 290 | 4328Total | 4328 iGT Elected Shipper Sites Report - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Closedown | External | 7.1 | 7.1 | 0 | 0 | 7.1 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 7.1 | 0 | 0 |  |  | F | 291 | 4354External | 4354 Nested CSEP Report for DNs - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Closedown | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | F | 292 | 4354Internal | 4354 Nested CSEP Report for DNs - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Closedown | Total | 7.1 | 7.1 |  | 0 | 7.1 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 7.1 | 0 | 0 |  |  | F | 293 | 4354Total | 4354 Nested CSEP Report for DNs - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
Note on AM2: Max Pemberton: Checks whether the value for this years spend has actually changed, or just moved from forecast to actual