## Slide 1: Xoserve IX Refresh
Customer Update
03/01/2019

## Slide 2: IX Refresh Update
Welcome to the December update for the IX Refresh Project.
Throughout December, we have been working with our Information Security team to complete penetration testing ahead of the Proof of Concept (PoC) scheduled for early January. The initial testing has been completed, meaning the PoC may continue. Final tests will take place in parallel to the PoC ready for migration of the Pilot site in late January.
December Milestones Achieved
Phase One, Two and Three customer’s phone lines continued to be installed
Phase Four customers work packages continued to be progressed via Gamma
77 sites have had phone lines installed
20 customers received appointments for phone line installations
16 customers contacted for outstanding site surveys. 11 are now remaining
Customers with DR equipment engaged about testing approach
Customers contacted about additional IP range / addresses for IX End User equipment

## Slide 3: IX Refresh Update
Three Month Timeline
January
PoC to be tested at out supplier’s data centre
IX solution will be installed at the pilot site
Phone line installations to continue
Continue to engage customers with DR equipment about testing approach
Continue to engage relevant customers requesting additional IP range / addresses for IX End User equipment
February
Post successful PoC testing and Pilot site migration, the rollout will begin
Phase One sites contacted to have routers and servers installed
Prepare March migrations
Phone line installations to continue
March
Rollout continues
Phase Two sites contacted to have routers and servers installed
Prepare April migrations
Phone line installations to continue
You will be contacted by Gamma before either your Network survey or phone line installation takes place (dependant on the complexity and IX option required).
If you have any queries, a Q&A document has been prepared for our IX customers which can be found on the IX Refresh page on the Xoserve website here.

## Slide 4
December
January
February
March
April
May
Proof of Concept
Pilot Site
Phase One
Network and Router Installation
Server Installation
Phase Two
Phase Three
Phase Four
Remaining Sites
(Where surveys are outstanding)
Penetration Testing
TBC
Timeline