## Slide 1
Amendment Invoice Task Force Progress Report
Contract Managers Meeting
16th January 2019

## Slide 2: Background
Amendment Invoice Issues – What’s the issue?
  A number of functional defects and integration issues are causing presentation issues and charge calculation issues within the AMS invoice, resulting in presentation issues where data is missing or incorrect within the supporting data and incorrect charge calculations which are excluded from the invoice until a fix is deployed.
  Delays in issuing the amendment invoice supporting information files and additional correction files required to enable customers to validate the charges issued
What is Xoserve doing about the issues?
  A taskforce consisting of business process and technical experts are working together to fix the issues.
  Resources have been increased for both the technical team and the business. The team will focus on defect resolution, resolving exclusions and releasing reconciliation charges
  Defect and exclusion resolution plans have been produced and will be tracked, these will be published
  Since October an update on progress will be provided to Contract Management Committee (CoMC) and Change Management Committee (ChMC) monthly

## Slide 3: Task Force Focus Areas (Workstreams)
There are 4 Primary Focus areas (Streams of work)
  Business as Usual (BAU)
    Maintaining the quality of the invoice, and improving the workaround process for issuing supporting AML and ASP files.
  Technical Design Review and Root Cause Analysis (RCA)
    Detailed technical review to identify any process improvements, and understand the root cause of functional defect
  Defect Resolution
    Managing the resolution of defects associated with the Amendment invoice and supporting files, including data correction and release of reconciliation charges (exclusions).
  Customer Engagement and support
    Provide regular updates to Customers
    Engage with Customers to understand the impact that the issue is having on each organisation and work together to find ways to provide additional support.

## Slide 4: Amendment Task Force: dashboard
Overall RAG status:*
A
*R = programme objectives at risk and no agreed plan to resolve; A = programme objectives at risk, with agreed plan in place to resolve; G = on track.
Executive Summary | RAG | 
Of the original 32 defects in scope for the taskforce we now have 6 remaining , these are planned for deployment at the end of January 2019. Further to these we have 21 BAU defects currently being worked on and all exclusions associated with these defects will be released once they has been deployed. Details of all defects and their progress are shared on the Xoserve website and updated on a weekly basis. The UIG Weighted Factors activities to release the adjustments have been completed therefore the status has been updated to Amber from Red. We will start to issue invoices along with supporting files week commencing 7th January 2019. | RCA | A
 | Defects & Exclusion | A
 | BAU | A
Progress since last month - key milestones | Workstream | Date | Status
Release Charges for Excluded MPRN’s 12,186K (for defects deployed) | Defects & Exclusions | 31/12/18 | Completed
Priorities for next month – key milestones | Workstream | Date | Status
Deploy Fix for 6 Defects | Defects & Exclusions | 31/01/19 | In progress
Exceptions Analysis (Procedure Update) | RCA | 05/10/18 10/11/18 07/12/18 31/01/19 | In progress
Automation of Offline ASP Mismatch files | RCA | 12/10/18 23/11/18 14/12/18 28/02/19 | In progress
PoC for single ASP file approval to proceed | RCA | 31/01/19 | In progress
Release Charges for Excluded MPRN’s (Billed) 8,267K (for defects deployed) | Defects & Exclusions | 31/01/19 | In Progress

## Slide 5: Amendment Invoice – Resolution Plan
6
 | 2018 |  |  |  | 2019 |  | 
 | Sept | Oct | Nov | Dec | Jan | Feb | Mar
Defects |  |  |  |  |  |  | 
Exclusions |  |  |  |  |  |  | 
Offline Automation |  |  |  |  |  |  | 
Design & RCA |  |  |  |  |  |  | 
Benefits Delivery |  |  |  |  |  |  | 
Mismatch reduction will be measured & reported, visible from October Invoice Cycle
Accelerated Offline file production +
backlog reduction
1
2
3
Mismatch & Exclusion reduction, will be measured & reported
4
All new defects fixed by end of following month (M+1)
Solution Work Packages
5
Number of system, scheduling and procedure changes – delivering final set of mismatch fixes
UBID P1
P2
1
5
ASP Correction file
2
BAU @ M+1
3
4
Eliminate Backlog (32 @ 1/9)
BAU @ M+1
Eliminate Backlog to 31/10

## Slide 6: Task Force Workstream Updates
7

## Slide 7: BAU Stream Update
8
Area | Action | Progress
ASP Mismatch Files | Reduce the delay issuing mismatch files Remove manual error within the files | The backlog continues to reduce slowly. We are still continuing to work on the automated solution to enable us to produce the ASP files to customers earlier. However the work involved is complicated and is proving to be very challenging. The number of shippers with an ASP file mismatch for November billing period has gone up to 22, Xoserve are currently investigating why this has happened and will update customers with an explanation once we have more information.
AML correction File (Data Extraction) | Change in the extraction script from SQL to ABAP | Due to a problem with the new ABAP process the October AML files were issued using the SQL extraction process. We are currently assuring the ABAP files for Nov-18, but will continue to use the SQL in the meantime. Once we have assured the ABAP and are confident the previous problems have been corrected it will be used for future AML Correction files. November AML files were due to be issued on Friday 4th January 2019. Due to an issue with the SQL extraction this has not been possible. A communication has been issued to Customers advising them of the problem.

## Slide 8: Defect and Exclusions Resolution Plan
10
Defect Resolution Plan as at 31st December 2018
https://www.xoserve.com/wp-content/uploads/Customer-Defects.pdf
A new Exclusion plan will be shared prior to the meeting.
These documents will be updated, tracked and published
weekly on Xoserve.com

## Slide 9: RCA Stream Actions
9
Activity | Target Completion Date | Benefits | Target Status
Package 3B: Additional Analysis: DM Rec Interface | 08/02/19 | Additional analysis required before benefits are understood. Areas were identified during RCA work as potential reasons for mismatches | On target
Package 3C: Additional Analysis: AML Extraction Process | 11/01/19 08/03/19 |  | On target
Package 4A: Exception Analysis: Procedure Update | 07/12/18 01/02/19 | Process improvements to ensure speedier closure of exceptions to release charges on the invoice and reduce mismatches | On target
Package 4B: Exclusion Analysis: Procedure Update | 28/09/18 16/11/18 |  | Complete
Package 5A: Service Improvement CRs: Automation and Reporting | 28/12/18 01/03/19 | Automated reporting internally to enable validation & invoice analysis prior to issue | On Target
Package 5B: Service Improvement CRs: Automation and Reporting | 18/01/19 |  | On target
Package 6: Code Review | 22/02/19 15/03/19 | Identify any further improvements areas to reduce mismatches | On target
Package 7: AML Scheduling Plan (Phase 1) | 05/10/18 | Delivery of file before payment due date | Complete
*Previous date given was for production of the plans to deliver the activity (Phase 2) is the actual plan to deliver AML files | 31/12/18* 11/01/19 |  | On target
Package 8: Single AML/ASP merge file *Previous date given was for POC and delivery of the supporting plans to deliver activity (Phase 1) Delivery Of PoC (Proof of Concept) for AML merge files PoC (Proof of Concept) for ASP merge file | 05/10/18 30/11/18 22/02/18 | Merge of files | Complete Complete In Progress
SAP Automation of Offline ASP Mismatch files | 14/12/18 28//02/19 | Earlier delivery of files | On target

## Slide 10: UIG Weighted Factors Issue - Update
During the extraordinary DSC Change Management Committee meeting held 27th November 2018 two option were provided for issuing the adjustments (link to meeting minutes below), the majority of customers opted for option 1. This was communicated during the WebEx held on 6th December 2018.
http://www.gasgovernance.co.uk/DSC-Change/291118
The latest communication was sent out before Christmas to advise customers that once assurance activities have been complete the invoice along with the supporting files will start to be issued week commencing 7th January 2019.

## Slide 11: Proof of Concept for AML/ASP and Historical files
Our aim is to deliver one complete supporting file for the amendment invoice (AML/ASP) in a timely manner and deliver all historical AML/ASP files going back to June 2017.
In order to achieve this we have three Proof of Concepts (POC) on-going for the amendment Invoice.
  The first is to merge the online and offline AML file so Customers receive one complete file with no mismatches. The POC for this has been completed and a plan to deliver this is currently under way.
  The Proof of Concept for the ASP file is being worked on at present and delivery plans will be share once the POCs have been completed.
  The POC for the historical files is being worked on at present and delivery plans will be share once the POCs have been completed.
Xoserve would like to highlight a few points regarding the delivery of the above
  The delivery of the AML/ASP files will be via the IX Route
  The sequence number for the files will be changed, this is to stop any confusion with previously sent files. Once the number sequence has been confirmed we will advise customers.

## Slide 12: UBID Implementation Update
12
Phase 1 was implemented in August and phase 2 implemented early October.
For the billing month of October the affected customers reduced to 16, and a financial value of £110,000 . This was significantly lower than the £2.5 million debit for the month of August.
For November billing period the number of customers with a billing mismatch has increased to 22 shippers and the financial value increase to £1.5 million.
  We are currently investigating the reason for the increase in numbers and will update customers with our findings.
Xoserve will continue to monitor the situation and keep customers informed of progress.

## Slide 13: Customer Engagement
15
Monthly progress updates provided to Contract Management Committee
(CoMC) and Change Management Committee (ChMC)
Updated plans published on Xoserve.com
DSG will be used to discuss and agree any solution options
Customer Liaison Manager will continue to be the first port of call for customers