## IP - In Analysis
UK Link Modification Implementation Plan - In Analysis
Functional Changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | AML Schedule Proposal | 1839.1 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 14/02/2018 - rejected | 03/01/2019 - We are currently investigating whether this intiative can be closed, and we will provide an update at the ChMC meeting in February 2019. Rejected at ChMC on 14th February. Xoserve to produce additional information - Cost vs benefit for further discussion. Further industry discussions to be held for both defects and requirements.
NA | NA | Change Pack Publication | 2008.2 | 2018-07-13 | 2018-07-27 | 2018-08-03 | X | X | X | X | X | NA | Still undertaking discussions at DSG. We are looking at several distibution mechanisms and will test how the Change Pack process would work for each one. 30/10/2018 - The intention will be to include this within the scope of the new Xoserve website design plans.

## IP - For Approval - Design
UK Link Modification Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
XRN4802 | N/A | Confirmation of the scope of delivery and planned deployment date of XRN4802 Minor Release Delivery ‘Drop 3’ | 2178.3 - RJ - ES | 2018-12-14 | 2019-01-04 | TBC | X |  |  |  |  | 2192 - RJ - ES | 2019-01-09 | 2019-02-16 | XRN4802 Minor Release Drop 3 (MiR Drop 3) commenced Detailed Design activities back in November 2018 with two changes in scope for full ‘end to end’ delivery. Both XRN4690 (Actual Read Following Estimated Transfer Read Calculating AQ of 1) and XRN4717 (Use of Up to Date Forecast Weather Data in First NDM Nominations Run) are ‘new’ changes that were approved for delivery by ChMC on the 10th October 2018. These two changes in scope for delivery as MiR Drop 3 are currently in progress with a planned deployment date of the 16th February 2019.
XRN4376 | N/A | GB Charging and Incremental (PARCA) Part B - Summary of the External Changes Identified | 2178.1 - RJ - ES | 2018-12-14 | N/A - For Information Only | N/A | X | X | X | X |  | N/A - For Information Only | N/A - For Information Only | 2019-09-08 | This Change Pack was submitted for information to confirm the system implementation date of 8th September 2019 for XRN4376 EU/GB Charging Project ‘Part B’, and to provide an overview of the Change Design Description.
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
Defect 1052 | N/A | Amendment to the UNC Validation Rules to allow the Central Data Service Provider (CDSP) to derive Round the Clock values where Meter Readings are provided in a non-Chronological Read Date order. | 2178.5 - RJ - ES | 2018-12-14 | 2019-01-04 | TBC | X |  |  |  |  | 2192 - RJ - ES | 2019-01-09 | Adhoc Release - January 2019 | There are no changes proposed to the Interface Definitions (i.e. records / hierarchies) in the UK Link Manual. Where the CDSP have derived an amended RTC value this will not be provided to Shipper Users. A change to the UNC Validation Rules are proposed to allow the Central Data Service Provider (CDSP) to derive Round the Clock values where Meter Readings are provided in a non-Chronological Read Date order.
3667a - XRN3667a Provision of Prospective Formula Year AQ/SOQ and Historic RAQ to Proposing Users (Design Approval)
3667a | N/A | XRN3667a Provision of Prospective Formula Year AQ/SOQ and Historic RAQ to Proposing Users (Design Approval) | 2140.6 - RJ - ES | 2018-11-09 | 2018-11-23 | 2018-11-30 | X |  |  |  |  | 2164 - RJ - ES | N/A | 01/02/2018 End of December 2018 | 12/12/2018 - This is a Design Change Pack; this Change Pack received two responses, which were in support of the Design Specification. 09/01/2019 - At the ChMC meeting on 12th December, an action was raised to remove this change from the functional changes section and indicate the revised implementation date.

## IP - Approved Last Meeting
UK Link Modification Implementation Plan - Approved on 12th December 2018
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4770 | 0654 | NDM Sample Data – Modification 0654 Delivery (Design Approval) | 2140.9 - RJ - ES | 2018-11-09 | 2018-11-23 | 2018-11-30 | X |  |  |  |  | 2164 - RJ - ES | N/A | 2019-03-01 | This is a Design Change Pack; this Change Pack received four responses, which were in support of the Design Specification.
4687 | N/A | PSR Updates for Large Domestic Sites | 2160.1 - SH - ES | 2018-11-27 | 2018-12-11 | 2018-12-12 | X |  |  |  |  | 2174 - RJ - ES | N/A | 2018-06-28 | This is a Design Change Pack associated with the June 2019 Release.
4670 | N/A | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | 2157.2 - RJ - ES | 2018-11-23 | 2018-12-07 | 2018-12-10 | X |  |  |  |  | 2171 - RJ - ES | N/A | 2018-06-28 | This is a Design Change Pack associated with the June 2019 Release.
4676 | N/A | Reconciliation issues with reads recorded between D-1 to D-5 | 2157.3 - RJ - ES | 2018-11-23 | 2018-12-07 | 2018-12-10 | X |  |  |  |  | 2171 - RJ - ES | N/A | 2018-06-28 | This is a Design Change Pack associated with the June 2019 Release.
Documentation Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
N/A | N/A | Release Implementation Dates | 2140.4 - RJ - ES | 2018-11-09 | 2018-11-23 | 2018-11-30 | X | X | X | X | X | 2164 - RJ - ES | 2018-12-12 | 2018-12-13 | We propose the November 2019 date is revised from 1st November 2019 to 8th November 2018 as the originally agreed November 2019 Release Date, approved in September 2018, does not follow the standard convention for UK Link Releases. Two responses were received, which supported this change.
N/A | N/A | Minor Changes to the UK Link Manual to reflect receipt of Service Desk contacts via Web portal | 2140.8 - RJ - ES | 2018-11-09 | 2018-11-23 | 2018-11-30 | X | X | X | X |  | 2164 - RJ - ES | 2018-12-12 | February 2019 Documentation Only Release | To support UK Link Users they may raise a Service Contact through a portal application as detailed in XCE1773 - New Portal for Submitting Service Desk Requests. The portal can be accessed here. The new portal is also accessible via the Quick Links on our website’s homepage and under the Contact Us section. We are proposing this change to support the amendment of UK Link Manual documents that refer to raising Service Contacts. We received two responses in support

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
N/A | Gemini B2B | 02/02/2019 03/02/2019 | 03:15:00 03:00:00 | 02/02/2019 03/02/2019 | 04:15:00 05:00:00 | Annual test to prove disaster recovery capabilities and procedures for Gemini B2B System. This activity does not impact the service. (second line timings are for failback activities). | 2019-01-09