## Slide 1: UKL Future Release 3
XRN4534 – Amendment to RGMA validation rules for asset install date
Deployment Options – 9th January 2019 Update

## Slide 2: Summary
1st February is no longer considered a viable option for deploying XRN4534 due to additional delays experienced at the start of acceptance testing. To pursue this date now would add unacceptable risk on dress rehearsal and therefore deployment of XRN4454 (Cadent).
By removing XRN4534 from the 1st February go live there is now no risk from this change remaining on the deployment of XRN4454 (Cadent)
Following discussion at the last ChMC meeting in December, the preferred contingency go live date of 1st March is now the only remaining option for delivering XRN4534 as part of Release 3
There remains significant risk to this plan given the continued expectancy to find additional defects within the process but at present the 1st March is a viable go live date
If 1st March is not achieved or is deemed undesirable by ChMC then options for future deployment of XRN4534 either independently or aligned with a future minor or major release will need to be fully investigated and evaluated
Approval is sought at this (9th January) meeting of ChMC to continue towards a 1st March deployment. Updates on progress will be given through the relevant channels and forums including the ChMC meeting in February.

## Slide 3: Option Timelines
w/c | 3 Dec | 10 Dec | 17 Dec | 24 Dec | 31 Dec | 7 Jan | 14 Jan | 21 Jan | 28 Jan | 4 Feb | 11 Feb | 18 Feb | 25 Feb | 4 Mar
Option 1 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Option 2 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Option 3 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Option 4 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
AT
RT
IDR / Cutover
AT
RT
IDR / Cutover
Cont.
AT
RT
IDR / Cutover
Cont.
AT – currently in progress
RT
IDR / Cutover
Previously presented – No longer viable
Previously presented – Disregarded in favour of March 1st option
Previously presented – Disregarded in favour of March 1st option