## Slide 1: DSC Change Committee Summary – 9th January ‘19
1 New change proposals raised and approved
  XRN4833 – Roll out of Business Intelligence and Data Discovery Capability – information
    Some additional slides presented and a demo:
0 New change proposal post initial review
  None presented
2 Solution/Delivery option approvals
  XRN4753 – CMS Increase information in .QCL response file
    Proposer preferred solution was additional training/knowledge, a couple of representatives wanted a technical solution so likely the proposer will withdraw CP and if technical solution required a new CP will need to be raised.
  XRN4691-94 – CSEPs and IGT & GT File Format changes
    On going work between GT’s & IGT’s will be tabled at April 2019 meeting
Implementation plan – approved
  Exception EUC Change pack deferred for extraordinary meeting 21st January 2019

## Slide 2: DSC Change Committee Summary – 9th January ‘19
Release Updates:
  Release 2 (delivered June 2018)
    CCR approved
  Release 3 (due to be delivered 2nd November 2018)
    Track 2 – Cadent Billing change on plan - Green
    1 change from track 1 (XRN4534 – amendment to RGMA validation rules) not delivered in track 1 due to regression test issues, due to delivered with track 2, conifrmed unlikely to be delivered 1st Feb 2019 without putting Cadent delivery at risk therefore aiming for 1st March 2019 delivery, will be confirmed Feb 2019 ChMC
  February 2019 release
    Minor and major release both on track for delivery
    BER for Feb minor release approved
  June 2019 release
    BER approved
  XRN4665 – Creation of new end user categories
    BER approved for UK Link change costs but some further analysis and costs to be provided for changes required to gemini
    Delivery plan approved

## Slide 3: DSC Change Committee Summary – 9th January ‘19
Standard agenda item updates:
  CSS consequential change update
  XRN4695 UIG Taskforce update
  Amendment invoice update
  Finance and Budget update
  Bubbling under report (MODs)
  Plan on a page:
    Gemini
    UK link changes (including data)

## Slide 4: DSC Change Committee Summary – 9th January ‘19
AOB items
  IX Update (same material shared in CoMC meeting)
    https://gasgov-mst-files.s3.eu-west-1.amazonaws.com/s3fs-public/ggf/2019-01/12.1%20IX%20Refresh%20Update.pptx
  KVI Change Survey results
    https://gasgov-mst-files.s3.eu-west-1.amazonaws.com/s3fs-public/ggf/2019-01/12.2%20KVI%20Change%20Survey%20Results.pptx
  Xoserve Change Proposals and the E2E change process
    https://gasgov-mst-files.s3.eu-west-1.amazonaws.com/s3fs-public/ggf/2019-01/12.3%20Xoserve%20Change%20Proposals%20and%20the%20E2E%20Change%20Process.pptx
  MDD process
    https://gasgov-mst-files.s3.eu-west-1.amazonaws.com/s3fs-public/ggf/2019-01/12.4%20MDD%20Process.pptx
  4770 NDM sample data change pack
    https://gasgov-mst-files.s3.eu-west-1.amazonaws.com/s3fs-public/ggf/2019-01/12.7%204770%20NDM%20Sample%20Data%20Change%20Pack.pptx