## Slide 1: XRN4802 - Feb 19 Minor Release - Status Update
29th October 2018 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Testing – All testing activities due to complete by Friday 8th Feb. Implementation – Implementation prep due to start w/c 11th Feb with planned on track Implementation date of Saturday 16th Feb |  |  | 
Risks and Issues | No current risks or issues around Minor Release Feb-19. |  |  | 
Cost | All costs covered in the approved BER (approved at ChMC 9th Jan 18) |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 2: XRN4802 – Feb 19 Minor Release & Feb 19 Document Release Timeline
Minor Release Key Milestone Dates:
16th February - Implementation
2019
May
Jun
Jul
Aug
Sept
Oct
Nov
Dec
Jan
Feb
Mar
2018
Testing
Build
UT
Imp
Apr
Feb-19 Minor Release Timeline
Design
Build
ST & Assurance
CM
PT / RT
IMP
PIS
Document Release Implementation
Document Release Key Milestone Dates:
1st March - Implementation
Feb-19 Minor Release Timeline
Feb-19 Document Release Timeline