## Slide 1: XRN4665 – EUC Release
04/12/18 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Design: Design workshops are completed and documentation is in final approval, The Change Pack was approved at an extraordinary ChMC on the 21st January Plan: Tracking to plan, detailed testing phases are being planned at the low level detail Funding: The BER was approved at ChMC 9th January. |  |  | 
Risks and Issues | Environments– There is a risk that due to multiple projects running in parallel in the same track (EUC & GB Charging) a detailed assessment of co-existence is in progress Review of risk to complete all testing phases to meet the full scope is in progress Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 
Cost | Project delivery costs are tracking to approved budgets |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 2: XRN 4665 - EUC Release Timelines
Key Milestone Dates:
Traceability of Detailed Design to Requirements to be completed
Detailed planning of overall Testing Phase and component aspects in progress
Agreement of EUC Release Part A & B Implementation Dates to be agreed with ChMC

## Slide 3: XRN4732 - June 19 Release - Status Update
29th October 2018 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Detailed Design: Design activities completed on the 25th January as per plan Build: Activities have commenced to plan Plan: Tracking to plan, detailed testing phases are being planned at the low level detail. Build has commenced to plan Funding: The BER was approved by ChMC at the 09th January 19 meeting |  |  | 
Risks and Issues | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, AML/ASP etc) and all requirements are able to be met |  |  | 
Cost | Project delivery costs are tracking to approved budgets |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 4: XRN4732 - June 19 Release Timelines
Key Milestone Dates:
Traceability of Detailed Design to Requirements to be completed
Agreement of June 19 Implementation Date to be agreed with ChMC