## Slide 1: DSC Change Committee Summary – 13th February ‘19
9 New change proposals raised, 1 to be withdrawn, 8 approved.
  XRN4824 – National Grid Transmission Daily Gemini Report
  XRN4850 – Notifications of Customer contact details to Transporters
  XRN4851** – Moving Market Participant Ownership from SPAAA to UNC/DSC
  XRN4852** – Amendments to the DSC Change Management Procedure
  XRN4853 – UIG – Recommendations 3.1 Option (Interim process to monitor & manually load rejected reads into UK Link where the read was rejected for reason code MRE00458 only)
  XRN4854 – Transfer of NDM Sampling Obligations from Distribution Network Operators to the CDSP
  XRN4858** - Amendments to DSC Service Description Table
  XRN4859 - Increasing MAM Access to CDSP Data to Mitigate Reduced MAM Appointment Timescale – To be withdrawn
  XRN4860 - National Temporary UIG Monitoring (requesting to draw on UIG taskforce funds)
  ** these changes are expected/will required future review and approval by Contract Committee due to DSC Contract change.
0 New change proposal post initial review
  None presented

## Slide 2: DSC Change Committee Summary – 13th February ‘19
2 Solution/Delivery option approvals
  XRN4777 – Acceptance of Contact Details Updates
    Recommended solution option timestamp file on receipt , expected to be delivered in July minor release
  XRN4806 - Additional Data at National Level to Support UIG Allocation Validation
    To be issued in design change pack and approved to implement 1st March
2 Change Proposals were withdrawn
  XRN4044 – Extension of Must-Read Process to include Annual Read Sites
  XRN4753 – CMS Increase Information Provided in .QCL Response File
Implementation plan – approved
Change Documents – Approved
  Evaluation Quotation Report for the November 2019 Release

## Slide 3: DSC Change Committee Summary – 13th February ‘19
Release Updates:
  Release 3 (due to be delivered 2nd November 2018)
    Track 2 – Cadent Billing change – delivered 1st Feb now in Post Implementation Support, minor defects raised
    1 change from track 1 (XRN4534 – amendment to RGMA validation rules) confirmed to be delivered 1st March 2019 delivery.
  February 2019 release
    Minor and major release both on track for delivery
  June 2019 release
    Currently tracking Amber – greatest risk is centred around resource
  XRN4665 – Creation of new end user categories (2 stage release Jul & Sept)
    Currently tracking Amber – re-planning activities undertaken, risk on resources, also used sharing environment with GB Charging MODs
Change Assurance update for Release 3 provided
  https://gasgov-mst-files.s3.eu-west-1.amazonaws.com/s3fs-public/ggf/2019-02/7.7%20Change%20Assurance%20Update.pdf

## Slide 4: DSC Change Committee Summary – 13th February ‘19
Standard agenda item updates:
  CSS consequential change update
  XRN4695 UIG Taskforce update
  Amendment invoice update
  Finance and Budget update
  Bubbling under report (MODs)
  Plan on a page:
    Gemini
    UK link changes (including data)

## Slide 5: DSC Change Committee Summary – 13th February ‘19
AOB items:
IX Refresh Update
  Link to Document
XRN4790 – Introduction of Winter Reads/Consumption Reports (Mod 0652): Annual Winter Consumption Calculation Issue
  Link to document
Verbal update provided on Data Catalogue
  Similar update was provided to DSG on 4th February
Using new Xoserve website for the management and distribution of Change Packs
Published Change Proposals – moving from the Joint Office website as a reference to Xoserve.com
MDD Update
  Link to document
KVI Change Management Survey Results
  Link to document