## Issue Register Open
Date Raised | XCE Reference | Customer Sector Affected | Defect / CR ID. | Issue Title | Issue Description and Materiality | Industry / Customer Impact (financial & process) | Impact to UIG | Xoserve Priority | Resolution Action Plan | Planned Implementation Date | Latest Update | Resolution Status | Date of Status Change
2017-06-01 |  | Shippers | Mod 0658 / XRN4695 | Levels & volatility of Unidentified Gas (UIG) | Levels & volatilty with UIG between D-5 of the gas day to GFD+5 and beyond D+5 close-out in extended reconciliation periods which create the need for Shippers to account for UIG until eventually reconciled. | The ongoing level, volatility and unpredictability of UIG is causing considerable commercial difficulty to Shippers across both domestic and non-domestic sectors | Investigating UIG | High | Please view latest update on Xoserve.com https://www.xoserve.com/index.php/unidentified-gas-uig/ | N/A | Please view latest update on Xoserve.com https://www.xoserve.com/index.php/unidentified-gas-uig/ | On Track
2017-07-18 |  | Shippers | N/A | Amendment Invoice supporting information (AML & ASP files) | A number of functional defects and integration issues are causing presentation and charge calculation issues within the AMS invoice. | Presentation issues where data is missing or incorrect within the ASP / AML supporting data files which a workaround is in place but is causing customers issues when trying to match the data. The charge calculation issues are excluded from the invoice until a fix is deployed. | Yes - UIG Reconciliation. Any incorrect or withheld reconciliations will affect UIG reconciliation. | High | Please view latest update on Xoserve.com: https://www.xoserve.com/index.php/amendment-invoice/ | Please see plans on Xoserve.com | Please view latest update on Xoserve.com: https://www.xoserve.com/index.php/amendment-invoice/ | Overdue
2018-06-21 | XCE1726 | All | See separate tab | Data issues affecting AQ calculations | Number of issues identified affecting AQ calculation. The analysis has identified that the issues appear to be related to specific scenarios associated with the energy used in the AQ calculation | Incorrect allocations which will only correct when a read is loaded and energy is reconciled however it could take upto 12 months for the AQ to correct. This will also affect UIG as the allocations for NDM meter points are based on the AQ. | Yes - UIG Gas Allocations. AQ is used to calculate gas allocations. | High | 1. Profiling to identify no. of meter points affected and the impacts on the AQ - ongoing, focus on RCA & fix 2. Map each issue to the scenarios identified that have caused issues in the AQ calculation - complete 3. Identify any defects resulting in held Reconciliations that have also affected AQ - Complete 4. Action plan agreed for all defects at DSG 5. Correction of consumption 6. Re-calculation of AQ effective for 1st December or 1st April for 'low' priority defects. | See separate tab for AQ defects deployment dates | See separate tab | On Track
2018-10-26 | XCE1784 | Shippers |  | UIG share & charges incorrect for since October 2017. | The UIG share & charges since October 2017 have been issued on the Amendment invoice incorrectly. This is due to the wrong UIG weighting factors being applied to two End User Category (EUC) bands. | The End User Category (EUC) bands affected are: EUC 02 and EUC 07 - all meter points in these EUC bands have been allocated UIG incorrectly following reconciliation. However, the energy for all EUC bands will require reapportionment to correct the energy position. The financial position for UIG will be incorrect. Individual Shippers positions could be under or over stated depending on their portfolio split. | Yes, incorrect values issued, this will be corrected when adjustments are applied. | High | 1. Communicated at ChMC on 29/11/18 & resolution plan agreed 2. Plan agreed by business 3. An adjustment to correct positions will be issued to customers by 23/04/19 | Please view latest update on Xoserve.com https://www.xoserve.com/index.php/unidentified-gas-uig/ | Please view latest update on Xoserve.com https://www.xoserve.com/index.php/unidentified-gas-uig/ | At Risk | Adjustment planned to be delivered by end of April
2018-11-15 |  | Shippers | 1164 | Incorrect formula year SOQ & AQ values in TRF file for Class change & AQ correction effective for same day | Issue where AQ & NDM_SOQ are not getting updated correctly in UKLink and not populated in NRL file. Linked to defect 1205 | Incorrect data issued in the transfer of ownership files. | No impact | High | 1. Fix development completion date 18/02/19 2. Testing completion date 3. Target deployment date is 22/03/19 | 22/03/2019 | Internal testing in progress - 12/03/2019 | At Risk | Resolution status is set to 'At Risk' due to the complex testing scenarios
2018-11-15 |  | Shippers | 1205 | Incorrect formula year SOQ & AQ values in TRF file for Class change & AQ correction effective for same day | Formula year SOQ value is incorrect in the TRF file when a class change received through CNF and AQ correction goes live for the same effective date. Ongoing AQ correction request has not been considered to derive the formula year SOQ value. Also the Formula year AQ value in fact is incorrect, ongoing AQ correction value needs to be considered. Same issue has also occurred when class change and EUC change happening on the same date. SOQ values in TRF / CFR and NMR files sent incorrectly | Incorrect data issued in the transfer of ownership files. | No impact | High | 1. Fix development completion date - 06/02/19 2. Target testing completion date 15/03/19 3. Target deployment date is 22/03/19 | 22/03/2019 | Internal testing in progress - 12/03/2019 | At Risk | Resolution status is set to 'At Risk' due to the complex testing scenarios
2018-12-20 |  |  | 1247 | Winter Consumption process not using all reads types during calculation | Winter Consumption calculation process in not using all read types to calculate the WC. | Not all required sites are using the winter consumption calculation, therefore the SOQ and AQ are incorrect. | No impact | High | 1. Fix development completion date 20/12/2018 2. Testing completion date 3. Target deployment date is 22/03/19 | 22/03/2019 | Internal testing in progress - 12/03/2019 Defect is aimed to be deployed on 22/03/2019 | On Track
2019-01-16 |  | Shippers | 1264 | Incorrect data provided in AQ notification file T98 file record | The monthly AQ Roll process is populating the incorrect EUC number, EUC description and confirmation reference number in the T98 file record of the NRL file (AQ notification) | Shippers are receiving incorrect data | No impact | Medium | 1. Code fix complete - 21/02/2019 2. Testing completion - 01/03/2019 3. Target deployment date is 15/03/19 | 15/03/2019 | Defect is aimed to be deployed on 15/03/2019 | On Track
2019-01-16 |  | Shippers | 1267 | Incorrect FYAQ calculation for Greenfield sites | Formula Year AQ not calculated correctly for greenfield sites where its changed from Daily Metered (DM) to Non Daily Metered (NDM) where the request was received in December with the D-2 date falling in December for confirmations due in January of the following year. | Incorrect FYAQ is being calculated, however this is only an issue for Confirmations going live in the new year with the D-2 date falling in December of the prior year. Manual corrections catered out for affected sites – Dec 28th and Dec 31st 2018 for Confirmations effective on 1st, 2nd and 3rd Jan 2019 and therefore no impact to customers. | No impact | Low | Manual correction was applied to the affected MPRNS, and therefore no direct impact to customers. Fix development completed on 25/02/2019 and internal testing is in progress The fix of this defect is low priority as it is not required until December 2019, however target deployment date is 22/03/19 | 22/03/2019 | Internal testing in progress - 12/03/2019 Defect is aimed to be deployed on 22/03/2019 | On Track
2019-01-16 |  | Shippers | 1269 | NDM Offers being cancelled incorrectly by Ratchet process | Class change from Daily Metered (DM) to Non Daily Metered (NDM) Offers are being incorrectly cancelled where the Ratchet SOQ is greater than the requested SOQ contained within the Offer | Offers are getting cancelled incorrectly | No impact | Medium | 1. Profiling to take place to identify affected Mprns and Shippers. 2. All affected MPRNs to be issued to shippers. 3. Fix development completed - 01/03/2019 4. Internal testing in progress - 12/03/3019 5. Defect aimed to be deployed on 22/03/2019 | 22/03/2019 | Fix development completed - 01/03/2019 Internal testing in progress - 12/03/3019 Defect aimed to be deployed on 22/03/2019 | On Track
2019-01-21 |  | Shippers | 1271 | AQ Correction request being processed incorrectly | AQ Correction request is being processed incorrectly. The file is correctly rejecting (S72), however is also sending an acceptance response (C43) | Conflicting information is being sent to the Shipper | No impact | Medium | 1. Profiling to take place to identify affected files 2. Defect fix planned deployment on 08/03/2019 3. All affected MPRNs to be issued to shippers | 01/03/2019 | Fix development completed - 15/02/19 Testing completed - 21/02/19 Fix deployed - 01/03/19 Profiling in progress for affected MPRN's - 12/03/2019 | Complete | 01/03/2019 as defect deployed however will continue to track until the MPRNs & associated data have been issued to customers.
2019-01-22 |  | Shippers | 1274 | Class Change requests incorrectly rejecting following Transfer of Ownership | Shipper class change requests are incorrectly rejecting where a change of ownership has taken place within 2 months of the previous class change request | Shippers are unable to submit Class Change requests following confirmation of a supply point. As per UNC, there is a two month restriction on class changes, however this should not apply when there has been a Transfer of Ownership. | No impact | Medium | 1. Profiling to take place to identify affected Mprns and Shippers. 2. All affected MPRNs to be issued to shippers. 3. Target deployment date is 05/04/19 | 05/04/2019 | Analysis underway - 12/03/2019 | On Track
2019-01-24 |  | Shippers | 1280 | Incorrect data provided within MDR and DDR files | Where a better estimate read is calculated and sent to Shippers/ DMSP, the read fields are being populated with the incorrect data | Shippers are receiving incorrect data | No impact | Medium | 1. Fix development completion date- 07/02/19 2. Testing completion 3. Target deployment date is 22/03/2019 | 22/03/2019 | Internal testing in progress - 12/03//2019 Aimed to be deployed on 22/03/2019 | On Track
2019-01-24 |  | Shippers | 1281 | Fault flag not being correctly removed within the system | Where a Site Visit and Asset Fault Notification File (SFN) is submitted to remove a fault flag in the system, the file is getting accepted, however the flag indicator remains | Shippers are being notified that the file has been accepted which result in the fault flag being closed, however the fault still remains in the system. This will result in Shippers not being able to upload reads for the affected sites | No impact | Low | 1. Fix development completion date - 20/02/2019 2. Testing completion 3. Target deployment date is 22/03/2019 | 22/03/2019 | Internal testing in progress - 12/03/2019 Aimed to be deployed on 22/03/2019 | On Track
2019-02-05 |  | Shippers | 1293 | Incorrect data provided within the MIF file | Issue with the MIF File (Supporting information file generated as part of the MAS invoice). The K50 file record (Meter Portfolil Detail) is being populated with the incorrect data. | Shippers are receiving conflicting data against the MAS invoice | No impact | Low | 1. Fix development 2. Testing completion 3. Deployment date | Not yet allocated | Analysis underway | No Date Recorded
2019-02-15 |  | Shippers | 1302 | Data issues affecting Monthly Shipper Packs | The count of MPRNs within the Confirmed No Asset section of the Shipper Pack does not currently include sites where there has never been an asset attached to the site | Shippers are receiving incorrect data | No impact | Low | 1. Fix development - 15/02/2019 2. Testing completion 3. Deployment date aimed for 08/03/2019 | 22/03/2019 | Testing in progress - 12/03/2019 Defect aimed to be deployed on 22/03/2019 | On Track
Insert new rows above this line

## Issue Register Closed
Date Raised | XCE Reference | Customer Sector Affected | Defect / CR ID. | Issue Title | Issue Description and Materiality | Industry / Customer Impact (financial & process) | Impact to UIG | Xoserve Priority | Resolution Action Plan | Planned Implementation Date | Latest Update | Resolution Status | Date of Status Change
2018-03-20 |  | Shippers | 945 | Incorrect functionality of a Meter Read validation routine affecting circa 3,000 meter reads | An issue was identified in March following a number of exceptions raised from UK Link. A validation routine in UK Link was creating exceptions in certain scenarios when processing the meter read. It was found that the validation job was incorrect. On the 9th March 2018 the validation was stopped. Analysis has identified that 3,652 MPRNs have been affected. | Reads accepted and displayed correctly on UKLink & Data Enquiry however AQ & Reconciliation calculated on the amended read or read date. |  | Medium | 1. Apply fix to all MPRNs. A data fix was deployed weekend of 5th/6th May. Complete 2. Correct energy of those MPRNs affected for the May Amendment invoice issued in June. Complete 3. Carry out analysis on affects on the MPRNs by 15th June. Complete 4. Notify Shippers of the MPRNs (completed on 11th May), impacts & what has been done to correct by w/c 17th September 5. Affected Shippers to either submit a new read (Rolling AQ) or an AQ correction (FYAQ) to correct the AQ value 6. Operations team to re-profile 314 MPRN's at the end of October (which were sent out to the industry on 17/09/2018) to identify how many AQ values have been corrected via Shipper action |  | Reports ran to identify meter points where a revised AQ has not been calculated. Comms issued 6th November advising those Shippers where a revised AQ has not been calculated to submit a read before No further action required. | Complete | 2018-11-06
2017-12-11 |  | DN's |  | Network Reports - providing aggregate AQ, SOQ & CSEP portfolio information (BOPRI & SCH606) | The BOPRI & SCH606 reports are issued to DNs monthly (BOPRI on 28th & SCH606 on the 1st). There have been issues with both reports including the December report which DNs use to set their transportation rates for the 12 months commencing 1st April. BOPRI shows all 'rolling' AQs, SCH606 all CSEP SOQs. Updated reports issued on the 11th January however, due to the difference in the reports Networks were not confident with the reports issued in January. | Reports are used by DNs for setting the transportation rates the the 12 months from April. Any errors in the reports will mean an under or over recovery which will need to be adjusted. |  | 3. High | 1. Validate the report issued in January. Complete 2. Ensure the monthly reports issued are correct. Complete 3. Ensure the IA carried out for datafixes includes BW impacts. |  |  | Complete | 2018-06-05
2018-04-01 |  | Shippers | XRN4671 | Energy for Class 2 sites incorrect in Gemini where a read replacement is received or a consumption adjustment within GFD+5. | Energy mismatch in Gemini where a read is replaced with a read or a consumption adjustment for Class 2 sites as the energy calculated is not being sent to Gemini correctly. | Impacts to invoicing: Energy Balancing, UIG, Commodity invoice, Impacts UIG - inaccurate values until adjustments are carried out. |  | High | 1. Carry out RCA. Complete 2. Raise defect. Complete CR raised 24/05/2018 4671. 3. Daily monitoring & adjustment process in place. 4. Deploy fix |  | Change implemented on 16/09/2018 | Complete | 2018-10-12
2018-05-15 |  | Shippers | 969 | Incorrect AQ/SOQ values issued in transfer of ownership files | At D-2 the TRF (transfer of ownership file) is issued to the Shipper and provides the values that will be effective on the transfer effective date, including AQ and SOQ values. Due to a code change for a defect deployed on September 27th 2017, incorrect Rolling SOQ data has been sent for all Class 3 and 4 sites transferring ownership, equating to 1.75 million Meter Points with incorrect SMP rolling SOQ values. The rolling SOQ being issued is the value as at EUC effective date (either 1st October or 1st of the month if a rolling AQ change has taken place).The transportation rates sent in the same file are correct. | Incorrect AQ & SOQ values issued to incoming Shipper. Transportation charges provided on the files are correct. |  | High | 1. Defect raised (969). Carry out RCA. Complete 2. Deploy fix. Complete 3. Notify Shippers of MPRNs affected & the correct values that should have been issued by 20th July. |  | Reports issued to Shippers on 23rd July 2018 showing the MPRNs affected, incorrect SOQ sent in the file & the SOQ that should have been sent in the file. | Complete | 2018-07-23
2018-03-01 |  | DN's |  | The number of Must Reads has increased significantly | - DNs raised the issue that the value on the invoices that we produce on their behalf to the Shippers has reduced since Nexus. At the same time, the invoices from the MRAs for procuring reads on their behalf has not reduced. - Analysis identified that the technical elements of the process are working correctly. However, there are reasons for the reduced value of the invoice (not all reasons affect all DNs) | Must Read revenue for DNs |  | Medium | 1. Analysis 2. Reporting to DNs 3. Focus on team to reduce queries outstanding & clear Must Reads 4. Discussions with MRA |  | 1. Updates provided directly to each DN on their position and the full position of Must Reads is provided 2. Attend DN Constituent meeting to provide overall updates. 3. Regular comms to DNs on progress updates & latest Must Read stats | Complete | 2018-08-15
2018-06-28 |  | Shippers | 1022 | Read issued in the Transfer of Ownership files (TRF) | At transfer of ownership the TRF file is issued on D-2 of the Confirmation effective date confirming the effective date of the Confirmation. The MRI file is also issued which contains asset information. The ‘Last Actual Read’ recorded on UKLink is submitted in both the TRF file (S15) and the MRI file however the read in the MRI is not the correct read. Defect 1022 raised. This has been since 01/06/2017. | Shippers use the read submitted in the transfer of ownership files to validate the next read received. |  | Medium | 1. Understand issue & resolve Complete 2. Apply fix 3. Advise Shippers when code deployed |  | Communication sent to Shippers on 28/08/2018 advising that the issue is fixed | Complete | 2018-09-15
2018-07-12 |  | Shippers | N/A | DPS file sequencing | DPS files issued to Shippers have not followed the sequence of the last release (e.g. .PN002332.DPS’ to .PN002354.DPS’ ) | Loading of files |  | Medium | 1. Understand issue & resolve 2. Advise Shippers |  | Files re-issued on 12/7/18 | Complete | 2018-07-12
2018-07-20 |  | Shippers | N/A | DM Reports | DM reports issued to Shippers were incorrect for 30/06/2018 to 06/07/2018 | TBC |  | Medium | 1. Identify reason for incorrect values being issued 2. Re-run reports & re-issue |  |  | Complete | 2018-07-17
2018-07-25 |  | Shippers | 999 | Incorrect FYAQ values issued in transfer of ownership files (TRF). | At D-2 the TRF (transfer of ownership file) is issued to the Shipper and provides the values that will be effective on the transfer effective date, including FYAQ and FYSOQ values. Incorrect FYSOQ data has been sent for all Class 3 and 4 sites transferring ownership, | Incorrect FYAQ & FYSOQ values issued to incoming Shipper. Transportation charges provided on the files are correct. |  | Medium | 1. RCA & profiling to identify no. of meter points - complete 2. Deploy fix. Complete. Complete 3. Notify Shippers of MPRNs affected & the correct values that should have been issued by 20th August. |  | 23/08/2018 - issue now closed and data provided to customers | Complete | 2018-08-23
2018-07-27 | XCE1739 | Shippers | N/A | UIG Rec Invoice includes kWh for SSP pre go live | The kWh presented in the supporting information is not as expected as it includes the kWh associated to SSP reconciliation pre go-live (which has no financial value). However this does not impact the invoice value as the smear is based on the monetary value (GRE) and we do not re-value the reconciliation using SAP and kWh. | TBC |  | Low | New, TBC |  |  | Complete | 2018-07-27
2018-07-27 | N/A | Shippers | N/A | Delay is publishing the Performance Assurance Report Register (PARR) reporting | The publication of the Performance Assurance Report Register (PARR) reporting for August 2018 will be delayed and will not be published on Monday 30 July 2018 as expected. | Unable to view reports |  | Low | The CDSP and PAFA are working on resolving these issues as efficiently as possible |  |  | Complete | 2018-07-27
2018-09-07 | N/A | Shippers |  | Estimated Transfer of Ownership Read Failure | Estimated Read not issued in MBR file following Transfer of Ownership . The two days affected were 15/06/2018 and 30/06/2018 and applied to 78 MPRN's (12 Shippers) | Shippers have not received notification of Estimated Transfer Read |  | Low | 1. Notify the Shippers of all affected MPRN's 2. IS Ops to ensure that the estimated read is sent via the MBR file to all affected Shippers by close of play Friday 14th September |  | 1. Reports issued to Shippers on 10/09/2018 2. IS Ops manually working through the affected MPRN's to ensure that the MBR file is re-generated 3. All MBR files were sent to the affected Shippers by 12/09/2018 | Complete | 2018-09-13
2018-09-07 | XCE1769 | Shippers | 1150 | Supplier details missing in the transfer of ownership (TRF) file | Issue with the Transfer of Ownership process where there is no asset on UK Link, the incoming Shipper has not received and will continue not to receive previous Supplier details in the TRF file (S75 file record). | Supplier details are not being sent to incoming Shipper. The Supplier details are required to be populated irrespective of the device status. |  | Medium | 1. Defect due to be deployed in November 2. Advice customers once deployed |  | Defect fixed and communication sent to Shippers to advise closure on 29/11/2018 | Complete | 2018-11-29
2018-10-01 | XCE1772 | Shippers | 1162 | .UPI (User Pays Index) File not incrementing when new file is issued | The August User Pays Index (UPI) file was issued with the same file name as the July a file name, e.g. PN00000X5. | August file may have rejected. Confusion & inconvenience to customers. |  | Medium |  |  | The User Pays Index (UPI) file is now being issued with the correct file name. The process will be continuously monitored to ensure no further exceptions arise from this. | Complete | 2018-10-01
2018-10-10 | N/A | Shippers | 1179 | Class change from incumbent Shipper issue | Where a class change request is received from an incumbent shipper, there is currently no rejection which is causing AQ mismatch between UKLink and Gemini. Confirmed this is not an issue. | AQ mismatch between UK Link and Gemini |  | Medium |  |  |  | Complete | 2018-10-01
2018-10-12 | XCE1804 | Shippers | 1188 | Incorrect rejection for Interconnector request (RCI file) | Request to register on the Interconnector is rejecting incorrectly stating Contact Job Details not provided (CTT00012) even though the Contact Job Title has been provided in the file | Shipper unable to register at the Interconnector |  | Low | 1. manual workaround taking place in Xoserve to ensure file is not rejected, this will continue until fix deployed. 2. Fix due to be deployed on 9th November. |  | Issue has been fixed and defect is closed | Complete | 2018-11-30
2018-11-28 | XCE1803 | Shippers |  | Incorrect Read Reason (READ_REASON) sent on the read file (MBR) notifying of an estimated opening read | Following registration of a meter point by a Shipper, if an opening meter reading is not submitted by D+10 of the transfer effective date an estimated read is calculated and issued to both incoming & outgoing Shipper. The read issued to the Incoming Shipper gave 'Read Reason' as 'CYCL', it should be 'OPNT'. This has affected 51, 000 meter points between 24/11/18 and 27/11/18. | Customers may load the read into their systems not realising this is the final/opening read for their customer. |  | High | 1. Notify Shippers of the meter points affected, transfer effective date, read & file name on 29/11/18 2. Submit replacement file with the read with the correct read reason - this was completed on 30/11/2018 3. Submit affected MPRNs to customers on request |  | Issue fixed and replacement files issued on 30/11/2018 | Complete | 2018-11-30
2018-02-12 |  | Shippers |  | Missing Read files where the meter exchange takes place on same date as transfer date | Transfer read files are not issued to the Shipper where there has been a meter exchange on the same day as a shipper transfer | Opening read & closing read not issued to the outgoing & incoming Shipper |  | Medium | 1. Agreement at DSG to apply a workaround until the defect is fixed |  | Fix took place on 24th November, however workaround to remain in place until end of December. Workaround is a weekly report that is sent by e-mail to all affected shippers informing them of sites in their ownership that have had a meter exchange on the same datre as the transfer date. Last report will be issued on 7th January. Fix implemented & sucessful. This issue can be closed. | Complete | 2019-01-04
2018-10-01 | XCE1774 | Shippers | N/A | Domestic M Number Helpline Incorrect Data | Since March the Domestic M Number Helpline service has not been providing accurate data in all cases | The lack of E22 and E23 files (E22_CONFIRMATION E23_METER_POINT & E25_METER) being loaded means that no supply point switches or new MPRN confirmations will have been reported from the M-number helpline since March 18. |  | High | 1. A solution was developed and the work to load the delta files will now commence in November which includes testing and is due to be completed by 12th December. 2. The method of implementation will mean that on 12th December the database will be at D+7. On the following day the remaining deltas will be applied meaning that by 14th December Supplier data will be D+1. |  | All updates were carried out sucessfully. Sample checks of previously incorrect data have confirmed data is now correct. Issue to be closed. | Complete | 08/01/2019
2018-10-12 | XCE1782 | Shippers | 1191 | Connection max AQ & SOQ incorrect in the Q44 record for iGT sites | Connection max AQ and SOQ values are incorrect in Q44 segment for the MPRNs that belong to CSEPs which are part of a nested configuration. This should have values for the parent CSEP, currently child CSEP AQ and SOQ values provided in this field. | Incorrect information being provided to Shippers in the Q44 record | No impact, presentation issue only | Medium | 1. Profiling to take place to identify affected Mprns and Shippers. 2. All affected MPRNs to be issued to shippers. 3. Deploy fix & advise Shippers | 11 Jan 2019 | 23.11 - Profiling is in progress 08/01 - Testing & assurance underway 09/01 - deploy fix on 11th january 14/01 - fix deployed | Complete | 14/01/2019
2018-10-12 | XCE1781 | Shippers | 1190 | Formual Year SOQ not provided in TRF File | Formula year SOQ value not provided for the TRF flows where confirmation effective date is 02nd Oct 2018. | Impact on green field sites only | No impact, presentation issue only | Low | 1. Profiling to take place to identify affected Mprns and Shippers. 2. All affected MPRNs to be issued to shippers. 3. Defect deployed 29/01/2019 | 29/01/2019 | Profiling complete and reports sent to affected Shippers on 22/10/2018 We will send communication advising that the issue is closed once the defect has been fixed | Complete | 29/01/2019
2018-10-02 |  | Shippers | 1172 | Class 1 or 2 Sites populating Incorrect Run ID as SSP instead of LSP | Class 1 & 2 meter points are being assigned as 'SSP' instead of 'LSP' on the Amendment invoice supporting information files. | Incorrect information being provided to Shipper on the Amendment invoice supporting files. However a manual workaround to correct the data is being carried out before the supporting files are issued. | No impact, presentation issue only | Low | 1. Continue to carry out manual data correction until fix is implemented. 2. Defect deployed 08/02/2019 | 08/02/2019 | Delay to deployment of fix as there is a manual workaround in place therefore pirority lowered 08/02 - Fix Deployed | Complete | 08/02/2019
2019-01-04 | XCE1809 | Shippers | 1256 Problem ID 1996 | Opening Reads Sent via the U03 file in Error to Previous Shipper | For Class 3 meter points, where a cyclic read is received from the Outgoing Shipper (via the .UBR file), for a read date, which is the same as the registration effective date (transfer date), the system is accepting the read, it should reject the meter reading. The read is being recorded as the Opening read (U03) and is being sent to the Shipper who submitted the read, and to the current Shipper as a Final read (U04) indicator | Outgoing Shipper is receiving reads with the incorrect reason code at transfer of ownership. Only affects Class 3 meter points when the Outgoing Shipper submits the read for the transfer effective date. | Potential if the read is not correct but very low impact to UIG Reconciliation | Medium | 1. Communicated to affected Shippers 2. Provided affected MPRNs to the affected Shippers on 4th january 3. RCA underway to understand cause. Assessment of fix & testing requirements in progress. 4. Target deployment date is 08/03/19 5. Defect deployed 08/03/2019 | 08/03/2019 | Testing completed - 12/02/2019 Fix deployed - 08/03/2019 | Complete | 2019-03-08
2019-01-16 |  | DNs & Shippers | 1265 | NDMSOQ Incorrect due to Winter Consumption process | The Winter Consumption calculation process does not create records in the correct table in UK Link, this results in the NDMSOQ value being incorrect for the annual FYAQ calculation. | Incorrect SOQ value sent to Shipper | No impact | Medium | 1. Fix development - 28/01/2019 2. Testing completion - 01/03/2019 3. Target deployment date is 08/03/19 4. Defect deployed 08/03/2019 | 08/03/2019 | Defect fix successful - 08/03/2019 | Complete | 2019-03-08
Insert new rows above this line

## P1 P2 Incidents
Ticket Ref | Date Raised | Issue Title | Issue Description | Cause | Resolution Action Plan | Raised By | Status | Closed Date
843169 (Problem ID 1636) | 2018-05-03 | Issues with the Allocation run in Gemini affecting UIG | Issue encountered with the first run of Energy Allocation for Gas Day 2nd & 6th May 2018. NDM Allocation failed to calculate for this gas day, for all LDZs, This was corrected within the day. | The cause of this issue is due to a code fault | 1. RCA 2. Daily monitoring until the cause is known 3. Datafix to be deployed end of June for issues relating to May allocation run (Problem ID 1636) 4. Review validations for data contained within files | Xoserve | Closed | 2018-05-03
848559 | 2018-05-17 | Gas Nominations batch job failure affecting UIG | Unidentified Gas nominations batch job failure within Gemini at approximately 11:00 on 17th May. Issue repeated on 21st May. All shippers with active Unidentified Gas meters in Gemini would have had a blank value within the Gemini demand screen for the next gas day nominations. Between 11:00 and 14:20 no forecasting figures shown | This is a known issue where a fault with the Gemini consequential code changes (as part of UK Link Replacement Implementation) resulted in figures remaining uncalculated in certain scenarios. | 1. RCA 2. Daily monitoring until the cause is known 3. Datafix to be deployed end of June | Xoserve | Closed | 2018-05-17
843903 | 2018-06-04 | Workflow did not complete in SAP potentially resulting in incorrect data held in UKLink & Gemini | Workflow did not complete for 4,000 meter points resulting in potential incorrect data being held in UKLink & SAP affecting gas nominations, allocations, DEs & invoicing. May also impact read estimation & read processing. | Fix deployed at the weekend affected the process. | 1. Identify cause 2. Re-start workflow & monitor until completion 3. If updates not completed by deadline date for each update, notify relevant customers & impacts as at 05/06/18: - 97 MPRNs which were due yesterday , have been completed yesterday - All affected workflows identified re-instantiated successfully - 3956 MPRNs - No Contract Change process flows pending for effective date prior to 04.06.2018. Out of 187 Class Change to be effective today i.e. 05.06.2018 , 82 are already completed, remaining are in progress . | Xoserve | Closed | 2018-06-05
| 2018-06-05 | Incorrect file loaded into Gemini affecting Allocations in Gemini & UIG | Issued experienced on 5th & 6th June due to incorrect file loaded for 5th June, delay with processing the file caused issues with allocation run on the 6th June. This was corrected within the day. Delayed publication of the UIG data for the 5th of June has meant that customers would have seen their UIG screens showing a blank value until the UIG job (as part of the Allocation Suite) had completed. | This was due to a system issue by Networks Aggregator systems experiencing a technical issue when transferring the file between systems. | 1. RCA 2. File re-loaded & Process re-ran 3. Correct UIG data was published around 12:30pm | Xoserve | Closed | 2018-06-06
856558 (Problem ID 1708) | 2018-06-08 | Incorrect demand forecast received affecting Gas Nominations & UIG | Separate issue affecting UIG for Gas Nominations on 8th June due to incorrect demand forecast received. All shippers with active Unidentified Gas meters in Gemini would have had a blank value within the Gemini demand screen for the next gas day nominations. Between 11:00 and 14:20 no forecasting figures shown | June issue caused by file an incorrect demand forecast had been sent to Gemini from National Grid’s Aggregator service, due to a Distribution Networks submitting incorrect values to NG. | 1. RCA 2. Daily monitoring until the cause is known 3. Continued daily monitoring until a manual validation or system validation can be implemented | Xoserve | Closed | 2018-06-10
856162 (Problem ID 1713) | 2018-06-15 | Issues with the Allocation run in Gemini affecting UIG | Issue identified on the 15th June. The UIG values are very high for LDZs NW, NO, WM for Gas Day 13/06/2018 | This is due to low Daily Metered (DM) values being used as part of the UIG calculation within the allocation suite job. | 1. RCA 2. New values received via the CON file will instigate a re-calculation using the correct Daily Meter value. UIG values will be monitored on a daily basis until Sunday Morning (17th June 2018) to ensure recalculation occurs. 3. If the UIG values do not re-calculate by the above date/time (due to no new amendments received via the CON file) then a data fix will be applied. 4. Further checks will be made early Monday morning (18th June) at 09:00 post the allocation suite run on Sunday evening at 19:00. | Xoserve | Closed | 2018-06-18
865213 | 2018-07-02 | Line Pack not published | A Control Room User raised a ticket as Line Pack had not been published for 00:00 hour bar. | Gemini Application Support began investigating and found that Gemini had received two Line Pack files at 23:00; this meant that the 23:00 hour bar loaded successfully with the first file but the second file got stuck in processing. The batch job was triggered and the 00:00 hour bar Line Pack file was published successfully. | P2 Incident Management process. | NG Control Room | Closed | 2018-07-02
| 2018-07-04 | Data Enquiry Service is at D-2 | There has been a delay in completing the daily data load for the Data Enquiry Service (DES). As a result the system is displaying data for 2nd July 2018 but data for 3rd July 2018 is not visible. The data for 3rd July 2018 is currently being loaded which means users may be experiencing slow performance on some of the screens |  | 1. RCA 2. Run batch process to update data 3. Advise customers | Xoserve | Closed | 2018-07-05
| 2018-07-12 | Technical issue with Data Search telephone service | technical issue with our Data Search telephone service, 0121 713 4901 and Contact Management Helpline, 0121 713 4903 |  | P2 Incident Management process Available 13/07/18 at 8.00 am | Xoserve | Closed | 2018-07-13
873558 | 2018-07-16 | UIG not visible in Gemini | Shippers and GNCC are unable to view the UIG Nominations balance for 15th and 16th Gas day & UIG allocations for 14th | A column in one of the table has size 8 digits which is causing the UIG job failures. Database have restructured the table column size from 8 to 10 in the production environment | P2 Incident Management process. The P2 for this issue will be closed, however as part of each Major Incident a Problem Record will be created that will be used to identify the Root Cause and provide any forward service improvement actions | Xoserve | Closed | 2018-07-16
874837 | 2018-07-20 | UIG mismatch in Gemini | Mismatch due to the UIG allocation job took time to complete for the gas day (11th ,12th,13th,14th,15th) which delayed the process. | Job overrun due to defect 873558 | This will be included in the RCA raised for the P2 | Xoserve | Closed | 2018-07-20
884278 | 2018-07-29 | Gemini-Demand Attribution not published for 10th hour bar | P2 raised at 10:30. Shippers unable to place gas nominations. | Scheduling team have identified that the demand attribution jobs were on hold | Batch jobs have manually released the jobs. Jobs are now completed and demand attribution is published. Service resumed at 11:31. Problem record raised for further investifgation: 1797. | Xoserve | Closed | 2018-07-29
886370 | 2018-08-05 | IX - Unable to connect to multiple shipper sites | AML file delivery to 3 shippers impacted. | Vodafone IX team have updated that the connectivity issue is due to huge file transfer (400MB files); | Rebooted the IX servers for the affected sites to restore the connectivity. | Xoserve | Closed | 2018-08-05
888227 | 2018-08-09 | UIG Allocations | The Unidentified Gas (UIG) batch job failed to complete in Gemini yesterday evening (August 8th). This has affected the following: The UIG allocation values for Gas Days 3rd to 6th August were not updated and are out of date for all LDZs. The UIG allocation values for Gas Day 7th August were not calculated and appear as zero for all LDZs for all Shippers | This was due to the allocation suite overrunning on 8th August hitting the maintenance window. | Calculations to have been completed and visible to Shippers via Gemini from this afternoon (Thursday 9th). A service improvement proposal is currently being reviewed by NG regarding our recommended tactical archiving solution to alleviate the operational issues associated with the overrunning allocation suite. We are expected approval from their change board next week so we can start the work | Xoserve | Closed | 2018-08-09
888227 | 2018-08-10 | UIG Allocations | The Unidentified Gas (UIG) batch job failed to complete in Gemini yesterday evening (August 9th). This has affected the following: The UIG allocation values for Gas Days 4th to 7th August were not updated and are out of date for all LDZs. The UIG allocation values for Gas Day 8th August were not calculated and appear as zero for all LDZs for all Shippers This is linked to 888227 | This was due to the allocation suite overrunning on 9th August hitting the maintenance window. | Calculations to be completed (by 12:45) and be visible to Shippers via Gemini from this afternoon (Friday 10th). A service improvement proposal is currently being reviewed by NG regarding our recommended tactical archiving solution to alleviate the operational issues associated with the overrunning allocation suite. Approval expected from change board next week so work can begin early September. | Xoserve | Closed | 2018-08-10
888227 | 2018-08-13 | UIG Allocations | The Unidentified Gas (UIG) batch job failed to complete in Gemini yesterday evening (August 12th). This has affected the following: The UIG allocation values for Gas Days 4th to 7th August were not updated and are out of date for all LDZs. The UIG allocation values for Gas Day 11th August were not calculated and appear as zero for all LDZs for all Shippers This is linked to 888227 | This was due to the allocation suite overrunning on 11th August hitting the maintenance window. | Currently discussing remedial action with National Grid to minimise further instances occurring, this is currently going through governance & planning stages for delivery of the service improvement. Highly likely that the issues will continue to delay the UIG batch jobs until the fix is implemented. Change proposal raised and approved. This will be implemented during Gemini maintenance window on Friday morning (with the caveat that the issue does not occur Thursday evening). So the first actual run in Production will be Friday evening. Fix was successful on Friday morning. Performance has been monitored over the last 3 days, and average run time for UIG allocations is around 2 hours instead of 6-8 hours | Xoserve | Closed | 2018-09-11
893054 | 2018-08-24 | Amendment Invoice | The UGR charge in the Amendment Invoice is incorrect. The total national Unidentified Gas reconciliation value is correct, but the allocation to individual Shippers is incorrect. | Error in the brought forward Shipper throughput values for market shares of UIG reconciliation allocation from the previous month | The correct allocation of Unidentified Gas reconciliation will be calculated and an adjustment invoice will be issued week commencing 3rd September 2018 | Xoserve | Open
896574 | 2018-09-05 | IX file transfer service unavailable | Inbound and outbound file flow for Shippers impacted |  | · Service Provider has configured and installed new kit for all affected shippers and the file flow has restarted. | Xoserve | Closed | 10/09/2018
899761 | 2018-09-14 | Gemini - Demand Attribution Failed for 16:00hrs | Demand did publish for 16:00 hrs. Latest NDM nomination and UIG nomination will not be visible on the screen, this will impact shipper's gas buying decision | Demand Attribution failed for 16:00 hrs. | Gemini Application Support team have retriggered the Demand Attribution job. | Xoserve | Closed | 2018-09-14
907330 | 2018-10-04 | Data Enquiry Service currently unavailable | When trying to access the data enquiry portal, the system is timing out and not allowing users to access the portal | Root cause analysis currently in progress to understand the cause | P2 Incident Management process Available 04/10/18 at 3.45pm | Xoserve | Closed | 2018-10-04
911178 / 918851 | 2018-10-08 | Delay in issuing some of the CFR files on 8th October | Small number of Confirmation response files not submitted to Shippers. 14 Shippers affected. | Files failed to process in AMT Marketflow. | All Shippers contacted directly and details of the files submitted. | Shipper | Closed | 2018-10-18
911345 | 2018-10-09 | Delay in issuing some of the CFR files on Thursday 4th October | Incoming Shipper - For impacted Shippers, a response to their confirmation request was not sent within two Supply Point Systems business days. Outgoing Shipper - For impacted Shippers, withdrawal notifications and confirmation cancellation notifications were also delayed. | We are investigating the root cause with our vendor and are awaiting their conclusions. | P2 Incident Management process being followed. Data sets of affected meter points will be issued to customers. All files were issued on Tuesday 9th October and Wednesday 10th October. | Xoserve | Closed | 2018-10-31
911345 | 2018-10-09 | Multiple confirmation responses in the Confirmation Response File (CFR) for the same confirmation request sent on 4th October. | Incoming Shipper - For impacted shippers, multiple confirmation reference numbers were issued for the same confirmation request. This means you have received two unique confirmation responses for the same transaction (meter point), one of which will be invalid. Outgoing Shipper - For impacted shippers, you have received two withdrawal notifications for your own confirmation. | We are investigating the root cause with our vendor and are awaiting their conclusions. | P2 Incident Management process being followed. Data sets of affected meter points will be issued to customers. Issued affected customers with a data set containing their impacted meter points on Friday 12th October. | Xoserve | Closed | 2018-10-31
907423 | 2018-10-22 | 43 files not processed in Marketflow, files stuck in Marketflow due to database issue, affected 15 Shippers. | 43 files submitted on the 4th October were not processed. Files affected: Supply Point update files, RGMA files and Class 3 & 4 read files. | Root Cause Analysis being carried out | P2 Incident Management process being followed. All affected customers contacted providing data sets of affected meter points, assessment of impacts to processes with delay in processing delay and request to process files. Following processing of files customers were contacted with details of any rejected records due to delay in processing. All rejections resolved. | Xoserve | Closed | 2018-10-31
923446 | 2018-10-28 | Two Confirmation files not processed. | Manual processing required to following a connectivity issue on 28th October. Two files were missed. | Manual error, 2 files were overlooked and not processed until Shipper raised a query. | Both Shippers contacted on 1st November with details. | Shipper | Closed | 2018-11-02
922156 | 2018-10-28 | Gemini - Hourly capacity data is not published for IP auction | Gemini hourly capacity data not published for IP auctions from 23:00 on 28/10/28 to 04:00. on 29/10/18. | An outage at Prisma from 16:00 till 23:00 affected Gemini as files from Prisma were not received. After 23:00 Prisma team have restarted the auctions and Gemini received the hourly auction data for 04 hour bar at 23:32. | P2 Incident Management process being followed. | Gemini App Support Team | Closed | 2018-10-29
922161 | 2018-10-29 | EU nominations placed by the shippers will not be confirmed until we receive files from BBL and IUK TSOs | EU nominations placed by the shippers were confirmed late as we received the acknowledgement files late in Gemini. | Gemini B2B team have identified the files are stuck in B2B hence they have restarted the services to process the files. | P2 Incident Management process being followed. Gemini team confirmed the files have been received & & Nominations confirmed at 01.55 on 29/10/18. | Gemini App Support Team | Closed | 2018-10-29
936152 | 2018-11-30 | Gemini - UIG Nomination Job Overrunning | There has been a delay in publishing the UIG nomination values in Gemini. The 10:00am UIG nomination process is still running. This has caused the 11:00am UIG nominations to not start. | The monthly Annual Quantity (AQ) update has overrun due to a large number of records. This has caused a delay to the 10:00am UIG nomination job in Gemini. The AQ job completed at 11:45am but the UIG nomination process is still in progress. The next UIG job was due to start at 11:00am, however this will be put on hold and the nomination job at 1:00pm will be run instead. | P2 Incident Management process being followed. The delay in publishing the UIG nomination values in Gemini are now publishing as scheduled. The 10:00am UIG values are now available and the 1:00pm UIG values have been triggered. This has completed and the UIG nominations are updating normal. | Gemini App Support Team | Closed | 2018-11-30
937188 | 2018-12-03 04:17 | Users unable to query Data Enquiry Servoce (DES) | Users unable to access DES due to high system utilisation. DES not available from 04:17 to 05:37 | Formula year AQ/SOQ extraction and the monthly NLSP load were running in parallel and causing the high utilisation. | Jobs have been cancelled and system availability has been restored. | Is Operations | Closed | 2018-12-03 05:57
938847 | 2018-12-08 | Connectivity issue with NG Metering | Daily reads file (.DLC) not received from DMSP at usual time due to a connectivity issue with the IX. | router fault as the circuit tests showed no issues | Contingency process involved to ensure KPIs were met. Engineer attended the data centre under the instruction of Vodafone to reboot the router | IS Operations | Closed | 2018-12-09
945238 | 2018-12-31 | Daily Read file (.MDR) not issued before 14:00 hrs. | Delay in submitting the daily reads file to Shippers (.MDR) file. | UK Link – AMT Market flow slowness / performance issue | AMT Market flow team restarted the server, confirmed that files processing as normal & backlog cleared. | Is Operations | Closed | 2018-12-31
947237 | 2019-01-07 | Issue with sending the NTS Exit Capacity Invoice | The NTS Exit Capacity Invoice (.NXC) for the December 2018 billing period failed to send due to the CHARGE_ITEM_REF_NUMBER being 10 digits. Previously it has always been a maximum of 9 digits but due to incrementation it is now 10 digits. This is a mandatory field in the file formats with a numeric field length of 9 digits. | This is due to the incrementation of the charge item reference number from 9 digits to 10 digits | 1. All affected customers will be contacted individually to request their preferred method to deliver the invoices: via IX or via email in .CSV or excel format 2. All invoices were issued on the 7th January 2019 via email for customers we were not able to contact 3. Contact all remaining customers on the 8th January 2019 to advise the invoices were issued on the 7th January via email 4. A change to the file formats to be requested to amend the field length from 9 to 12 digits 5. Checks carried out on all file formats to ensure this issue does recur with any other invoice or file 6. Proposal issued to Shippers & DNs on 21/01/2019 for a fix to be deployed for the CHARGE_ITEM_REF_NUMBER to be restarted from 976,789,400, this can be effective for the February 2019 billing period NTS Exit Capacity Invoice due to be issued on 6th March 2019. Customers will be contaqcted to request approval of this approach. Approach confirmed. | Xoserve | Closed | 2019-01-24
950723 | 2018-01-19 | Daily Read file (.MDR) not issued before 14:00 hrs. | Delay in submitting the daily reads file to Shippers (.MDR) file for Class 1 meter points. | Issue caused due to defect deployment performed affecting daily reads process. | IS team made the necessary changes and redeployed the code in production. DLC jobs has been completed and MDR file has generated and issued at 7pm. | Xoserve | Open
950723 | 2019-01-23 | Incorrect energy and incorrect estimated daily reads for Class 1 and 2 meter points | Incorrect energy for Class 1 and 2 meter points for Gas Flow Day (GFD) 18th January 2019 and incorrect estimated daily reads for Class 1 and 2 meter points issued in the MDR file for GFD 20th, 21st, 22nd and 23rd January 2019 | On 18th January 2019 a P2 incident (950723) was raised due to a batch failure which resulted in a delay issuing the daily reads (MDR file) to Shippers. The files were issued at 7:00pm on 19th January when they should have been issued by 2:30pm. Unfortunately, this had a knock on affect to subsequent days; 1. The actual Calorific Value (CV) was not loaded into UK Link on 19th January for GFD 18th January. Therefore the energy calculated used an estimated CV value. 2. Estimated reads, where an actual read was not received/accepted, was not calculated for GFD 19th January and was not loaded into Gemini nor issued to Shippers (via the MDR file). 3. Any estimated reads required for GFDs 20th, 21st, 22nd and 23rd January did not calculate correctly. The energy was correct but the meter reading issued in the file (MDR) was incorrect. | 1. For GFD 18th January 2019, the energy was recalculated on 23rd January using the actual CV and were issued to Gemini before the final batch run on 23rd January. The allocation process re-ran which updated the DM and UIG allocations. This took place within exit close out (GFD+5) therefore there was no impact to final allocations or Energy Balancing. 2. For GFD 19th January 2019 the estimated reads were calculated on 23rd January and issued to Gemini before the final batch run on 23rd January. The allocation process re-ran which updated the DM and UIG allocations. This took place within exit close out (GFD+5) therefore there was no impact to final allocations or Energy Balancing. The estimated reads were issued to Shippers via the MDR file on 23rd January. 3. For GFD 20th, 21st, 22nd and 23rd January the estimated reads were recalculated on 23rd January and issued to Shippers via the MDR file on 23rd January. There was no impact to Gemini processes as the estimated energy is correct in Gemini. | Xoserve | Open
954337 | 2019-01-31 | Delay in publishing UIG Gas Nominations for 1st Feb. | Delay in publishing the UIG Gas Nominations for 1st Feb | Gemini: UIG Nomination Day Ahead Batch Job Failed Due to Incorrect Meter ID Entries in file to gemini | 1. Deleted entries in the file (AAQ) 2. UIG process re-ran | Xoserve | Closed | 2019-01-31
955031 | 2019-02-02 | EU Nominations are not getting confirmed | EU Nominations in Gemini are not getting confirmed affecting 6 Shipper. | Service restarted, files started to flow successfully without any issues. | Service restarted, files started to flow successfully without any issues. Affected Shippers informed A P3 (955067) ticket has been raised for monitoring | Xoserve | Closed | 2019-02-02
959618 | 2019-02-18 | Demand attribution is not published for 17th and 18th gas day | Gas nominations & allocations not published for the 17th & 18th February in Gemini. |  | 1. Workaround implemented to publish the Demand Attribution for 17th and 18th gas day. 2. Confirmation received at 03:00 that data visible. Data unavailable from 00:27 to 03:00. | Xoserve | Closed | 2019-02-18
962629 | 2019-02-25 | CMS Unavailable | CMS - Application is currently unavailable between 12:04 to 13:10. | File Exchange service went down. P3 ticket has been raised for monitoring | 1. CMS services restored at 13:10 2. RCA & monitoring | Xoserve | Closed | 2019-02-27
963956 | 2019-02-27 | Gemini application will be unavailable | Unavailability of Gemini from 03:01 to 09:13 meaning Users will not be able to perform any of the business process untill the services are restored. | P3 ticket (964561) has been raised for monitoring | 1. Gemini services restored at 09:13 2. Catch up of all batch processes . 3. Monitoring & RCA. | Xoserve | Closed | 2019-02-27
Insert new rows above this line

## Open AQ Issues
Defect No. | Description | Volume | Customer Impact | Priority | Potential Volume | Potential Materiality | Expected Fix Date | Expected Consumption Correction Date | Expected AQ Correction Date | Tracked by AMS/AML Team? | Reason why no impact to Amendment Invoice | Update as of 08th March 2019 | Status | Issue Profiled | Date Affected Meter Points Issued
1045 | Following read replacement prior to a shipper transfer the reconciliation is missing any read between the replaced read and the shipper transfer read. The replaced read should reconcile back to the next subsequent read, instead it is reconciling to the shipper transfer read. | 1260 | The incorrect energy will be used in the AQ process for calculating a revised AQ | Medium (3) | Low | Medium | Deployed on 18/09/2018 | 15th March 2019 | 15th March 2019 | Yes |  | AQs will be recalculated mid February & issued in the NRL files at the end of February. The revised AQs will be effective from 1st March. The Formula Year AQ (FYAQ) will also be updated, effective 1st April 2019. | Open | Yes | 2018-12-12
863 | Incorrect volume and energy calculated where a read is replaced via the UKLink SAP screens (by Xoserve users) | TBC | The incorrect energy will be used in the AQ process for calculating a revised AQ | Low | Low | Low | Deployed 18/09/2018 | 15th March 2019 | 15th March 2019 | Yes |  | Profiling for this defect was sent on 11th February 2019 AQs will be recalculated mid March & issued in the NRL files at the end of March. The revised AQs will be effective from 1st April. The Formula Year AQ (FYAQ) will also be updated, effective 1st April 2019. | Open | No
1122 | Incorrect consumption on RGMA removal MRO when there is an RGMA update for the removal date. | approx. 2,000 | The incorrect energy will be used in the AQ process for calculating a revised AQ | Low | Medium | Medium | 05/04/2019 | 15th March 2019 | 15th March 2019 | No | Does not affect the creation of a reconciliation or the charges. | The enduring fix is on target. The AQs will be calculated for 1st April effective date. The Formula Year AQ (FYAQ) will also be updated, effective 1st April 2019. | Open | Yes | 2018-12-12
1089 | On the final read (FINX) submitted on a meter update (RGMA) the system is using the round the clock count (TTZ) on the FINX read and for the transfer read where the asset update read is used as the transfer read. This creates an incorrect inflated volume between the asset update read (FINX) and the opening read (OPNT). | Approx. 350 | The incorrect energy will be used in the AQ process for calculating a revised AQ | Medium | Low | Medium | Deployed 11/01/2019 | Completed | Completed | No | Does not affect the creation of a reconciliation or the charges. | AQs will be recalculated mid March & issued in the NRL files at the end of March. The revised AQs will be effective from 1st April. The Formula Year AQ (FYAQ) will also be updated, effective 1st April 2019. | Open | Yes | 2018-12-12
XRN4676 | Where a cyclic read is present for the same day as an final (FINT) read (outgoing shipper transfer read) the system is currently applying an incorrect/duplicate energy and creates reconciliation charges against the one day reconciliation between cyclic and Final read | 5200 | The incorrect energy will be used in the AQ process for calculating a revised AQ | Medium | Low | Medium | 1st June 2019 | Completed | Completed | Yes |  | Consumption and AQ have now been corrected | Open | Yes | 2018-12-12
1073 | Where an asset exchange is received & accepted post a Class change from any class to class 3, volume/consumption is calculated incorrectly which results in an incorrect AQ. | 26 | The incorrect energy will be used in the AQ process for calculating a revised AQ | High | Low | Medium | Deployed 22/02/2019 | 15th March 2019 | 15th March 2019 | No | Does not affect the creation of a reconciliation or the charges. | Contacted affected shippers with MPRNs and plan to fix. | Open | No
1199 | Volume and energy calculated wrong where Read insert between actual and estimated shipper transfer with TTZ of 1 (inserted using manual read screen). | Linked to 1052 | The incorrect energy will be used in the AQ process for calculating a revised AQ | High | Low | Medium | 22nd March 2019 | Completed | Completed | Yes |  | This defect is linked to the fix for 1052 | Open | No
1305 | The WAALP period in AQ calculation is being ignored for the period where Meter point is in DE status resulting in incorrect AQ as the consumption during this period is being | TBC | The incorrect energy will be used in the AQ process for calculating a revised AQ | Medium | Low | Low | TBC | TBC | TBC | No | Does not affect the creation of a reconciliation or the charges. |  | Open | No

## Closed AQ Issues
Defect No. | Description | Volume | Customer Impact | Priority | Potential Volume | Potential Materiality | Expected Fix Date | Expected Consumption Correction Date | Expected AQ Correction Date | Tracked by AMS/AML Team? | Reason why no impact to Amendment Invoice | Update as of 12th March 2019 | Status | Issue Profiled | Date Affected Meter Points Issued
1043 | The AQ calculation process should only consider consumption history on or after the backstop date. Functionality prior to fix on 12th July 2018 was not considering any reads where the read date is equal to the backstop date. Therefore a revised monthly AQ will not be calculated. This scenario will apply in the following cases: 1. New meter points confirmed on or after 1st June 2017 where the confirmation effective date is the backstop date for AQ calculation process. 2. Following an AQ Correction, the effective date of the corrected AQ is the backstop date. | 9922 | Potential impacts: The consumption period is reduced for the purposes of the monthly AQ process. | Low |  |  | Deployed on 12/07/2018 | Completed | Completed | No | Does not have an impact on the energy used for Reconciliation process. | Defect fixed, consumption corrected & AQ's re-calculated & issued end of November 2018 in the .NRL files. Revised, corrected AQs will be effective 1st December 2018. | Closed | Yes | 2018-07-11
937 | Where a consumption adjustment is received for a DM meter point (Class 1 and 2 only) during the period of an asset update, the consumption adjustment is rejected. Only affects Class 1 and 2 meter points. | TBC. Linked to defect 974. | For the AQ process the original consumption will be used, not the revised consumption. | Low |  |  | Deployed on 08/08/18 | N/A | N/A | No | Reconciliation is not created. | N/A | Closed | Yes | 2018-07-11
1067 | Where an estimated transfer read is replaced (via the Shipper Agreed read process) the consumption and energy calculated from the replaced read is incorrect. | 67474 | The incorrect energy will be used in the AQ process for calculating a revised AQ. | Medium (1) |  |  | Deployed | Completed | Completed | No | Does not have an impact on the energy used for Reconciliation process. | Defect fixed, consumption corrected & AQ's re-calculated & issued end of November 2018 in the .NRL files. Revised, corrected AQs will be effective 1st December 2018. | Closed | Yes | The MPRNs known as at 30/07/2018 issued on 03/08/18
985 | Where an RGMA asset update is submitted and accepted between D & D+5 of the effective date of the transfer, the energy is calculated incorrectly. Volume & energy for asset read is being calculated, should be recorded as zero as the volume & energy is calculated from transfer read. | 11,855 as at 7th August | The incorrect energy will be used in the AQ process for calculating a revised AQ | Medium (2) |  |  | Deployed in R2.02 on 27/07/2018 | Completed | Completed | Yes |  | Defect fixed, consumption corrected & AQ's re-calculated & issued end of November 2018 in the .NRL files. Revised, corrected AQs will be effective 1st December 2018. | Closed | Yes | The MPRNs known as at 04/07/2018 issued on 06/07/18
1040 | Where a read is received for a Class 4 Prime & Sub site the read is not triggering an AQ calculation | 49 | No AQ for Class 4 P&S sites. | Low |  |  | Deployed as part of R2.05 | Completed | Completed | No | Does not affect the creation of a reconciliation or the charges. | Defect fixed, consumption corrected & AQ's re-calculated & issued end of November 2018 in the .NRL files. Revised, corrected AQs will be effective 1st December 2018. | Closed | No | Will be provided once the fix is deployed
XRN4742 | When a shipper carried out a reconfirmation the new UKLink system required a reading for the Final read (FINT) and the Opening read (OPNT). It was an agreed approach at the time of migration to load a consumption of zero for OPNT and FINT reads and leave all the consumption against the latest read. This was carried out for 175k NDM Supply Meter Points. This approach was taken as it was deemed too difficult to apportion in the Energy, however will/has caused incorrect AQ and possibly FYAQ calculations since Nexus Go Live | 156k | The incorrect energy will be used in the AQ process for calculating a revised AQ | High |  |  | 2018-11-09 | Completed | Completed | No | Does not affect the creation of a reconciliation or the charges. | Defect fixed, consumption corrected & AQ's re-calculated & issued end of November 2018 in the .NRL files. Revised, corrected AQs will be effective 1st December 2018. | Closed | No | TBC
933 | Where an estimated transfer read is generated and loaded with a TTZ (Through the Zeros) count of one, on receipt of the next actual read the energy calculated is incorrect. Estimate loaded with TTZ of 1, when Shipper replaces the read the TTZ count is used to calculate the energy. A negative consumption should have been created. | 166 | The incorrect energy will be used in the AQ process for calculating a revised AQ | High |  |  | Deployed in R1.21 on 04/05/2018 | Completed | Completed | Yes |  | Defect fixed, consumption corrected & AQ's re-calculated & issued end of November 2018 in the .NRL files. Revised, corrected AQs will be effective 1st December 2018. | Closed | Yes | The MPRNs known as at 04/07/2018 issued on 06/07/18
947 | Where an incoming Shipper is supplying the Opening Read D-5 and D-1 of the actual shipper transfer date, the outgoing shipper is also submitting a cyclic read within this transfer window which is causing the volume/energy to be calculated incorrectly. This is affecting the AQ values calculated. | 4242 | The incorrect energy will be used in the AQ process for calculating a revised AQ | High |  |  | Deployed on 14/10/2018 | Completed | Completed | Yes |  | Defect fixed, consumption corrected & AQ's re-calculated & issued end of November 2018 in the .NRL files. Revised, corrected AQs will be effective 1st December 2018. | Closed | No | TBC
| For AQ Corrections submitted & accepted in December 2018 with an effective date of 1st January 2019, UKLink did not update the AQ correctly. | 1122 | Incorrect values submitted to Shippers and used in gas allocations | Medium |  |  | 2019-01-09 | N/A | N/A | No | Does not affect the creation of a reconciliation or the charges. | AQs corrected in Gemini for the 1st to 4th January within GFD+5 correcting gas allocations. Uklink updated with correct AQ & FYAQ and affected shippers notified on 10th january 2019 of the correct values. DEs updated from 11th january 2019. | Closed | Yes | 2019-01-10
1137 | Where an estimated transfer reading has been created with a round the clock of 1 and the subsequent actual read confirms the meter/convertor has not clocked a negative consumption should be created, instead we are seeing large consumptions. | N/A | The incorrect energy will be used in the AQ process for calculating a revised AQ | N/A |  |  | N/A | N/A | N/A | Yes |  | This is a duplicate of defect 1052. Closed 07/02/2019. | Closed | No | N/A
1266 | Where there has been a consumption adjustment applied for a period which includes the Final Transfer Read (FINT) the AQ calculation process is not taking the comsumption adjustment into consideration | 194 | The incorrect energy will be used in the AQ process for calculating a revised AQ | High |  |  | Deployed 16/02/2019 | Completed | Completed | No | Does not affect the creation of a reconciliation or the charges. | Defect deployed and closed | Closed | No
XRN4740 | When a Site Visit read is submitted a Check to Check Reconciliation is carried out back to the previous Site Visit read. When the AQ calculation is triggered the energy between each cyclic read as well as the energy calculated between the Check to Check Read is being used by the AQ calculation process, resulting in increased energy and an incorrect AQ value. | Approx 17000 | The incorrect energy will be used in the AQ process for calculating a revised AQ | High |  |  | Deployed 16/02/2019 | Completed | Completed | No | Does not affect the creation of a reconciliation or the charges. | Defect deployed and closed | Closed | Yes | 2018-12-12
1052 | The energy calculation is incorrect where there is an estimated read used for reconciliation, the TTZ of -1 is being used in the calculation. | 947-1049 | The incorrect energy will be used in the AQ process for calculating a revised AQ | High |  |  | Deployed 19/01/2019 | Completed | Completed | Yes |  | Consumption and AQ have now been corrected | Closed | Yes | 2018-12-12
1125 | Where a Site Visit for a Class 4 Sites with AMR fitted is received and accepted and a subsequent cyclic read has already been processed, the system is not recognising the site visit read (Check Read) and is not recalculating the volume/energy between the site visit read and the cyclic read. | 923 | The incorrect energy will be used in the AQ process for calculating a revised AQ | Low |  |  | Deployed 31/01/2019 | Completed | Completed | Yes | Does not affect the creation of a reconciliation or the charges. | Consumption and AQ have now been corrected | Closed | Yes | 2018-12-12
1288 | For some Prime-sub setup there is no net off volume calculated at the prime site even though the sub site has consumption. This results in the AQ being calculated as 1 which inturn impacts the FYAQ values. | TBC | The incorrect energy will be used in the AQ process for calculating a revised AQ | High |  |  | N/A | N/a | N/A | Yes | Does not affect the creation of a reconciliation or the charges. | Defect closed as duplicate of defect 720 | Closed | N/A | N/A