## Slide 1: DSC Change Committee Summary – 13th March ‘19
7 New change proposals raised – 4 approved, 2 deferred for an initial review, 1 for information
XRN4865 Amendment to Treatment and Reporting of CYCL Reads – Approved to proceed to the Delivery Sub Group (DSG).
XRN4866 – Removal of Validation on Uncorrected Read (UIG Recommendation) – Approved to proceed to DSG.
XRN4869 – DC (Date Centre) Exit Programme – Progress updates to be presented to ChMC frequently. This agenda item was for information only.
**XRN4871 – Modification 0665 – Changes to Ratchet Regime - Approved to proceed to DSG.
XRN4876 - Changes to PARR Reporting – providing further data to PAFA to aid analysis of performance reporting – Deferred for a 10 working day initial review consultation within the March Change Pack.
**XRN4867 Service Description Table - Approved to proceed to be passed to CoMC. This is only a documentation change to the DSC Service Description Table.
XRN4888 – Removing duplicate address update validation for IGT Supply Meter Points via Contact Management Service (CMS) - Deferred for a 10 working day initial review consultation within the March Change Pack.
** DSC impacting, likely to require action from CoMC members

## Slide 2: DSC Change Committee Summary – 13th March ‘19
4 New change proposal post initial review:
XRN4850 Notification of Customer Contact Details to Transporters –proceed to DSG for solution development, but return to April’s ChMC for approval of the funding arrangements. DN’s have a view iGT should part fund the change.
XRN4851 Moving Market Participant Ownership from SPAA to UNC/DSC –This change was presented to ChMC only to give an update on the progress of the consultation period. Change to be presented for approval to proceed to DSG in April.
XRN4853 UIG Recommendation 3.1 Option 5 (Interim process to monitor & manually load rejected reads into UK Link where the read was rejected for reason code MRE00458 only) – Approved to go into delivery, action on Xoserve to liaise with customers as not all want reads to be loaded on their behalf
XRN4860 National Temporary UIG Monitoring (Projection of National UiG from Allocation through to reconciliation (Code Cut-off Date)) - This change was presented to ChMC only to give an update on the progress of the consultation period. Change to be presented for approval to proceed to DSG in April.

## Slide 3: DSC Change Committee Summary – 13th March ‘19
2 Solution/Delivery option approvals, and one deferral
  XRN4772 – Composite Weather Variables
    Approved to proceed with the recommended solution option and for implementation in the June 2020 release
  XRN4790 – Introduction of Winter Read Consumption Reports and Associated Obligation
    The preferred solution option and Xoserve’s intention to implement this change at some point in April 2019 were approved
  XRN4686 – Smart Metering Report
    Approval decision deferred to the ChMC meeting in April due to questions around the value of the report, awaiting recommendation from DSG and the Change Proposer.
Implementation plan – approved
Change Documents – 3 approvals and one deferral
  BER for XRN4686 Smart Metering Report - deferred
  BER for XRN4790 - Introduction of winter read consumption reports and associated obligation (Mod 0652) – approved
  CCR for XRN4542 - Changes to the Shipper Portfolio Summary Report – approved
  CCR for XRN3667a Formula Year AQSOQ to proposing Users via API - approved

## Slide 4: DSC Change Committee Summary – 13th March‘19
Release Updates:
  Release 3 (due to be delivered 2nd November 2018)
    Track 2 – Successfully Implemented on 1st/2nd February 2019
    XRN4534 (RGMA Validation Updates) implemented on 1st March
  February 2019 release
    Documentation Release implemented on 1st March
    Minor Release Drop 3 implemented on 16th February
  June 2019 release
    Currently tracking Amber – greatest risk is centred around resource
  XRN4665 – Creation of new end user categories (2 stage release Jul & Sept)
    Currently tracking Amber – re-planning activities undertaken, risk on resources, also used sharing environment with GB Charging MOD
  Minor Release Drop 4 (Scope and Delivery Plan)
    Presented for information
  November 2019 Release – Delivery Plan – MT Required for 4621 (Suspension of the validation between Meter Index and Unconverted Convertor Index) ChMC agreed that DSG can look at the implications of carrying out MT just for XRN4621 and provide a recommendation to ChMC in April.
Change Assurance update for June and EUC provided
https://gasgov-mst-files.s3.eu-west-1.amazonaws.com/s3fs-public/ggf/2019-03/7.7%20Change%20Assurance%20Update%20-%20June%202019%20and%20EUC.pptx

## Slide 5: DSC Change Committee Summary – 13th March ‘19
Standard agenda item updates:
  CSS consequential change update
  XRN4695 UIG Taskforce update
  Amendment invoice update
  Finance and Budget update
  Bubbling under report (MODs)
  Plan on a page:
    Gemini
    UK link changes
    Prioritisation of Data Office changes (new standing agenda item, which ChMC welcomed)

## Slide 6: DSC Change Committee Summary – 13th March ‘19
AOB items:
IX Refresh Update
  Link to Document
Published Change Proposals – from 1st April all new Change Proposals will be published on Xoserve.com, not the JO website
DSC Change Management Governance Group (verbal)
XRN4795 Amendment to PARR Reports (PAC approved change for delivery)
  Link to Document
Change Pack process on Xoserve.com (verbal)
Strategy on the future of MIS
  Link to Document