## Slide 1: UIG Task Force Progress Report
Change Management Committee 13/03/19

## Slide 2: Background
Modification 0658: ‘CDSP to identify and develop improvements to LDZ settlement processes’ approved by Ofgem on 6th July 2018
  Modification raised to authorise the CDSP to assign resources and incur costs related to a task force to investigate the causes and influencers of Unidentified Gas (UIG), with a target of reducing the volatility and scale of UIG and developing a robust predictive model for daily UIG for use by all parties.
BER for Change Reference Number XRN4695: ‘Investigating causes and contributors to levels and volatility of Unidentified Gas’ approved at ChMC on 11th July 2018
  This Change Proposal added an additional service line into the DSC to enable Xoserve access to investigate, using resources and technology, causes and contributors to levels and volatility of Unidentified Gas. Xoserve is to provide monthly update reports and recommend proposals and subsequent changes or modifications for the industry.
The following slides provide:
  Task force dashboard
  POAP
  Recommendation stats
  Reporting on budget
  Task force next steps

## Slide 3: UIG Task Force: Dashboard
G
RAG | 
Time | G
Cost | G
Benefit | N/A
Progress since last month - key milestones | Workstream | Date | Status
Attend UIG working group | IA & AA | 22/01/19 | C
Run UIG Recommendation day under UIG work group banner | IA & AA | 28/01/19 | C
Attend CoMC | Task force | 20/02/19 | C
Attend UIG working group | Task force | 26/02/19 | C
Raise CRs & CPs to support recommendations allocated to Xoserve | Task force | 29/01/19 - completed | C
Create and publish UIG Investigation Guide | Taskforce | 15/02/19 | C
Publish post sprint executive summary | Taskforce | 15/02/19 | C
Priorities for next month – key milestones | Workstream | Date | Status
Draft Mod/support Eon – 12.1 & 12.3 - Site specific Conversion factors |  | W/c 4/03/19 | G
Draft Mod – 12.2 - Standard conversion factors |  | W/c 4/03/19 | G
Draft Mod – 3.2.1 - Automatically change meter read frequency to monthly where AQ increases above 293,000 |  | W/c 4/03/19 | G
Draft Mod – 3.2.1 – Reduce qualifying period for Class 1 |  | W/c 4/03/19 | G
Draft Mod – 3.2.1 – Automatically convert site to Class 1 and install DM equipment. |  | W/c 4/03/19 | G
Attend UIG working group |  | 25/03/19 | G
Attend March Change Management Committee |  | 13/03/19 | G
Attend March Contract Management Committee |  | 20/03/19 | G
Overall RAG status:*

## Slide 4: Plan on Page
Delivery team milestone
Advanced Analytics
I
DSC ChMC governance
C
Completed activity
 | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | 
 | 05/11 | 12/11 | 19/11 | 26/11 | 03/12 | 10/12 | 17/12 | 24/12 | 31/12 | 07/01 | 14/01 | 21/01 | 28/01 | 04/02 | 11/02 | 18/02 | 25/02 | 04/03 | 11/03 | 18/03 | 25/03 | 01/04
Issue analysis and tracking (Investigation Tracker updated and published bi-weekly)
Develop and manage shipper action plans (linked to Investigation Log)
22/10 Action plan template developed
Sprint 5
Sprint 6
I
07/11 DCS ChMC
I
12/12 DSC ChMC
C
Sprints 4-6 to continue at the same pace and follow directly after the initial sprints to maintain momentum and ensure existing team resources are fully utilised. A 14-day stand-down period applies at any time.
08/11 Sprint 4 Exec Summary
22/11 Sprint 5 Exec Summary
05/12 Sprint 6 Exec Summary
C
C
Develop Findings template and Recommendation Packs
I
09/01 DSC ChMC
28/01 CUSTOMER RECOMMENDATION DAY
C
Investigation Analysis
Develop Xoserve owned Recommendation options – update and publish recommendation tracker in line with UIG working group meetings
I
13/02 DSC ChMC
15/2 Post Sprint Exec Summary
C
15/2 Published Investigation Guide
C
I
13/03 DSC ChMC
Draft Mods to support recommendations
Support Mod development

## Slide 5: 13 Findings – 85 Recommendation lines - where we are
1 CR4868 in progress
1 CR4867 in progress
1 CP4853 in progress
2 ongoing engagement using existing MI
85 recommendation lines
3 lines – Xoserve (3.2.1) = 3 MODS
7 review April
19 lines Future review
2 review May
3 review July
3 review November
4 review December
8 lines - PAC /Xoserve
3 lines – EON & Xoserve = 1 MOD
37 lines CLOSED
As at 04/3/19
9 lines – Xoserve (12.2) = 1 MOD
6 lines In progress
1 CP4866 in progress
All future reviews include non task force related changes that are pending, defects with planned resolution dates, other options which may be considered if engagement/PAC reporting does not deliver results. (PAC can look to deliver these when PAC reporting is updated).
Notes: 85 lines in recommendation tracker
37 lines closed = 3.2.1 option 1, 5, 8 & 9. 3.2.2 option 1, 2, 3, 4, 5, 7a, 8. 1 option 1,5 &8. 12.1&12.3 options 1, 5, 7, 8 & 9b. 12.2 option 1. 3.2.8 option 1, 6, 10 & 11. 3.1 option 1, 3, 4, 8 & 9. 2 option 1, 2 & 3. 13.2.2 option 1 & 2. 13.2.5 option 1, 2 & 3.
8 lines PAC/Xoserve action = 3.2.1 option 3 & 4. 3.2.2 option 10. 1 option 4 & 7. 12.1&12.3 option 3 & 6. 3.2.8 option 5.
3 lines EON/Xoserve MOD = 12.1&12.3 option 9a, 10, & 11.
9 lines Xoserve draft mod – 12.2 options 2,3,4,5,6,7,8,9&10.
3 lines Xoserve draft mod 3.2.1 options 6,7 & 10.
6 lines in progress =
2 ongoing engagement 12.1&12.3 option 2, 3.2.8 option 2 – using current MI shipper performance packs
1 CP in progress - 3.1 option 5 – 3.2.1 option 7 - CP4853 manual workaround
1 CP in progress – CP4866 removal of validation on uncorrected read
1 CR in progress – 3.2.1 option 2 - CR4867 sites over 58.6m kWh that need reconfirming
1 CR in progress – 1 option 2 - CR4868 class 1&2 read rejections
18 lines for future review =
7 review April 3.2.2 option6, 7b & 9. 1 option 3, 6 & 9. 12.1&12.3 option 4.
2 review May 2 option 5 & 6.
3 review July 3.2.1 option 11. 3.2.8 option 3 & 4.
3 review November 3.1 option 6&7, 2 option 7,
4 review December 3.2.8 option 7, 8 & 9. 2 option 4.

## Slide 6: Overview Of Taskforce Funding

## Slide 7: Taskforce Next Steps
Use the UIG working group as the mechanism to share progress on all recommendations where options residing with Xoserve.
Provide updates to the “Recommendation Tracker” in line with UIG Working Group timescales.
Continue analysis on investigation lines & publish investigation tracker updates bi-weekly.
Publish any new findings/recommendations drawn from investigation lines which are currently “work in progress” when completed.
Continue the customer engagement, progress the CPs & CRs raised to support the recommendation options agreed at 28th January UIG-Recommendation session.
Drafting MODs to progress agreed recommendation options.
Lead the creation of new PAC reports as per the agreed recommendation options.

## Slide 8: External Assurance?
External party has approached Xoserve to carry out:
  Assurance of findings/recommendations/analysis to date – No challenge received to date, output supports other shippers’ analysis
  Supporting draft modifications – Taskforce on target with Mods drafting
  Costs benefit analysis of all options – unclear if this could be delivered
Change Managers to consider:
  Is there an appetite/need
  Impacts to current workload timescales/resource
  Costs/impact to budget