## Slide 1: Xoserve IX Refresh
Customer Update
04/04/2019

## Slide 2: IX Refresh Customer Update
Welcome to the March update of the IX Refresh Project
Our focus during March has been to work on improvements identified from the learnings from the pilot which will incorporate into the rollout and most importantly enhancing the customer experience.
Following on from this we have been busy planning the next pilot which we are anticipating by the end of April 2019. This will allow us to test and assure ourselves of the improvements that we have identified as well as identifying further improvements.
In the meantime line installation continues as well as ongoing work with our suppliers. Whilst we appreciate that the improvements outlined will have an impact on the timelines we will look to identify efficiencies during the delivery phases of the program where possible and we will provide further information in future updates.
Again I would like to reiterate our overriding aim is to make this process as seamless as possible ensuring the installation experience meets your expectations. If you’d like more detailed information about dates relevant to your migration, please email box.xoserve.IXEnquiries@xoserve.com
Thank you for your ongoing support and I look forward to updating you again in April.
Michelle Callaghan
People Platform Director

## Slide 3: Look Forward: IX Program Quarterly Activity
Three Month Timeline
April
IX Server image to be amended based on findings from the Pilot V1
Updated server to be tested with a Proof of Concept (PoC) V2
Pilot V2 site migration
Ongoing initial line installations to continue across all phases
Router installations to take place at some phase one sites
Prepare May migrations
Continue to engage customers with Disaster Recovery equipment about testing approach
Continue to engage relevant customers requesting additional IP range / addresses for IX End User equipment
May
Rollout begins with Phase One
Relevant sites contacted to have servers installed
Prepare June migrations
Phone line installations to continue
June
Rollout continues for line, router and server installations
Customers contacted to have servers installed
Prepare July migrations
Phone line installations to continue
Please be assured that you will be contacted by Gamma before either your Network survey or phone line installation takes place (dependant on the complexity and IX option required).
If you have any queries answers to the most commonly asked questions can be found on our website in the Q&A section here.

## Slide 4
June
August
September
October
April
May
Phase One
Network and Router Installation
Server Installation
Phase Two
Phase Three
Phase Four
Remaining Sites
(Where surveys are outstanding)
High level migration plan – Current & future view
Phase Five
July
PoC V2
Pilot V2