## Slide 1: XRN4732 - June 19 Release - Status Update
1st April 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | System Testing : Testing has commenced and is continuing to plan to be completed by 29th April Plan: Tracking to plan, detailed testing phases have been planned out, implementation planning and assessment has started alongside System Testing Funding: The BER was approved by ChMC at the 09th January 19 meeting |  |  | 
Risks and Issues | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, AML/ASP etc) and all requirements are able to be met Environments– There is a risk that multiple projects are running in parallel (EUC, June 19 & GB Charging) a detailed assessment of plans and co-existence in pre-production is in progress |  |  | 
Cost | Project delivery costs are tracking to approved budgets |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 2: XRN4732 - June 19 Release Timelines
Key Milestone Dates:
Build and UT has completed
ST+SIT has now commenced

## Slide 3: June 19 Release Summary
June 19 Release consists of 3 changes:
  XRN4670 - Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date
  XRN4687 - PSR updates for large domestic sites
  XRN4676 - Reconciliation issues with reads recorded between D-1 to D-5
The agreed implementation date is the 28th June completing and going live with the changes on the 29th June 09:00

## Slide 4: High Level Implementation Timeline
The implementation for the 3 changes consists of code transports only across our PO, AMT and ISU systems.
We will need to close our EFT channels in order to implement the AMT changes as part of XRN4687

## Slide 5: File Format Transition plan
Change ID | Last inbound in Old File Format (Time = File Processing) | Last Outbound in Old File Format (Time = File Processing) | First Inbound in New File Format (Time = File Processing) | First outbound processed in New File format (Time = File Processing)
XRN4687 | 28/06/2018 CNC – 23:00:00 CNF – 23:00:00 | 28/06/2018 TRF – 08:00:00 CNR and CFR will be processed after CNC and CNF execution at 23:00:00 | 29/06/2018 CNF – 11:00:00 CNC – 18:00:00 | 29/06/2018 TRF - 09:00:00 CFR – 12:15:00 CNR – 18:00:00
To incorporate the changes in the file formats the EFT channels will need to be closed in order to implement the validation changes in AMT
  CNF/CFR – Conditionality changes
  TRF – Occurrence changes
  CNC – no file change but rejection code changes
We will follow the standard processing times of the files below and ensure that they are all processed before we close the channels
The new CNF file format will be effective for files received after 23:00:01 on the 28/06/19. The change in rejections for the CNC file will be applicable to any files received after this point
All old file formats are expected to be received by 22:59:59
Monitoring of all inbound files and confirmation of all response outbound files will be completed between 23:00:01 and 23:59:59 prior to closing the channels