## Slide 1: R&N Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2019 | 2020
June-19
Sept-19 (EUC)
Nov-19
CSS CC
RETRO
UIG
Mod 678 – GB Charging
Feb-20
June-20
Nov-20
Assumes February Release continue to be documentation only release
Assumes RETRO will be Nov 2020 Major Release Delivery
Please note that this is all potential activity within UK Link over the next 24 months
Minor Release D4

## Slide 2: 2019 / 2020 R&N Delivery Timeline
2019 | 2020
Assumes February Release continue to be documentation only release
Assumes RETRO will be Nov 2020 Major Release Delivery
Please note that this is all potential activity within UK Link over the next 24 months
Jun-19
Build
Testing
Imp
PIS
EUC
Build
Testing
Imp #1
PIS
Imp #2
PIS
Nov-19
Capture
Initiation
Design
Build & UT
ST
SIT
UAT
Reg / Pen Test
Imp
PIS
MT
MR
Potential Activity
CSS CC
HLD
Detailed Design
System / Internal Acceptance / Pen Testing
SIT / Reg Test
MT
IMP
Retro
Nov-2020
UIG
2020
ST
SIT
SUPT
UKL PT
UKL ST
UKL AT & RT
UT
UKL RT
UAT
IDR
IMP
PIS
Mod678 – Uk Link Impacts
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
J | F | M | A | M | J | J | A | S | O | N | D

## Slide 3: 2019 / 2020 R&N Governance Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2019 | 2020
Assumes February Release continue to be documentation only release
Assumes RETRO will be Nov 2020 Major Release Delivery
Please note that this is all potential activity within UK Link over the next 24 months
Jun-19
BER Approval 09/01/19
Sep-19 / EUC
BER Approval 09/01/19
Nov-19
BER Approval
10/04/18
EQR Approval
06/02/19
Change Pack Issue
08/05/19
MR
Potential Activity
ChMC Scope Approval
10/04/19
RETRO
Potential Activity
Governance Approval dates tbc
On track
At risk
Key
Complete
Feb-20
Potential Activity
Governance Approval dates tbc
BER Approval
10/04/19

## Slide 4: Change Index – R&N Allocated Change
Proposed Release | XRN | Change Title | Current Status | Xos Proposed Prioritsation Score | Proposed R&N Release | Complexity | Finance
June 19 | 4670 | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | In Delivery | 27% | June 2019 | Low | Xoserve
 | 4687 | PSR updates for large domestic sites | In Delivery | 37% | June 2019 | Low | Shippers
 | 4676 | Reconciliation issues with reads recorded between D-1 to D-5. | In Delivery | 67% | June 2019 | Medium | Xoserve
Sept 19 | 4376 | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | In Delivery | 31% | September 2019 | High | NTS
 | 4665 | Creation of new End User Categories | In Delivery | 52% | June/Sep-2019 | High | Shippers
Nov-19 | 4679 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | CP high level solution approved at ChMC | 41% | November 2019 | Medium | Xoserve
 | 4725 | New read reason type for LIS estimate readings | CP high level solution approved at ChMC | 28% | November 2019 | Medium | Xoserve
 | 4621 | Suspension of the validation between meter index and unconverted index | CP high level solution approved at ChMC | 29% | November 2019 | Tbc | Shipper

## Slide 5: Change Index – R&N Unallocated External Impacting Changes
Proposed Release | XRN | Change Title | Current Status | Xos Proposed Prioritsation Score | Indicative R&N Release | Complexity | Finance
Unallocated | 4777 | Acceptance of Contact Details Updates | A7 - CP awaiting ChMC solution approval | 32% | Minor Release Drop 4 | Tbc | Shippers
 | 4795 | Amendments to the PARR (520a) reporting | Approved | 44% | Minor Release Drop 4 | Tbc | PAC
 | 4780 | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | A5b - Undergoing Solution Impact Assessment | 27% | Minor Release Drop 4 | Tbc | Tbc
 | 4803 | Removal of validation for AQ Correction Reason 4 | A7 - CP awaiting ChMC solution approval | 71% | Minor Release Drop 4 | Tbc | Shippers
 | 4871 | Modification 0665 – Changes to Ratchet Regime | A2 - CP proposed for ChMC | 27% | Minor Release Drop 4 | Tbc | Tbc
 | 4866 | UIG Recommendation – removal of validation on uncorrected read | A5 - CP in capture with DSG | 28% | Nov-19 | Tbc | Tbc
 | 4851 | Moving Market Participant Ownership from SPAA to UNC/DSC | A5 - CP in capture with DSG | 47% | Feb 2020 | Tbc | Tbc
 | 4645 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | A5a - Solution Development | 44% | June 2020 | Tbc | Shippers/DN
 | 4772 | Composite Weather Variable (CWV) Improvements | Approved | 44% | June 2020 | Tbc | Shippers / DN
 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | A10 - ICAF - Capture complete, awaiting CIO PM assignment | 41% | June 2020 | Tbc | Tbc
 | 4850 | Notification of Customer Contact Details to Transporters | A5 - CP in capture with DSG | 33% | June 2020 | Tbc | Tbc
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | A2 - CP proposed for ChMC | 32% | June 2020 | tbc | tbc
 | 4801 | Additional information to be made viewable on DES | A5 - CP in capture with DSG | 29% | June 2020 | Tbc | Tbc
 | 4474 | Delivery of Retro | A9 - Internal change progressing through capture | 48% | 2020 | Tbc | DN
 | 4584 | Central Switching Services | A9 - Internal change progressing through capture | 20% | 2020 | Tbc | Shippers
 | 4627 | Consequential Central Switching Services | B1 - Start Up In Progress (Awaiting PAT/RACI) | 51% | 2020 | Tbc | Shippers
 | 4854 | Transfer of NDM sampling obligations from Distribution Network Operators to the CDSP | A5a - Solution Development | 29% | Unallocated | Tbc | Tbc
 | 4713 | Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | A5b - Undergoing Solution Impact Assessment | 32% | Unallocated | Tbc | Shippers