## Slide 1: DSC Change Committee Update
10th April 2019 meeting

## Slide 2: New Change Requests
Xoserve Ref No. | Change title | Next steps | Service area | DSC impact
4894 | Shipperless and Unregistered Pre-Payment Supply Point reconciliation | Deferred - Understand if ‘permissions’ are needed | 16 | Potential new service line
4914 | Modification 0651 Retrospective Data Update Provisions | Approved for Capture | New? | Potential new service area
4850 | Notification of Customer Contact Details to Transporters | Approved for Capture | 16 | Potential new service line
4851 | Moving Market Participant Ownership from SPAA to UNCC | Approved for Capture | 3 | Potential new service line
4860 | National Temporary UIG monitoring / Impact of Reconciliation on temporary UIG over time | Approved for Capture | 3 | Potential new service line
4876 | Change to PARR reporting | Approved for Capture |  | No impact to service lines
4888 | Removing Duplicated Address Update Validation for IGT Supply Points via CMS | Approved for Capture | 3 | No impact to service lines

## Slide 3: Change Proposals – Capture complete
Xoserve Ref No. | Change title | Next steps | Service area | DSC impact
4686 | Smart Metering Report | Rejected to be closed | n/a | 
4691 | IGT and GT File Format (CGI Files) | Approved for delivery June 2020 | 10 | No impacted expected on service lines

## Slide 4: Change Documents
BER approvals
    XRN4550 – Gemini replatforming
    XRN4653 – iConversion Phase one
    XRN4828 – November 2019 release
Amended BER approvals
    XRN4732 – June 2019 release
    XRN4665 – Creation of new End User Categories
CCR approval
    XRN4572 – Release 3
    XRN4802 – Minor release drop 3

## Slide 5: Summary key messages
Change Proposal raised for Retrospective Data Update Provisions (XRN4914)
November 19 major release BER approval
Release 3 close down report approved
    Under budget
All releases currently tracking to plan
    June 2019 major release
    Creation of New End User Categories
    November 2019
Change congestion over the coming 24 months, Xoserve to present options next meeting