## IP - In Analysis
UK Link Modification Implementation Plan - In Analysis
Functional Changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | Change Pack Publication | 2008.2 | 2018-07-13 | 2018-07-27 | 2018-08-03 | X | X | X | X | X | NA | Still undertaking discussions at DSG. We are looking at several distibution mechanisms and will test how the Change Pack process would work for each one. 30/10/2018 - The intention will be to include this within the scope of the new Xoserve website design plans. 30/01/2019 - We are currently working on some requirements to include this within a 'phase 2' implementation of the new website. 27/03/2019 - Build is expected to be completed in Mid-April, ready for May's Change Pack publication
4833 | NA | Roll Out of Business Intelligence and Data Discovery Capability | N/A | N/A | N/A | N/A | X | X | X | X |  | NA | XRN4833 was implemented on 7th May 2019 Since the go-live of UK Link the CDSP have been using a cloud based data discovery and Business Intelligence (BI) technology to monitor and analyse internal data. It is proposed that this capability is now rolled out to their customers to complement and enhance current Business Intelligence (BI) / analytical insight provisions. The opportunity to leverage this CDSP capability provides customers a new and more visual way to receive and interpret the data services we are able to provide. By offering this externalised flexible and scalable BI/MI solution our complete customer base would gain a much broader ability to obtain not only the market data they are looking for but to also be made aware of other information that may be of significance to them as an organisation.

## IP - For Approval - Design
UK Link Modification Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4679 | N/A | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | 2293.8 - RJ - ES | 2019-04-12 | 2019-04-30 | 2019-04-30 | X |  |  |  |  | TBC | 2019-05-08 | 2019-11-08 | This Change is within the scope of the November 2019 Release. The Design Change Pack has closed out and Xoserve seeks approval of the Detail Design specification.
4725 | N/A | New Read Reason type for LIS Estimate Readings | 2293.9 - RJ - ES | 2019-04-12 | 2019-04-30 | 2019-04-30 | X |  |  |  |  | TBC | 2019-05-08 | 2019-11-08 | This Change is within the scope of the November 2019 Release. The Design Change Pack has closed out and Xoserve seeks approval of the Detail Design specification.
4621 | N/A | Suspension of the Validation between Meter index and Unconverted Index | 2293.7 - RJ - ES | 2019-04-12 | 2019-04-30 | 2019-04-30 | X |  |  |  |  | TBC | 2019-05-08 | 2019-11-08 | This Change is within the scope of the November 2019 Release. The Design Change Pack has closed out and Xoserve seeks approval of the Detail Design specification.
4376 | 678/597/611 | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | 2293.4 - RJ - ES | 2019-04-12 | 2019-04-30 | 2019-04-30 | X |  | X |  |  | TBC | 2019-05-08 | 2019-09-08 | The purpose of this Change Pack was to notify System Users of the changes that will be deployed on 8th September 2019 in readiness for a 1st October 2019 effective date.
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## IP - Approved Last Meeting
UK Link Modification Implementation Plan - Approved on 10th April 2019
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4665 | N/A | Creation of New End User Categories | 2264.3 - RJ - ES | 2019-03-15 | N/A | N/A | X | X |  | X |  | 2280 - RJ - ES | 2019-04-10 | Part A - 03/08/2019 Part B - 31/08/2019 Contingency - 07/09/2019 | This was a revised version of the Design Change Pack we distributed on 21st December 2018 (2184 – RJ – ES), and is for information only. In the revised version, we have confirmed that no functional changes are required to Gemini, and there are no external impacts to existing Gemini processes. Furthermore, we have also included the two implementation dates as discussed at the Change Management Committee (ChMC) meeting on 13th March : • Part A on 3rd August 2019 to make new End User Category (EUC) bands allowable in SAP ISU to share new EUC bands with the industry via the T67 file • Part B on 31st August 2019 (with a contingency date of 7th September 2019 if required) to implement all code changes to processes affected by new EUC bands We will confirm the above implementation dates at the ChMC meeting on 10th April 2019.
Documentation Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
7274 | Peterborough Power Outage | 2019-05-18 | 20:00 | 2019-05-19 | 8:00 | This is a planned annual activity and permits the site facilities contractor to complete essential maintenance to the high voltage electrical distribution equipment at the Peterborough Datacentre site. Infrastructure impacts: All TTD/DR/Standby servers and equipment at Peterborough will be powered down during the outage Application Impacts: There will be no impact to production Gemini and Gemini Exit systems as these operate from the primary datacentre at Kettering. There will be no impact to production CMS as this system operates from the primary datacentre at Kettering. There will be no impact to production UK Link as this system operates from the primary datacentre at Woking. | 10/04/2019 / 08/05/2019
TBC | UK Link Portal and CMS | 2019-08-16 | 23:00 BST | 2019-08-17 | 10:00 BST | The purpose of this notification is to provide Change Management Committee with an early notification of the UK Link Disaster Recovery Tests in 2019. Further communications regarding the impact of the test will be issued shortly. | 2019-05-08
TBC | UK Link Portal | 2019-08-17 | 23:00 BST | 2019-08-18 | 07:00 BST | The purpose of this notification is to provide Change Management Committee with an early notification of the UK Link Disaster Recovery Tests in 2019. Further communications regarding the impact of the test will be issued shortly. | 2019-05-08