## Slide 1: XRN4665 – EUC Release
08/05/19 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Testing : ST & SIT activities commenced as per plan and currently running to schedule and on track for completion OUAT activities commenced as per plan Implementation : Internal Implementation Approach approved Part A on 03/08 to make new EUC bands allowable in ISU to enable sharing of new EUC bands with Industry via the T67 file Part B on 31/08 (with a contingency date of 07/09 if required) to implement all code changes to processes affected by new EUC bands |  |  | 
Risks and Issues | Environments– There continues to be a risk that multiple projects are running in parallel (EUC, June 19 & GB Charging). A detailed assessment of co-existence in Pre-production is currently in progress with relevant project teams. However the current view is that this should not impact the EUC release. |  |  | 
Cost | Project delivery costs are tracking to approved budgets |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 2: XRN 4665 - EUC Release Timelines
Key Milestone Dates:
ST/SIT activities currently tracking to schedule and on track to complete by milestone date of 03/05
OUAT activities have commenced as per plan
Internal discussions continue to finalise an agreed PIS duration (to include first usage monitoring)