## Slide 1: UK Link Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2019 | 2020
June-19
Sept-19 (EUC)
Nov-19
CSS CC
RETRO
UIG
Mod 678 – GB Charging
Feb-20
June-20
Nov-20
Assumes February-2020 Release continue to be documentation only release
Assumes RETRO will be Released Nov 2020
Please note that this is all potential activity within UK Link over the next 24 months
Minor Release D4

## Slide 2: 2019 / 2020 UK Link Delivery Timeline
2019 | 2020
Jun-19
Build
Testing
Imp
PIS
EUC
Build
Testing
Imp #1
PIS
Imp #2
PIS
Nov-19
Capture
Initiation
Design
Build & UT
ST & SIT
UAT
RT
Test Cont
IDR
PT
MR
Potential Activity – MiR 4
CSS CC
HLD
Detailed Design
System / Internal Acceptance / Pen Testing
SIT / Reg Test
MT
IMP
Retro
Retro
UIG
Potential Activity
ST
SIT
SUPT
UKL PT
UKL ST
UKL AT & RT
UT
UKL RT
UAT
IDR
IMP
PIS
Mod678 – Uk Link Impacts
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
J | F | M | A | M | J | J | A | S | O | N | D
Assumes February-2020 Release continue to be documentation only release
Assumes RETRO will be Released Nov 2020
Please note that this is all potential activity within UK Link over the next 24 months
PIS

## Slide 3: 2019 / 2020 UK Link Governance Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2019 | 2020
Assumes February Release continue to be documentation only release
Assumes RETRO will be Nov 2020 Major Release Delivery
Please note that this is all potential activity within UK Link over the next 24 months
Jun-19
BER Approval 09/01/19
Sep-19 / EUC
BER Approval 09/01/19
Nov-19
BER Approval
10/04/18
EQR Approval
06/02/19
Change Pack Issue
04/2019
MiR 4
Potential Activity
ChMC Scope Approval
10/04/19
RETRO
Potential Activity
Governance Approval dates tbc
On track
At risk
Key
Complete
Feb-20
Potential Activity
Governance Approval dates tbc
BER Approval
10/04/19
Jun - 20
Change Pack Issue
Dec-19
BER Approval
Sept-19
EQR Approval
Jul-19
Scope Approval
Jun-19

## Slide 4: Change Index – UK Link Allocated Change
Proposed Release | XRN | Change Title | Current Status | Xos Proposed Prioritsation Score | Proposed R&N Release | Complexity | Finance
June 19 | 4670 | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | In Delivery | 27% | June 2019 | Low | Xoserve
 | 4687 | PSR updates for large domestic sites | In Delivery | 37% | June 2019 | Low | Shippers
 | 4676 | Reconciliation issues with reads recorded between D-1 to D-5. | In Delivery | 67% | June 2019 | Medium | Xoserve
Sept 19 | 4376 | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | In Delivery | 31% | September 2019 | High | NTS
 | 4665 | Creation of new End User Categories | In Delivery | 52% | June/Sep-2019 | High | Shippers
Nov-19 | 4679 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | In Delivery | 41% | November 2019 | Medium | Xoserve
 | 4725 | New read reason type for LIS estimate readings | In Delivery | 28% | November 2019 | Medium | Xoserve
 | 4621 | Suspension of the validation between meter index and unconverted index | In Delivery | 29% | November 2019 | Tbc | Shipper
CSS | 4627 | Consequential Central Switching Services | In Delivery | 51% | 2021 | High | Shippers

## Slide 5: Change Index – UK Link Unallocated External Impacting Changes
Proposed Release | XRN | Change Title | Current Status | Xos Proposed Prioritsation Score | Indicative R&N Release | Complexity
Unallocated | 4866 | UIG Recommendation – removal of validation on uncorrected read | Awaiting ChMC Scope Approval | 32% | Nov-19 | High
 | 4777 | Acceptance of Contact Details Updates | Awaiting ChMC Scope Approval | 32% | Minor Release Drop 4 | Medium
 | 4780 | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | Awaiting ChMC Scope Approval | 27% | Minor Release Drop 4 | Medium
 | 4803 | Removal of validation for AQ Correction Reason 4 | Awaiting ChMC Scope Approval | 71% | Minor Release Drop 4 | Low
 | 4851 | Moving Market Participant Ownership from SPAA to UNC/DSC | CP in Capture | 39% | Feb 2020 | Tbc
 | 4645 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | CP in Capture | 44% | June 2020 | Tbc
 | 4691 | CSEPs: IGT and GT File Formats (CGI Files) | Solution Approved | 32% | June 2020 | Tbc
 | 4692 | CSEPs: IGT and GT File Formats (CIN Files) | Requirement Sign-Off | 32% | June 2020 | Tbc
 | 4772 | Composite Weather Variable (CWV) Improvements | Solution Approved | 47% | June 2020 | Medium
 | 4801 | Additional information to be made viewable on DES | Requirement Sign-Off | 35% | June 2020 | Tbc
 | 4850 | Notification of Customer Contact Details to Transporters | Requirement Sign-Off | 35% | June 2020 | Tbc
 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | In HLSO | 49% | June 2020 | Tbc
 | 4871 | Modification 0665 – Changes to Ratchet Regime | In Solution Review | 27% | June 2020 | Tbc
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | Requirement Sign-Off | 32% | June 2020 | Tbc
 | 4896 | Failure to Supply Gas System and Template Amendment | In HLSO | 31% | June 2020 | Tbc
 | Mod647 | Opening Class 1 Reads to Competition | In HLSO | High | June 2020 | Tbc
 | 4914 | Mod 651 - Retrospective Data Update Provisions | CP in Capture | 35% | 2020 | Tbc
 | 4854 | Transfer of NDM sampling obligations from Distribution Network Operators to the CDSP | In Capture | 29% | Unallocated | Tbc
 | 4930 | Requirement to Inform Shipper of Meter Link Code Change | In Capture | Tbc | Unallocated | Tbc
 | 4931 | Submission of Space in Mandatory Data on Multiple SPA Files | In Capture | tbc | Unallocated | tbc