## Slide 1: UK Link Change Horizon
Retro and CSS present two lengthy complex change programmes over 2020/21
May present constraints on ability to deliver further major releases through the 2020/21
Current business planning sets out budget for 2 major releases a year plus minor release budget
Resource requirement and environments requirements are based on the 2 major releases plus minor
The following slides show some options for meeting customer UK Link change demand fulfilment over the next 24 months.

## Slide 2: UK Link Delivery Option 1
May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | Apr | 
2019 | 2020 | 2021
GB Charging
Retro (Nov 2020)
Feb 2021
CSSC (June 2021)
Nov 2021
June 2020
EUC
Jun 19
Nov 19

## Slide 3: Delivery Option 1
Key Deliveries:
June 2020 - Major Release
November 2020 Major Release (RETRO only)
February 2021 - Major Release
June 2021 – CSSC Go Live
November 2021 – Major Release
Pro’s | Con’s
- Distinct major releases aligned to industry release dates | - Xoserve sized to deliver two major releases per year – resources/environments
- Maximised Post Implementation Support (PIS) gives improved stability to the UKLink platform | - Delivery schedule does not take into account any change freezes for Retro or CSSC (unknown at this time)
- Maximise releases prior to delivery of CSSC change | - Risk around environment availability. The approach may result in multiple projects running on same environment track
- Continuity of customer change delivery through 2020 - 2021 | 

## Slide 4: UK Link Delivery Option 2
May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | Apr | 
2019 | 2020 | 2021
Retro + Customer Change (Nov 2020)
CSSC (June 2021)
Nov 2021
June 2020
GB Charging
EUC
Jun 19
Nov 19

## Slide 5: Delivery Option 3
Key Deliveries:
June 2020 - Major Release
November 2020 Major Release - Retro and additional Customer Changes
June 2021 – CSSC Go Live
November 2021 - Major Release
Pro’s | Con’s
- Distinct releases aligned to industry release dates | - Increased complexity and risk in Nov 2020 release delivering both RETRO and BAU change
- Maximises change delivery prior to CSSC delivery | - Could add risk as expectation we would run retro as a separate delivery to BAU Nov Release but implement together
 | - Risk around environment availability – running all change for Nov 2020 on one track