## Slide 1: Request for Data Change proposals

## Slide 2: Introduction
Options for Request for Data Change Proposal process presented at DSC Governance review group on 9th May 2019
After review it was decided to recommend Option 3 with the addition of an Initial Review Change pack to run alongside Capture stage to enable DSC Customers to review change requirements
To be presented for approval at DSC Change Management committee.

## Slide 3: Proposed Definition of ‘Request for Data’
A Request for Data is:
Change Proposal requesting creation or updates to report(s) for one or more customer class
Change proposal requesting access to data where there is no functional change needed
A Request for Data is not:
A Request for Data Change Proposal must not impact on Customer systems or processes
The solution for a Request for Data must not be a functional change to CDSP systems including to SAP BW

## Slide 4: Proposed Governance Options
Solution Options
Do Nothing
Minimum Governance
Medium Governance
Any other suggestions
1
2
3
4
Problem Statement
The current DSC Change process, including the capture stage, can take several months to progress a Change Proposal through approved governance. This is appropriate for functional changes to UK Link and other Xoserve systems but does not allow for timely delivery of smaller non-functional changes such as Requests for Data. For example whilst progressing XRN4686 SMART Metering report through the end to end change process and required governance steps it was noted that the report could have actually been ready for delivery at the point of solution optioning during Capture stage with the remaining governance steps ultimately delaying delivery.

## Slide 5
Option 1 – Do nothing
Risks
No changes to current ways of working.
Cons
Request for Data changes won’t be delivered as efficiently as they could be due to the delays in taking the Change Proposals through full DSC Change Governance.
High Level Solution
To keep current DSC Change Management arrangements for Request for Data Change proposals.
Pros
Won’t need to amend current change management processes.
No changes needed to templates or documentation.
Impact on DSC Change Governance
No impact to DSC Change Governance.
Option not recommended by DSC Governance review group – 9 May 2019

## Slide 6
Option 2 – Minimal Governance
Risks
Fast track Request for Data Governance may prevent alternative solution being considered
Changes may be marked as Request for Data to attempt to override standard change governance
Cons
New ways of working being introduced to support Fast Track Governance which may feel onerous to ChMC
Introduction of new governance process that needs to run alongside existing change governance – impact on CDSP and Joint Office resources
High Level Solution
Request for Data (RFD) Change proposal raised – indicator on template selected. No initial review period. Initial vote for approval/ reject by Change Management committee offline via email or 10 minute extra ChMC approval WebEx if more than 1 week to next formal meeting.
Change goes into Capture stage where requirements are ratified by Change proposer and next DSG meeting before going into Solution Options.
At Solution Option stage Request for Data Solution to be ratified – if not needs to return to ChMC. There should be only 1 solution option for RFD change
Ad Hoc Solution Option / Design Change pack combined, including proposed implementation, and issued for responses – 10 working days
Responses to Change pack along with BER issued for Approval by ChMC – offline or 10 mins WebEx if more than 1 week to next meeting
Note: BER will only be needed for funding approval when systems changes needed for delivery of the change. Could ChMC approvals be provided retrospectively in Requests for Data Changes that are zero funded?
Change implemented as per agreed implementation.
NB: 5 days notice for Ad hoc ChMC or off-line ChMC approval
Pros
Enables fast track governance for delivery of simple Requests for Data change proposals
RFD changes can be delivered in a timely fashion not being hindered by unnecessary governance steps
Impact on DSC Change Governance
Updates would be needed to DSC Change Management procedures to cater for Request for Change alternative governance process and methods.
Update to Change proposal template
Introduction of new ways of working – WebEx/Off line ChMC etc
Joint office availability to host extra ChMC meetings
Option not recommended by DSC Governance review group – 9 May 2019

## Slide 7: Option 2 – Minimal Governance
CP sent to Xoserve for initial processing and Xoserve Reference number (XRN)
Change Proposal (CP) raised with Request for Data indicator selected
If not a single RFD Solution only Change needs to return to ChMC and continue through standard Change Governance
Change Rejected
XRN Closed
Change Approved
Requirements statement
Capture session
Define requirements
Capture session
Solution Options
Requirements ratified
Requirements ratified with CP’s proposer and/or by next DSC Delivery Sub Group (DSG)*
* May be presented/discussed at alternate groups e.g. PAC, UIG Workgroup
RFD Solution only
Yes
No
Ad Hoc Solution/ Design consultation combined
10 working days
Responses and BER sent for approval at ChMC
Build, and Test
Awareness session, if required
implementation
Closedown report approved at ChMC
Extra ChMC if needed
Extra ChMC if needed
Option not recommended by DSC Governance review group – 9 May 2019

## Slide 8
Option 3 – Medium governance
Risks
Fast track Request for Data Governance may prevent alternative solution being considered
Changes may be marked as Request for Data to attempt to override standard change governance
Cons
Introduction of new governance process that needs to run alongside existing change governance
High Level Solution
Request for Data (RFD) Change proposal raised – indicator on template selected. Initial vote for approval/ reject by Change Management Committee at next meeting. Change issued in Initial review Change Pack to run alongside Capture stage.
Change goes into Capture stage where requirements are ratified by Change proposer and next DSG meeting before going into Solution Options.
At Solution Option stage Request for Data Solution to be ratified – if not needs to return to ChMC. There should be only 1 solution option for RFD change
Solution Option / Design Change pack combined, including proposed implementation, and issued for responses as per normal timetable – 10 working days
Responses to Change pack along with BER issued for Approval by ChMC at the next meeting.
Note: BER will only be needed for funding approval when systems changes needed for delivery of the change. Could ChMC approvals be provided retrospectively in Requests for Data Changes that are zero funded?
Change implemented as per agreed implementation.
Pros
Enables fast track governance for delivery of simple Requests for Data change proposals
RFD changes can be delivered in a timely fashion not being hindered by unnecessary governance steps
Does not involved new ways of working and keeps to already agreed governance timetable
Impact on DSC Change Governance
Updates would be needed to DSC Change Management procedures to cater for Request for Change alternative governance process and methods.
Update to Change proposal template

## Slide 9: Option 3 – Medium Governance
CP sent to Xoserve for initial processing and Xoserve Reference number (XRN)
Change Proposal (CP) raised with Request for Data indicator selected
If not a single RFD Solution only Change needs to return to ChMC and continue through standard Change Governance
Change Rejected
XRN Closed
Change Approved
Requirements statement
Capture session
Define requirements
Capture session
Solution Options
Requirements ratified
Requirements ratified with CP’s proposer and/or by next DSC Delivery Sub Group (DSG)*
* May be presented/discussed at alternate groups e.g. PAC, UIG Workgroup
RFD Solution only
Yes
No
Ad Hoc Solution/ Design consultation combined
10 working days
Responses and BER sent for approval at ChMC
Build, and Test
Awareness session, if required
implementation
Closedown report approved at ChMC
Initial Review Change Pack 10 working days

## Slide 10
Option 4 – Other suggestions
Risks
To be confirmed
Cons
To be confirmed
High Level Solution
For inclusion of any other suggestions for Request for Data governance
Pros
To be confirmed
Impact on DSC Change Governance
To be confirmed
No further options suggested by DSC Governance review group – 9 May 2019

## Slide 11: Indicative minimum delivery timescales
Assumptions made:
Initial Review – 10 working days
Capture stage – 10 working days
Solution review/ Design Change pack – 10 working days
No EQR required
Can be implemented outside Major/Minor Release in 10 working days following BER approval
ChMC – held monthly/ DSG held every 2 weeks
Option 1
Do nothing
ChMC initial view
Initial Review
ChMC approval
31 working days
DSG x 2
Solution Consultation
ChMC approval
46 working days
Option 2 Minimal
Ad hoc ChMC
No Initial Review
5 working days
DSG x 1
Ad hoc Solution/ Design pack combined
25 working days
Option 3 Medium
Monthly ChMC
Initial Review at same time as Capture
10 working days
DSG x 1
Monthly Solution/ Design pack combined
31 working days
ChMC BER
Design Pack
Implementation
43 working days
Monthly ChMC approval with BER
28 working days
Ad hoc ChMC approval with BER
Implementation
15 working days
Pre-Capture
Capture
Delivery
120
working days
45
working days
69
working days
Options not recommended by DSC Governance review group – 9 May 2019