## Slide 1: XRN4828 - Nov 19 Release - Status Update
12th June 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Start Up and Initiation phases complete Detailed Design plan finalised with execution commencing on June 17th Change Packs published and approved on 8th May Funding: BER for full delivery approved in April 2019. BER for XRN4866 (UIG Recommendation – removal of validation on uncorrected read) to be presented on 12th June. |  |  | 
Risks and Issues | Risk: There is a risk that the Nov 19 Release may be impacted by Pre-Production environment congestion due to multiple deliveries running in parallel Risk: There is a risk that due to multiple UKLink deliveries running in parallel there may be limited access to resources. |  |  | 
Cost | The BER with full delivery costs were approved at ChMC in April 2019. BER for XRN4866 to be presented on 12th June. |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 2: XRN4828 - Nov 19 Release Timelines
Key Milestone Dates:
Receive supplier responses – 13/02/19
Supplier contract approval – 05/04/19
Approve and issue EQR – 04/02/19
Gain Business Case approval at IRC - 13/03/19
PID approval 12/04/19
Detailed Delivery Plan approved – 05/04/19
BER Approval – 10/04/19
Design Change Packs Approval –08/05/19
2019
Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
XRN4828
Nov-19
HLD & Change Pack Production
Design
Build & FUT
ST & SIT
UAT
RT
PT
Test Cont.
PIS
04/02: EQR Approval
10/04: BER Approval
08/05: Change Pack Approval
GO LIVE 08/11/19 - TBC
IDR