## Slide 1: UKL4914 Retro
ChMC - 12th June 2019

## Slide 2: XRN4914:Retro – Progress update
Progress update | 
Schedule | Capture – in progress Change to original request to include a Proof of Concept to gain better understanding of data quality issues Planning Capture and Start-up phases Context diagram drafted; scenarios identified Agreeing approach for capture of next level of requirement; w/c 10th June
Risks and Issues | Issue - project is behind original draft plan; assumptions to be validated to feed into re-planning Risk – that cost required to deliver project is greater than project funding (2017 day rates used) Risk – not all resources formally allocated to project Risk – availability of resources (environments/people) may impact plan for Retro
Cost | Project cost - to be re-confirmed Project funding - £1.5 mill; £700k for 2019 and £800k for 2020
Resources | Project mobilising Resources required for project being identified and seeking allocation Engaged with other programmes of work for consequential impacts / synergies (CSSC, AML/ASP, UIG) SI agreed for project w/c 3rd June – project kick-off Engagement approach to be agreed with Customers

## Slide 3: XRN4914:Retro – Planning assumptions
    Work streams to run parallel for Proof of Concept, Data Cleanse & Enduring Solution
    Proof of Concept work stream to be commenced first
    Recommend Market Trials is required – recommend minimum of 12 weeks
Assumptions to be validated
Proof of Concept
Data Cleanse
Enduring Solution
June ‘19
Nov ‘20
Market Trials
Key: dashed line – to be defined

## Slide 4: XRN4914:Retro – Key points
  Change Proposal
  Recommendation that Change Proposal is updated to incorporate Proof of Concept phase
      Customers to advise on their support of this inclusion
  Requirements
  In order to gain Customer approval for requirements; we plan to issue a schedule of Customer workshops to review each work stream (Proof of Concept, Data Cleanse & Enduring Solution)
      Schedule issued shortly to ChMC/DSG attendees