## Slide 1: XRN4732 - June 19 Release - Status Update
1st July 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Regression Testing : Testing was completed as planned on 21st June Implementation: Changes were successfully implemented and went live on 29th June PIS: PIS period commenced on 1st July and daily monitoring of 1st usage of changes in progress |  |  | 
Risks and Issues | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, AML/ASP etc) and all requirements are able to be met |  |  | 
Cost | Project delivery costs are tracking to approved budgets |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 2: XRN4732 - June 19 Release Timelines
Key Milestone Dates:
Regression Testing completed
Implementation successful and Go Live

## Slide 3: June 19 Release Summary
June 19 Release consists of 3 changes:
  XRN4670 - Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date
  XRN4687 - PSR updates for large domestic sites
  XRN4676 - Reconciliation issues with reads recorded between D-1 to D-5
Changes were successfully implemented on the 29th June with the changes going live at 09:00:00